## Schedule
10000
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last update | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process | Bitmap Days | Variant
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | No catenary | Cancellation | Re-routing | Train replacement | Delays | Other
0081 |  |  | < > | Nettingsdorf | Krift | 2023 | 2023 | 32 | 37 | 2023-08-05 | 0:00 | 2023-09-11 06:00 | 23:59 | 37d | continuous | track & rail | X | [11 empty] | N |  |  | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0081 | 60987 |  | < > | Kirchdorf a.d.Krems | Micheldorf | 2023 | 2023 | 32 | 37 | 2023-08-07 07:00 | 45145.2917 | 2023-09-11 06:00 | 45180.25 | 34d + 23h 00min | continuous | track & rail | X | LT | [8 empty] | Gleisneulage |  | N |  | 2021-06-15 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned |  |  | 00000000000000000000000000000000000 | 00
0081 |  |  | < > | Schwarzach-St. Veit | Boeckstein | 2023 | 2023 | 40 | 41 | 2023-09-30 |  | 2023-10-02 |  | 2d | continuous |  | X | [11 empty] | N |  |  | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0081 |  |  | < > | Villach Auen | Jesenice | 2023 | 2023 | 46 | 47 | 2023-11-11 |  | 2023-11-13 |  | 2d | continuous |  | X | [11 empty] | N |  |  | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0081 |  |  | < > | Abzww Villach Sued Gvbf | Staatsgrenze naechst Rosenbach | 2024 | 2024 | 12 | 13 | 2024-03-23 |  | 2024-03-25 |  | 2d | continuous |  | X | [11 empty] | N |  |  | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0081 |  |  | < > | Schwarzach-St. Veit | Boeckstein | 2024 | 2024 | 18 | 19 | 2024-05-04 |  | 2024-05-06 |  | 2d | continuous |  | X | [11 empty] | N |  |  | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0081 |  |  | < > | Traun | Rohr-Bad Hall | 2024 | 2024 | 44 | 45 | 2024-10-29 |  | 2024-11-04 |  | 5d | continuous |  | X | [11 empty] | N |  |  | unclassified | 2,3,4,5,6,7,1 | 1 | 0 |  |  |  | planned
0081 |  |  | < > | Abzww Villach Sued Gvbf | Staatsgrenze naechst Rosenbach | 2024 | 2024 | 46 | 47 | 2024-11-16 |  | 2024-11-18 |  | 2d | continuous |  | X | [11 empty] | N |  |  | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0081 | 000081-62901 |  | < | Graz-Vbf (in G) | Graz-Fbf (in G) | 2024 | 2025 | 36 | 14 | 2024-09-02 08:00 | 45537.3333 | 2025-03-31 17:00 | 45747.7083 | 210 days + 9,0 h | continuous | others |  | LT | [8 empty] | Neubau der Brücke Peter-Tunner-Gasse (Phase 2) |  | N |  | 2022-06-06 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned |  |  |  | 00
0081 | 0081-6290179 |  | < | Graz-Vbf (in G) | Graz-Fbf (in G) | 2024 | 2025 | 36 | 14 | 2024-09-02 08:00 | 45537.3333 | 2025-03-31 17:00 | 45747.7083 | 210 days + 9,0 h | continuous | others |  | LT | [8 empty] | Neubau der Brücke Peter-Tunner-Gasse (Phase 2) |  | N |  | 2022-06-06 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned |  |  |  | 00
0081 | 0081-6290177 |  | < | Graz-Vbf (in G) | Graz-Fbf (in G) | 2024 | 2025 | 36 | 14 | 2024-09-02 08:00 | 45537.3333 | 2025-03-31 17:00 | 45747.7083 | 210 days + 9,0 h | continuous | others |  | LT | [8 empty] | Neubau der Brücke Peter-Tunner-Gasse (Phase 2) |  | N |  | 2022-06-06 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned |  |  |  | 00
0081 | 0081-6290178 |  | < | Graz-Vbf (in G) | Graz-Fbf (in G) | 2024 | 2025 | 36 | 14 | 2024-09-02 08:00 | 45537.3333 | 2025-03-31 17:00 | 45747.7083 | 210 days + 9,0 h | continuous | others |  | LT | [8 empty] | Neubau der Brücke Peter-Tunner-Gasse (Phase 2) |  | N |  | 2022-06-06 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned |  |  |  | 00
0079 |  |  | < | State border | Dobova | 2023 | 2023 | 31 | 31 | 2023-07-28 19:00 | 19:00 | 2023-07-30 | 19:00 | 2 days | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | > | State border | Dobova | 2023 | 2023 | 32 | 32 | 2023-08-04 | 19:00 | 2023-08-06 | 19:00 | 2 days | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Zagorje | Zagorje | 2023 | 2023 | 6 | 40 | 2023-02-01 | 0:00 | 2023-09-30 | 23:59 | 242 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Litija | Litija | 2023 | 2023 | 35 | 52 | 2023-08-22 | 0:00 | 2023-12-31 | 23:59 | 132 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Laze | Laze | 2023 | 2023 | 23 | 29 | 2023-05-29 | 0:00 | 2023-07-11 | 23:59 | 44 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < | Sava | Litija | 2023 | 2023 | 44 | 45 | 2023-10-27 | 19:00 | 2023-10-30 | 15:00 | 68 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track + track 1 in station Litija to km 534+300 |  | N |  | 2021-12-02 | unclassified | 5,6,7,1 | 1 | 0 |  |  |  | planned
0079 |  |  | > | Sava | Litija | 2023 | 2023 | 45 | 45 | 2023-10-30 | 15:00 | 2023-11-05 | 19:00 | 148 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track + tracks 2 and 3 in station Litija to km 534+300 |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < | Litija | Kresnice | 2023 | 2023 | 28 | 36 | 2023-07-08 | 7:00 | 2023-08-30 | 19:00 | 52 days + 36 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | > | Litija | Kresnice | 2023 | 2023 | 18 | 23 | 2023-04-29 | 7:00 | 2023-05-30 | 19:00 | 30 days + 36 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | > | Laze | Ljubljana Zalog | 2023 | 2023 | 24 | 25 | 2023-06-09 | 19:00 | 2023-06-12 | 5:00 | 58 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 5,6,7,1 | 1 | 0 |  |  |  | planned
0079 |  |  | < | Laze | Ljubljana Zalog | 2023 | 2023 | 25 | 26 | 2023-06-16 | 19:00 | 2023-06-20 | 5:00 | 82 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 5,6,7,1,2 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Ljubljana | Ljubljana | 2023 | 2023 | 23 | 52 | 2023-06-01 | 0:00 | 2023-12-31 | 23:59 | 214 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Jesenice | State border | 2023 | 2023 | 46 | 47 | 2023-11-11 | 6:00 | 2023-11-13 | 6:00 | 48 hours | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Jesenice | Jesenice | 2023 | 2023 | 24 | 52 | 2023-06-07 | 0:00 | 2023-12-31 | 23:59 | 208 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | > | Hoče | Maribor Tezno | 2023 | 2023 | 45 | 47 | 2023-11-05 | 7:00 | 2023-11-18 | 19:00 | 13 days + 12 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track + tracks 1, 101, 201, 301 and 401 in station Maribor Tezno |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < | Hoče | Maribor Tezno | 2023 | 2023 | 47 | 52 | 2023-11-19 | 7:00 | 2023-12-31 | 19:00 | 42 days + 12 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track + tracks 2, 102 and 39 in station Maribor Tezno |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Maribor | Pesnica | 2023 | 2023 | 31 | 33 | 2023-07-29 | 7:35 | 2023-08-13 | 18:00 | 15 days + 10,5 hours | continuous | track & rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Maribor | Pesnica | 2023 | 2023 | 34 | 36 | 2023-08-16 | 11:45 | 2023-08-31 | 18:10 | 16 days | periodically (5 -7 hours daily, not every day) | rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Krško | Krško | 2024 | 2024 |  |  | 2024-02-17 | 0:00 | 2024-12-19 | 23:59 | 307 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Litija | Litija | 2024 | 2024 |  |  | 2024-01-01 | 0:00 | 2024-01-11 | 23:59 | 11 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < | Laze | Ljubljana Zalog | 2024 | 2024 |  |  | 2024-07-13 | 7:00 | 2024-08-11 | 19:00 | 26 days + 12 hours | continuous | rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Ljubljana | Ljubljana | 2024 | 2024 |  |  | 2024-01-01 | 0:00 | 2024-12-31 | 23:59 | 366 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Ljubljana Šiška | Ljubljana Vižmarje | 2024 | 2024 |  |  | 2024-08-10 | 7:00 | 2024-08-23 | 19:00 | 13 days + 12 hours | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Jesenice | Jesenice | 2024 | 2024 |  |  | 2024-01-01 | 0:00 | 2024-08-27 | 23:59 | 240 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Podnart | Podnart | 2024 | 2024 |  |  | 2024-02-12 | 0:00 | 2024-12-31 | 23:59 | 324 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | < > | Lesce Bled | Lesce Bled | 2024 | 2024 |  |  | 2024-03-25 | 0:00 | 2024-12-31 | 23:59 | 282 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0079 |  |  | > | Hoče | Maribor Tezno | 2024 | 2024 |  |  | 2024-02-01 | 7:00 | 2024-02-14 | 19:00 | 13 days + 12 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track + tracks 1, 101, 201, 301 and 401 in station Maribor Tezno |  | N |  | 2022-12-11 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
0078 |  |  | < > | Zagreb Zk (Kustošija) | Zagreb Gk | 2022 | 2024 | 50 | 52 |  |  |  |  | 2 years | periodical | trask & rail renewal |  | LT+ST | X | [7 empty] | Renewal of the line section: Zagreb Zk (Kustošija) - Zagreb Gk left track and right track. Permanent closure of one track for the laying of subbase, permanent closure of one track for replacing of the track, closures by day (Monday - Sunday) 6-8 hours (as needed). Possible closures of the line section Zagreb ZK-Trešnjevka fork, closures by day (Monday - Sunday) 6-8 hours (as needed), possible closuresfor 72 hours according to the needs of contractors | 0079 | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  |  | Zagreb Zapadni kolodvor | Zagreb Zapadni kolodvor | 2022 | 2023 | 37 | 52 |  |  |  |  | 15 months | periodical | station tracks renewal |  |  | X | [7 empty] | Renewal of Zagreb Zapadni kolodvor station. Closures by day (Monday - Sunday) for 6 to 8 hours, alternately left track and right track (as needed), possible closures for 72 hours according to the needs of contractors. Possible closures of the line section Zagreb ZK-Trešnjevka fork, closures by day (Monday - Sunday) 6-8 hours (as needed), possible closuresfor 72 hours according to the needs of contractors |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | < > | Dugo Selo | Novska | 2024 | 2029 | 2 | 17 |  |  |  |  | 5 years and 3 months | periodical | Upgrade, renewal, construction of the second track and construction of a new double-track line |  |  | X | [7 empty] | 8 hours day closure every working day from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the sections Dugo Selo - Sesvete, Dugo Selo - Vrbovec, Banova Jaruga - Lipik, Novska - Okučani and Novska - Hrvatska Dubica (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). If needed, possible closures longer than 72 hours. |  | N |  | 2022-12-08 | minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | > | Andrijevci | Garčin | 2023 | 2024 | 2 | 52 |  |  |  |  | 2 years | periodical | Renewal of the left track km 198+480 - 206+260 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) and possible closures up to 72 hours according to the needs of contractors |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  |  | > | Strizivojna-Vrpolje | Andrijevci | 2023 | 2024 | 2 | 52 |  |  |  |  | 2 years | periodical | Renewal of the right track 188+500 - 197+400 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) and possible closures up to 72 hours according to the needs of contractors |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  |  | > | Belgrade Center | Zemun | 2020 | 2022 | 44 | 25 | 2020-10-21 |  |  |  | 20 months | periodical | Modernization (construction and reconstruction) of the railway line Belgrade – Subotica – state border (Kelebia) section |  |  | X | [7 empty] | Works are executed with interruption of traffic along the reconstructed left track during time interval from 10:00 pm to 05:00 am |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0072 |  |  | > | Batajnica | Stara Pazova | 2021 | 2022 | 13 | 25 | 2021-03-22 |  |  |  | 15 months | periodical | Modernization (construction and reconstruction) of the railway line Belgrade – Subotica – state border (Kelebia) section |  |  | X | [7 empty] | Works are executed with interruption of traffic along the left track during time interval from 10:00 pm to 05:00 am |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0072 |  |  | > | Zemun | Batajnica | 2020 | 2022 | 47 | 25 | 2020-11-15 |  |  |  | 19 months | periodical | Modernization (construction and reconstruction) of the railway line Belgrade – Subotica – state border (Kelebia) section |  |  | X | [7 empty] | Works are executed with interruption of traffic along the left track during time interval from 10:00 pm to 05:00 am |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0072 |  |  | > | Sićevo | Dimitrovgrad | 2022 | 2024 | 2 | 25 |  |  |  |  | 2 years and 6 months | periodical | Civil engineering reconstruction of the Niš – Dimitrovgrad railway line | X |  | X | [7 empty] | Traffic functioning and works execution will be as agreed with the Contractor (72 hours - the execution of works and 96 hours - traffic functioning) |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  |  |  | Niš station | Niš station | 2022 | 2024 | 41 | 42 |  |  |  |  | 2 years | periodical | Railway bypass Niš |  |  | X | [7 empty] | Civil works on construction of railway bypass Niš |  | N |  | 2022-12-08 | minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  |  | > | Sićevo | Dimitrovgrad | 2022 | 2024 | 25 | 24 |  |  |  |  | 2 years | periodical | Electrification of the Niš – Dimitrovgrad railway line and railway bypass Niš |  |  | X | [7 empty] | Traffic functioning and works execution will be performed alternately during time intervals that are going to be agreed with the Contractor |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2026 | 19 | 11 |  |  |  |  | 5 years and 10 months | periodical | railway line km 22+554 to km 42+200 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2019 | 2024 | 41 | 39 |  |  |  |  | 5 years | periodical | railway line km 42+200 to km 62+400 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2025 | 33 | 52 |  |  |  |  | 5 years and 4 months | periodical | railway line km 62+400 to km 73 +598 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Kostenets | Septemvri | 2019 | 2024 | 15 | 33 |  |  |  |  | 5 years and 4 months | periodical | railway line | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Voluyak | Sofia | 2023 | 2024 | 50 | 50 | 2023-12-10 |  | 2024-12-14 |  | 12 months | periodical | Modernization of the railway infrastructure | X |  | X |  |  |  | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption of one of the running lines. Bypass line - Voluyak - Iliyantsi - Sofia |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Dragoman | Voluyak | 2023 | 2024 | 50 | 50 | 2023-12-10 |  | 2024-12-14 |  | 12 months | periodical | Modernization of the railway infrastructure | X |  | X |  |  |  | X |  |  |  | Construction and repair works will be carried out under the conditions of full interruption of one of the running lines. The train traffic will be conducted along a newly built running line (the railway line is doubled) |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Sofia station | Sofia station | 2023 | 2024 | 50 | 50 | 2023-12-10 |  | 2024-12-14 |  | 12 months | periodical | Modernization of the railway infrastructure | X |  | X |  |  |  | X |  |  |  | Interruption of traffic along the eastern part of the station tracks from track 8 to track 14. Partial isolation of the signalling equipment at the station. Bypass line - Voluyak - Iliyantsi - Yana - Kazichene |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Septemvri | Dobrinishte | 2024 | 2024 | 27 | 31 | 2024-07-01 |  | 2024-07-30 |  | 30 days | continuous | Repair of equipment | X | [5 empty] | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption. No bypass line is available |  | N |  | 2022-12-08 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | overpass km 97+217 | overpass km 97+217 | 2023 | 2023 | 20 | 20 | 2023-05-10 | 9:00 | 2023-05-10 | 17:00 | 8 hours | continuous | Overpass construction | X | [5 empty] | X |  |  |  | During the interruption from Plovdiv to Dimitrovgrad, a bypass route Kazichene – Karlovo – Plovdiv/transboarding is offered. |  | N |  | 2022-12-08 | major | 3 | 1 |  |  |  |  | publication
0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 23 | 23 | 2023-06-01 | 8:00 | 2023-06-02 | 8:00 | 24 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | During the interruption from Plovdiv to Dimitrovgrad, a bypass route Plovdiv-MihailovoDimitrovgrad / transboarding is offered. |  | N |  | 2022-12-08 | major | 4.5 | 1 |  |  |  |  | publication
0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 23 | 23 | 2023-06-02 | 8:00 | 2023-06-03 | 8:00 | 24 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | No capacity is offered for freight traffic/transboarding |  | N |  | 2022-12-08 | major | 5.6 | 1 |  |  |  |  | publication
0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 32 | 32 | 2023-08-01 | 8:00 | 2023-08-03 | 8:00 | 48 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | No capacity is offered for freight traffic/transboarding |  | N |  | 2022-12-08 | major | 2,3,4 | 1 |  |  |  |  | publication
New
Changed
Deleted
Map
Show all

## TCR 2023 Map SŽ-I
Zagorje – the closure of individual tracks 01.02. to 30.09.2023
Litija – the closure of individual tracks 22.08. to 31.12.2023
Laze – the closure of individual tracks 29.05. to 11.07.2023
Litija - Kresnice (LT) 08.07 to 30.08.2023 continuously
Litija - Kresnice (RT) 29.04 to 30.05.2023 continuously
Laze – Ljubljana Zalog (RT) 09.06 to 12.06.2023 continuously
Laze – Ljubljana Zalog (LT) 16.06 to 20.06.2023 continuously
Ljubljana - the closure of individual tracks 01.06.do 31.12.2023
Jesenice – the closure of individual tracks 07.06. to 31.12. 2023
Ljubljana Šiška – the closure of individual tracks 01.01. to 31.05.2023

## TCR 2024 Map SŽ-I (2)
Krško – the closure of individual tracks 17.02. to 19.12.2024
Laze – Ljubljana Zalog (LT) 13.07 to 11.08.2024
Ljubljana – the closure of individual tracks 01.01. to 31.12.2024
Jesenice – the closure of individual tracks 01.01. to 27.08.2024
Podnart – the closure of individual tracks 12.02. to 31.12.2024
Lesce Bled – the closure of individual tracks 25.03. to 31.12.2024