## Schedule
10000
| IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last update | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process | Bitmap Days | Variant
[5 empty] | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | No catenary | Cancellation | Re-routing | Train replacement | Delays | Other
| 0081 | 81-63830 |  | < > | Üst Lz 2 | Wels Hbf | 2023 | 2027 | 31 | 49 | 31.07.2023 | 00:00 | 12.12.2027 | 24:00 | 1 596 days | cont. | BFUM |  | LT | S | [5 empty] | 0 |  | ETCS-LA 160 km/h |  | N |  | 12.12.2022
| 0081 | 81-64207 |  | < > | Graz-Fbf | Graz-Vbf | 2024 | 2024 | 3 | 5 | 20.01.2024 | 14:00 | 04.02.2024 | 17:00 | 3x 27,0 h | period. cont. | SP |  | LT | [8 empty] | Einbau DSV Säulen für Bauphase 2 |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64212 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 3 | 5 | 21.01.2024 | 00:45 | 04.02.2024 | 05:00 | 3x 4,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | - Vorarbeiten (Umbau Oberleitung,...) |  | Y |  | 02.04.2023 | Medium |  |  | 100%
6 | 0081 | 81-64213 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 4 | 6 | 22.01.2024 | 00:45 | 05.02.2024 | 04:00 | 3x 3,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | - Vorarbeiten (Umbau Oberleitung,...) |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-63190 |  | < > | Werndorf | Wettmannstätten | 2024 | 2024 | 4 | 5 | 22.01.2024 | 07:30 | 29.01.2024 | 16:30 | 6x 9,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen |  | N |  | 06.03.2023 |  |  |  | 0%
| 0081 | 81-64111 |  | < > | Werndorf | Wettmannstätten | 2024 | 2024 | 4 | 7 | 22.01.2024 | 07:30 | 16.02.2024 | 16:30 | 20x 9,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Werndorf (a) - Wettmannstätten (e) |  | N |  | 06.03.2023
| 0081 | 81-65470 |  | > | Graz-Vbf Nord | Graz-Vbf | 2024 | 2024 | 4 | 5 | 27.01.2024 | 14:00 | 03.02.2024 | 22:00 | 2x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Fundierung und Maststellen |  | N |  | 13.06.2023
| 0081 | 81-65469 |  | > | Graz-Vbf Nord | Graz-Vbf | 2024 | 2024 | 4 | 5 | 28.01.2024 | 07:00 | 04.02.2024 | 17:00 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Fundierung und Maststellen |  | N |  | 13.06.2023
| 0081 | 81-64448 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 5 | 5 | 29.01.2024 | 08:00 | 29.01.2024 | 14:00 | 6,0 h | cont. | WF |  | LT |  |  |  | C |  | B |  |  | Wartungs- und Instandsetzungsarbeiten in den eingleisigen Bereichen |  | N |  | 11.09.2023
| 0081 | 81-62760 |  | < | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 6 | 8 | 05.02.2024 | 08:00 | 23.02.2024 | 16:00 | 15x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Vorarbeiten zur Erneuerung der Oberleitung: Vormontage |  | N |  | 12.12.2022
| 0081 | 81-64449 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 6 | 6 | 05.02.2024 | 08:00 | 05.02.2024 | 14:00 | 6,0 h | cont. | WF |  | LT |  |  |  | C |  | B |  |  | Wartungs- und Instandsetzungsarbeiten in den eingleisigen Bereichen |  | N |  | 13.06.2023
| 0081 | 81-64561 |  | > | Kalsdorf-Süd | Werndorf | 2024 | 2024 | 6 | 7 | 05.02.2024 | 08:30 | 14.02.2024 | 15:00 | 6x 6,5 h | period. | WF |  | LT | [6 empty] | 10 |  | Schlägerungsarbeiten |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-62900 |  | > | Graz-Vbf | Graz Hbf | 2024 | 2024 | 6 | 27 | 10.02.2024 | 08:00 | 05.07.2024 | 17:00 | 146 days + 8,0 h | cont. | SP |  | LT | [6 empty] | 10 |  | - Neubau der Brücke Peter-Tunner-Gasse (Phase 1) - Gleisneulage mit Unterbausanierung BGl 181 - Errichtung BGl 183neu (seitenrichtiges Überholgleis) |  | N |  | 03.05.2023 |  |  |  | 0%
| 0081 | 81-64206 |  | < > | Graz-Vbf |  | 2024 | 2024 | 6 | 30 | 10.02.2024 | 08:00 | 22.07.2024 | 17:00 | 163 days + 8,0 h | cont. | SP |  | ST | [8 empty] | - Abtrag BGl 641 und Einkürzung BGl 643 - Neubau der Oberleitung |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64450 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 7 | 7 | 12.02.2024 | 08:00 | 12.02.2024 | 14:00 | 6,0 h | cont. | WF |  | LT |  |  |  | C |  | B |  |  | Wartungs- und Instandsetzungsarbeiten in den eingleisigen Bereichen |  | N |  | 13.06.2023
| 0081 | 81-64529 |  | < > | Leoben Hbf | Leoben Donawitz | 2024 | 2024 | 7 | 7 | 17.02.2024 | 08:00 | 17.02.2024 | 16:00 | 8,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsfenster |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-65702 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 7 | 8 | 17.02.2024 | 08:00 | 25.02.2024 | 15:30 | 4x 7,5 h | period. | SP |  | LT | [6 empty] | 5 |  | Schlägerungsarbeiten |  | Y |  | 05.11.2023 |  |  |  | 0%
| 0081 | 81-64214 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 7 | 7 | 18.02.2024 | 00:45 | 18.02.2024 | 05:00 | 4,2 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Ausbau der Hilfsbrücke bei der Ibererstraße auf BGl 181 |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64208 |  | < | Graz-Vbf | Graz-Fbf | 2024 | 2024 | 8 | 9 | 19.02.2024 | 00:15 | 26.02.2024 | 04:00 | 8x 3,8 h | period. | SP |  | LT | [8 empty] | Einbau DSV Säulen für Bauphase 1 |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64451 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 8 | 8 | 19.02.2024 | 08:00 | 19.02.2024 | 14:00 | 6,0 h | cont. | WF |  | LT |  |  |  | C |  | B |  |  | Wartungs- und Instandsetzungsarbeiten in den eingleisigen Bereichen |  | N |  | 13.06.2023
| 0081 | 81-64534 |  | < > | Graz Puntigam | Leibnitz | 2024 | 2024 | 8 | 8 | 19.02.2024 | 08:00 | 23.02.2024 | 13:30 | 5x 5,5 h | period. | WF |  | LT |  |  |  | C |  | B | 10 |  | Diverse Instandhaltungsarbeiten im Streckenverlauf |  | N |  | 04.09.2023 |  |  |  | 10%
| 0081 | 81-65680 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 8 | 8 | 19.02.2024 | 10:45 | 19.02.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 05.11.2023 | Medium |  |  | 100%
| 0081 | 81-63191 |  | < > | Graz Puntigam | Wildon | 2024 | 2024 | 8 | 16 | 19.02.2024 | 20:30 | 19.04.2024 | 04:30 | 36x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Montage der ETCS Balisen |  | N |  | 12.12.2022
| 0081 | 81-64112 |  | < > | Graz Don Bosco | Werndorf | 2024 | 2024 | 8 | 16 | 19.02.2024 | 20:30 | 19.04.2024 | 04:30 | 36x 8,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Graz-Don Bosco (a) - Werndorf (e) |  | N |  | 06.03.2023
| 0081 | 81-62243 |  | < > | Linz Hbf |  | 2024 | 2024 | 8 | 18 | 23.02.2024 | 00:00 | 05.05.2024 | 24:00 | 72 days + 23,0 h | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Umbau Linz Hbf West / Bauphase 15 |  | Y |  | 07.08.2023
| 0081 | 81-61408 |  | > | Hallein | Üst Hl 3 | 2024 | 2024 | 8 | 9 | 23.02.2024 | 22:00 | 26.02.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 5 |  | Verlängerung Personentunnel Hallein Burgfried, Einbau HIB |  | Y |  | 03.09.2023
| 0081 | 81-65545 |  | < > | Marchtrenk | Wels Vbf-Terminal | 2024 | 2024 | 8 | 9 | 24.02.2024 | 08:00 | 26.02.2024 | 12:00 | 2 days + 4,0 h | cont. | GES | T | LT |  |  |  | C |  |  |  |  | Hilfsbrückenausbau Str10112 (Berggleis) |  | Y |  | 07.08.2023
| 0081 | 81-65674 |  | < > | Gratwein-Gratkorn | Leibnitz | 2024 | 2024 | 9 | 9 | 03.03.2024 | 01:00 | 03.03.2024 | 04:00 | 3,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Graz (Schnittstelle ETCS) |  | Y |  | 01.10.2023 | Medium |  |  | 100%
| 0081 | 81-65674 |  | < > | Gratwein-Gratkorn | Leibnitz | 2024 | 2024 | 9 | 9 | 03.03.2024 | 01:00 | 03.03.2024 | 04:00 | 3,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Graz (Schnittstelle ETCS) |  | Y |  | 01.10.2023 | Medium |  |  | 100%
| 0081 | 81-62761 |  | > | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 10 | 12 | 04.03.2024 | 08:00 | 22.03.2024 | 16:00 | 15x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Vorarbeiten zur Erneuerung der Oberleitung: Sondieren |  | N |  | 12.12.2022
| 0081 | 81-63095 |  | < | Gaishorn | Üst Was 2 | 2024 | 2024 | 10 | 10 | 08.03.2024 | 08:10 | 09.03.2024 | 16:30 | 2x 8,3 h | period. | SP |  | LT | [6 empty] | 8 |  | Tragseiltausch Gl. 1 |  | N |  | 11.04.2023
| 0081 | 81-63096 |  | < | Gaishorn | Üst Was 2 | 2024 | 2024 | 10 | 10 | 10.03.2024 | 06:00 | 10.03.2024 | 18:00 | 12,0 h | cont. | SP |  | LT | [6 empty] | 8 |  | Fahrdrahttausch und Nacharbeiten Gl. 1 |  | N |  | 11.04.2023
| 0081 | 81-63097 |  | < | Üst Was 2 | Wald am Schoberpaß | 2024 | 2024 | 11 | 11 | 15.03.2024 | 08:10 | 16.03.2024 | 16:30 | 2x 8,3 h | period. | SP |  | LT | [6 empty] | 4 |  | Tragseiltausch Gl. 1 |  | N |  | 11.04.2023
| 0081 | 81-63566 |  | < | Hallein | Üst Aj 5 | 2024 | 2024 | 11 | 12 | 15.03.2024 | 22:00 | 18.03.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 4 |  | Sanierung Brücke Einbau Hib Sgl 1 |  | Y |  | 23.08.2023
| 0081 | 81-60350 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 11 | 11 | 17.03.2024 | 00:15 | 17.03.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abtrag und Einheben der Fertigteilträger |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-63098 |  | < | Üst Was 2 | Wald am Schoberpaß | 2024 | 2024 | 11 | 11 | 17.03.2024 | 06:30 | 17.03.2024 | 18:30 | 12,0 h | cont. | SP |  | LT | [6 empty] | 8 |  | Fahrdrahttausch und Nacharbeiten Gl. 1 |  | N |  | 11.04.2023
| 0081 | 81-60408 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 12 | 12 | 18.03.2024 | 00:15 | 18.03.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abtrag und Einheben der Fertigteilträger |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-64535 |  | > | Bruck a.d.Mur-Stadtwald | Leoben Hbf | 2024 | 2024 | 12 | 12 | 18.03.2024 | 08:30 | 21.03.2024 | 13:30 | 4x 5,0 h | period. | WF |  | LT |  |  |  | C |  | B | 10 |  | Diverse Instandhaltungsarbeiten im Streckenverlauf |  | N |  | 01.05.2023
| 0081 | 81-60409 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 12 | 12 | 20.03.2024 | 00:15 | 20.03.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abtrag und Einheben der Fertigteilträger |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-60410 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 12 | 12 | 21.03.2024 | 00:15 | 21.03.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abtrag und Einheben der Fertigteilträger |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-63567 |  | > | Üst Aj 5 | Hallein | 2024 | 2024 | 12 | 13 | 22.03.2024 | 22:00 | 25.03.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 4 |  | Sanierung Brücke Einbau Hib Sgl 2 |  | Y |  | 23.08.2023
| 0081 | 81-63003 |  | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2024 | 2024 | 12 | 13 | 23.03.2024 | 07:00 | 25.03.2024 | 05:30 | 1 day + 22,5 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | Y |  | 30.08.2023 | Medium |  |  | 100%
| 0081 | 81-64562 |  | < > | Hieflau | Selzthal-Nord | 2024 | 2024 | 13 | 13 | 26.03.2024 | 08:00 | 26.03.2024 | 15:00 | 7,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Gesamtsperre - Instandsetzungsarbeiten im gesamten Streckenverlauf |  | Y |  | 01.05.2023
| 0081 | 81-64563 |  | < > | Hieflau | Selzthal-Nord | 2024 | 2024 | 13 | 13 | 28.03.2024 | 08:00 | 28.03.2024 | 15:00 | 7,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Gesamtsperre - Instandsetzungsarbeiten im gesamten Streckenverlauf |  | Y |  | 01.05.2023
| 0081 | 81-64671 |  | < > | Villach Hbf-Ostbf | Villach Westbf | 2024 | 2024 | 13 | 13 | 31.03.2024 | 01:05 | 31.03.2024 | 04:05 | 2,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Vb |  | Y |  | 11.09.2023 | Medium |  |  | 100%
| 0081 | 81-64669 |  | < > | Villach Hbf | Villach Hbf-Draubrücke | 2024 | 2024 | 13 | 14 | 31.03.2024 | 21:20 | 04.04.2024 | 03:20 | 4x 6,0 h | period. | SP |  | LT | [8 empty] | Abtrag der Oberleitung BGl 201, 203, 205 und 207 |  | Y |  | 11.09.2023 |  |  |  | 0%
| 0081 | 81-60779A |  | < > | Linz Hbf | Salzburg Hbf | 2024 | 2024 | 14 | 17 | 06.04.2024 | 00:00 | 28.04.2024 | 24:00 | 23 days | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Sperre Semmering |  | N |  | 06.02.2022 | Minor |  |  | 20%
| 0081 | 81-62156A |  | < > | Linz Hbf | Selzthal | 2024 | 2024 | 14 | 17 | 06.04.2024 | 00:00 | 28.04.2024 | 24:00 | 23 days | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Sperre Semmering |  | N |  | 06.02.2022 | Minor |  |  | 20%
| 0081 | 81-60779A |  | < > | Linz Hbf | Salzburg Hbf | 2024 | 2024 | 14 | 17 | 06.04.2024 | 00:00 | 28.04.2024 | 24:00 | 23 days | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Sperre Semmering |  | N |  | 06.02.2022 | Minor |  |  | 20%
| 0081 | 81-62156A |  | < > | Linz Hbf | Selzthal | 2024 | 2024 | 14 | 17 | 06.04.2024 | 00:00 | 28.04.2024 | 24:00 | 23 days | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Sperre Semmering |  | N |  | 06.02.2022 | Minor |  |  | 20%
| 0081 | 81-64220 |  | < > | Spielfeld-Straß |  | 2024 | 2024 | 16 | 25 | 15.04.2024 | 07:00 | 17.06.2024 | 17:00 | 63 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 0 |  | Sanierung Brücke in km 0,201 (Mühlkanal) |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-62999 |  | < > | Greifenburg-Weißensee | Abzww Str 40701 | 2024 | 2024 | 16 | 16 | 15.04.2024 | 08:40 | 17.04.2024 | 13:10 | 3x 4,5 h | period. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten |  | Y |  | 01.10.2023 | Medium |  |  | 100%
| 0081 | 81-64113 |  | < > | Graz-Fbf | Graz Don Bosco | 2024 | 2024 | 17 | 26 | 22.04.2024 | 20:30 | 28.06.2024 | 04:30 | 40x 8,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Graz Hbf. (Peter-Tunner Gasse bis Graz-Don Bosco) |  | N |  | 06.03.2023
| 0081 | 81-64113 |  | < > | Graz-Fbf | Graz Don Bosco | 2024 | 2024 | 17 | 26 | 22.04.2024 | 20:30 | 28.06.2024 | 04:30 | 40x 8,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Graz Hbf. (Peter-Tunner Gasse bis Graz-Don Bosco) |  | N |  | 06.03.2023
| 0081 | 81-62770 |  | > | Üst Bo 2 | St.Johann im Pongau | 2024 | 2024 | 17 | 21 | 22.04.2024 | 21:40 | 20.05.2024 | 05:20 | 28x 7,7 h | period. | SP |  | LT | S | [5 empty] | 3 |  | Vorarbeiten zur Gleisneulage - Schotterbettsicherung |  | N |  | 01.10.2023
| 0081 | 81-63532 |  | < > | Marchtrenk |  | 2024 | 2024 | 18 | 26 | 29.04.2024 | 00:00 | 24.06.2024 | 24:00 | 57 days | cont. | SP |  | ST | [8 empty] | Errichtung Gleis 303 neu |  | N |  | 02.04.2023
| 0081 | 81-64419 |  | < | Dorfgastein | Abzw Lof 1 | 2024 | 2024 | 18 | 18 | 29.04.2024 | 07:00 | 30.04.2024 | 17:30 | 2x 10,5 h | period. | SP |  | LT | [6 empty] | 3.5 |  | OL-Arbeiten, Sondieren |  | N |  | 02.04.2023
| 0081 | 81-60052 |  | < > | Abzww Traun West | Marchtrenk | 2024 | 2024 | 18 | 26 | 29.04.2024 | 08:00 | 29.06.2024 | 18:00 | 61 days + 10,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Erneuerung der Gleise und Oberleitungsanlagen Mak - T 4-gleisiger Ausbau, Bf Marchtrenk; Errichtung LM21 und 22 in offener Bauweise. Geänderter Ablauf aufgrund Bescheidthema |  | Y |  | 01.08.2023
| 0081 | 81-62194A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 18 | 26 | 29.04.2024 | 08:00 | 29.06.2024 | 18:00 | 61 days + 10,0 h | cont. | RES |  | LT |  |  |  | C |  | B |  |  | 4 Gleisiger Ausbau Lz - We / Umbau Bf Machtrenk Sperre Str21001 Mak - T, Errichtung LM 21 und 22 in offener Bauweise |  | N |  | 23.08.2022
| 0081 | 81-69574A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 18 | 26 | 29.04.2024 | 08:00 | 29.06.2024 | 18:00 | 61 days + 10,0 h | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Erneuerung der Gleise und Oberleitungsanlagen Mak - T 4-gleisiger Ausbau, Bf Marchtrenk; Errichtung LM21 und 22 in offener Bauweise. Geänderter Ablauf aufgrund Bescheidthema |  | Y |  | 01.08.2023
| 0081 | 81-62194A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 18 | 26 | 29.04.2024 | 08:00 | 29.06.2024 | 18:00 | 61 days + 10,0 h | cont. | RES |  | LT |  |  |  | C |  | B |  |  | 4 Gleisiger Ausbau Lz - We / Umbau Bf Machtrenk Sperre Str21001 Mak - T, Errichtung LM 21 und 22 in offener Bauweise |  | N |  | 23.08.2022
| 0081 | 81-69574A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 18 | 26 | 29.04.2024 | 08:00 | 29.06.2024 | 18:00 | 61 days + 10,0 h | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Erneuerung der Gleise und Oberleitungsanlagen Mak - T 4-gleisiger Ausbau, Bf Marchtrenk; Errichtung LM21 und 22 in offener Bauweise. Geänderter Ablauf aufgrund Bescheidthema |  | Y |  | 01.08.2023
| 0081 | 81-62542 |  | < | Villach Hbf | Abzw Gu 2 | 2024 | 2024 | 18 | 18 | 29.04.2024 | 20:10 | 04.05.2024 | 05:10 | 5x 9,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Vorarbeiten zur Gleisneulage mit Untergrundverbesserung km 164,985 - km 166,487: - Aufbau AWS - Einbau Schotterbettsicherung |  | N |  | 12.12.2022
| 0081 | 81-60343 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 18 | 18 | 01.05.2024 | 00:15 | 01.05.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-64420 |  | < | Dorfgastein | Abzw Lof 1 | 2024 | 2024 | 18 | 18 | 02.05.2024 | 07:00 | 04.05.2024 | 17:30 | 3x 10,5 h | period. | SP |  | LT | [6 empty] | 4 |  | OL-Arbeiten, Sondieren |  | N |  | 02.04.2023
| 0081 | 81-60386 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 18 | 18 | 03.05.2024 | 00:15 | 03.05.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-65424 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 18 | 19 | 03.05.2024 | 23:00 | 06.05.2024 | 04:00 | 2 days + 5,0 h | cont. | BFUM | T | LT |  |  |  | C |  | B |  |  | Umbau Bf. Jesenice |  | Y |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-60387 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 18 | 18 | 04.05.2024 | 00:15 | 04.05.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-60803 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 18 | 19 | 04.05.2024 | 05:30 | 06.05.2024 | 17:00 | 2 days + 11,5 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten im Streckenverlauf - Inbetriebnahme des neuen Schaltgerüsts Bf. Mallnitz |  | Y |  | 30.08.2023 | Medium |  |  | 100%
| 0081 | 81-62922 |  | < > | Niklasdorf |  | 2024 | 2024 | 18 | 20 | 04.05.2024 | 06:00 | 13.05.2024 | 04:00 | 8 days + 22,0 h | cont. | SP |  | ST |  |  |  | C |  |  | 30 |  | Weichenneulage W55, 56 und 57 |  | Y |  | 12.12.2022
| 0081 | 81-62941 |  | < > | Leoben West | Leoben Göss | 2024 | 2024 | 18 | 18 | 04.05.2024 | 07:00 | 05.05.2024 | 17:00 | 1 day + 10,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Inbetriebnahme ESTW Leg |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-64210 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 18 | 21 | 05.05.2024 | 00:45 | 26.05.2024 | 05:00 | 4x 4,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | - Rückbau Kabelprovisoium Brücke Ibererstraße (Gruppenkabel) - OL-Kabelziehen und Hochführen im Bereich zwischen BGl 182 und 106 |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-62942 |  | < > | Leoben Hbf | Leoben West | 2024 | 2024 | 18 | 18 | 05.05.2024 | 01:00 | 05.05.2024 | 02:30 | 1,5 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Inbetriebnahme ESTW Leg (Softwaretausch ESTW Leb) |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-64418 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2024 | 2024 | 18 | 18 | 05.05.2024 | 07:00 | 05.05.2024 | 17:30 | 10,5 h | cont. | GES | T | LT | [8 empty] | OL-Arbeiten, Sondieren |  | N |  | 02.04.2023
| 0081 | 81-62774 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 19 | 19 | 06.05.2024 | 00:00 | 10.05.2024 | 05:00 | 5x 5,0 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Vorarbeiten Ennstalsperre Vorarbeiten Errichtung Haltestelle Hüttau |  | Y |  | 31.07.2023
| 0081 | 81-64211 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 19 | 22 | 06.05.2024 | 00:45 | 27.05.2024 | 04:00 | 4x 3,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | - Rückbau Kabelprovisoium Brücke Ibererstraße (Gruppenkabel) - OL-Kabelziehen und Hochführen im Bereich zwischen BGl 182 und 106 |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64421 |  | > | Abzw Lof 1 | Dorfgastein | 2024 | 2024 | 19 | 19 | 06.05.2024 | 07:00 | 08.05.2024 | 17:30 | 3x 10,5 h | period. | SP |  | LT | [6 empty] | 3.5 |  | OL-Arbeiten, Sondieren |  | N |  | 02.04.2023
| 0081 | 81-62540 |  | > | Villach Hbf | Abzw Gu 2 | 2024 | 2024 | 19 | 20 | 06.05.2024 | 08:00 | 16.05.2024 | 16:00 | 11x 8,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Vorarbeiten zur Gleisneulage mit Untergrundverbesserung km 164,985 - km 166,487: - Kabelarbeiten - Begleitende Unterbauarbeiten |  | N |  | 12.12.2022
| 0081 | 81-64084 |  | > | Rothenthurn |  | 2024 | 2024 | 19 | 26 | 06.05.2024 | 08:00 | 30.06.2024 | 17:00 | 55 days + 9,0 h | cont. | BFUM |  | ST | S | [5 empty] | 1 |  | Bauphase 1 - Baufeldfreimachung, Vorarbeiten neben Gl. 202 - Schutz-LA v-80 Gl. 202 |  | N |  | 11.09.2023
| 0081 | 81-64006 |  | > | Rothenthurn |  | 2024 | 2024 | 27 | 27 | 01.07.2024 | 08:00 | 07.07.2024 | 16:00 | 4x 8,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 2.1 - Vorbereitung Hilfsbrückeneinbau Bereich Personentunnel neu - Rammen und Maststellen |  | Y |  | 05.02.2023
| 0081 | 81-64000 |  | > | Rothenthurn |  | 2024 | 2024 | 27 | 27 | 01.07.2024 | 22:30 | 07.07.2024 | 04:45 | 6x 6,2 h | period. | BFUM |  | ST | [8 empty] | Bauphase 2.2 - Vorbereitung Hilfsbrückeneinbau Bereich Personentunnel neu |  | Y |  | 05.02.2023
| 0081 | 81-64001 |  | > | Rothenthurn | Paternion-Feistritz | 2024 | 2024 | 27 | 27 | 06.07.2024 | 08:00 | 07.07.2024 | 16:00 | 2x 8,0 h | period. | BFUM |  | LT | [8 empty] | Bahnhofumbau Bf. Rothenthurn, Bauphase 2.1 - Rammen und Maststellen |  | Y |  | 05.02.2023
| 0081 | 81-64002 |  | < | Rothenthurn |  | 2024 | 2024 | 28 | 29 | 08.07.2024 | 22:30 | 21.07.2024 | 04:45 | 13x 6,2 h | period. | BFUM |  | ST | [8 empty] | Bauphase 3 - Vorbereitung Hilfsbrückeneinbau Bereich Personentunnel neu - OL-Masten rammen und stellen |  | Y |  | 11.09.2023
| 0081 | 81-64085 |  | > | Rothenthurn |  | 2024 | 2024 | 30 | 30 | 22.07.2024 | 08:00 | 26.07.2024 | 17:00 | 5x 9,0 h | period. | BFUM |  | ST | S | [5 empty] | 1 |  | Bauphase 4 - Erdarbeiten und Entwässerungsarbeiten neben Gl. 202 - Schutz-LA v-80 Gl. 202 |  | Y |  | 05.02.2023
| 0081 | 81-64003 |  | < | Rothenthurn |  | 2024 | 2024 | 30 | 30 | 27.07.2024 | 18:00 | 28.07.2024 | 12:00 | 18,0 h | cont. | BFUM |  | ST | [8 empty] | Bauphase 5 - Einbau HIB Bereich Personentunnel neu Bgl 201 |  | Y |  | 05.02.2023
| 0081 | 81-64004 |  | > | Rothenthurn |  | 2024 | 2024 | 30 | 31 | 28.07.2024 | 18:00 | 29.07.2024 | 12:00 | 18,0 h | cont. | BFUM |  | ST | [8 empty] | Bauphase 6 - Einbau HIB Bereich Personentunnel neu Bgl 202 |  | Y |  | 11.09.2023
| 0081 | 81-64086 |  | > | Rothenthurn |  | 2024 | 2024 | 31 | 31 | 29.07.2024 | 08:00 | 02.08.2024 | 17:00 | 5x 9,0 h | period. | BFUM |  | ST | S | [5 empty] | 1 |  | Bauphase 7 - Bauarbeiten neben Gl. 202 - Schutz-LA v-80 Gl. 202 |  | Y |  | 05.02.2023
| 0081 | 81-64005 |  | < > | Rothenthurn |  | 2024 | 2024 | 31 | 31 | 03.08.2024 | 18:00 | 04.08.2024 | 12:00 | 18,0 h | cont. | BFUM |  | ST | [8 empty] | Bauphase 8 - Hilfsbrückeneinbau Gl. 203 Bereich Personentunnel neu |  | Y |  | 05.02.2023
| 0081 | 81-64087 |  | < | Rothenthurn |  | 2024 | 2024 | 31 | 32 | 04.08.2024 | 22:30 | 09.08.2024 | 04:45 | 5x 6,2 h | period. | BFUM |  | ST | [8 empty] | Bauphase 9 - OL Vormontage Bgl 201 und 203 |  | Y |  | 05.02.2023
| 0081 | 81-64088 |  | < | Rothenthurn |  | 2024 | 2024 | 33 | 33 | 12.08.2024 | 22:30 | 18.08.2024 | 04:45 | 6x 6,2 h | period. | BFUM |  | ST | [8 empty] | Bauphase 10 - Vorbereitung Einbau Schwarzenbachbrücke NEU Bgl 1 - Herstellen Randbahnsteig - Herstellen Personentunnel - Vormontage OL Bgl 201 und 203 |  | Y |  | 05.02.2023
| 0081 | 81-64007 |  | > | Rothenthurn |  | 2024 | 2024 | 34 | 34 | 19.08.2024 | 22:30 | 25.08.2024 | 04:45 | 6x 6,2 h | period. | BFUM |  | ST | [8 empty] | Bauphase 11 - Vorbereitung Einbau Schwarzenbachbrücke Bgl 2 - OL-Vormontage - Herstellen Randbahnsteig - Herstellen Personentunnel |  | Y |  | 11.09.2023
| 0081 | 81-64089 |  | > | Rothenthurn |  | 2024 | 2024 | 35 | 35 | 26.08.2024 | 08:00 | 29.08.2024 | 17:00 | 4x 9,0 h | period. | BFUM |  | ST | S | [5 empty] | 1 |  | Bauphase 12 - Bauarbeiten neben Gl. 202 - Schutz-LA v-80 Gl. 202 |  | Y |  | 05.02.2023
| 0081 | 81-64009 |  | < | Rothenthurn |  | 2024 | 2024 | 35 | 36 | 30.08.2024 | 07:00 | 05.09.2024 | 17:00 | 6 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bauphase 13 - Einbau Schwarzenbachbrücke NEU Bgl 1 km 192,529 - Herstellen Randbahnsteig - Herstellen Personentunnel |  | Y |  | 01.08.2023
| 0081 | 81-64010 |  | > | Rothenthurn |  | 2024 | 2024 | 36 | 37 | 06.09.2024 | 07:00 | 12.09.2024 | 17:00 | 6 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bauphase 14 - Einbau Schwarzenbachbrücke NEU Bgl 2 km 192,529 - Herstellen Randbahnsteig - Herstellen Personentunnel - OL-Vormontage |  | Y |  | 01.08.2023
| 0081 | 81-64090 |  | > | Rothenthurn |  | 2024 | 2024 | 38 | 38 | 16.09.2024 | 22:30 | 22.09.2024 | 05:30 | 6x 7,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 15 - Einbau Quertragwerke für die neue OL - Herstellung Randbahnsteig - Herstellung Personentunnel |  | Y |  | 05.02.2023
| 0081 | 81-64091 |  | > | Rothenthurn |  | 2024 | 2024 | 39 | 39 | 23.09.2024 | 22:30 | 29.09.2024 | 05:30 | 6x 7,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 16 - Montage der Hängesäulen, Übernahme Bgl 2 - Herstellung Randbahnsteig - Herstellung Personentunnel |  | Y |  | 05.02.2023
| 0081 | 81-64092 |  | < | Rothenthurn |  | 2024 | 2024 | 40 | 40 | 30.09.2024 | 23:30 | 06.10.2024 | 04:30 | 6x 5,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 17 - OL Arbeiten Montage Hängesäulen, Übernahme Bgl 1 und 3 |  | Y |  | 05.02.2023
| 0081 | 81-64093 |  | > | Rothenthurn |  | 2024 | 2024 | 41 | 41 | 07.10.2024 | 22:30 | 11.10.2024 | 05:30 | 4x 7,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 18 - Demontage der alten Querfelder |  | Y |  | 05.02.2023
| 0081 | 81-64011 |  | > | Rothenthurn |  | 2024 | 2024 | 42 | 43 | 16.10.2024 | 07:00 | 23.10.2024 | 17:00 | 7 days + 10,0 h | cont. | BFUM |  | ST | [8 empty] | Bauphase 19 - Herstellen W 52 neu und Bgl 4 bis W 6 neu - Herstellen Randbahnsteig, Personentunnel, Zufahrt P&R Süd - Ausbau HIB Gl. 2 |  | Y |  | 11.09.2023
| 0081 | 81-64094 |  | > | Rothenthurn |  | 2024 | 2024 | 43 | 44 | 24.10.2024 | 08:00 | 28.10.2024 | 17:00 | 2x 9,0 h | period. | BFUM |  | ST | S | [5 empty] | 1 |  | Bauphase 20 - Aufziehen der OL Gl. 204 - Schutz-LA v-80 Gl. 202 |  | Y |  | 05.02.2023
| 0081 | 81-64095 |  | > | Rothenthurn |  | 2024 | 2024 | 44 | 44 | 28.10.2024 | 22:30 | 01.11.2024 | 04:30 | 4x 6,0 h | period. | BFUM |  | ST | [8 empty] | Bauphase 21 - OL-Kettenzug Gl. 204 (bis zur W 6 NEU) |  | Y |  | 05.02.2023
| 0081 | 81-64012 |  | > | Rothenthurn |  | 2024 | 2024 | 45 | 46 | 04.11.2024 | 07:00 | 17.11.2024 | 17:00 | 13 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bauphase 22 - Herstellen W 2, 3, und 6 neu, Abtrag W1 - Herstellen Bgl 2 Verschwenkung, Personentunnel, Brücke - Herstellen Zufahrt P&R - Ausbau HIB Gl. 2 |  | Y |  | 01.08.2023
| 0081 | 81-64013 |  | < | Rothenthurn |  | 2024 | 2024 | 47 | 48 | 18.11.2024 | 07:00 | 29.11.2024 | 17:00 | 11 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bauphase 23 - Abtrag W 2, 3, und 1d alt, Abtrag W1 - Herstellen W1, 4 neu - Vormontage OL Gl. 1 und 3 - Umbau Randbahnsteig neben Gl. 1 - Ausbau HIB Gl. 1 |  | Y |  | 01.08.2023
| 0081 | 81-64549 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 19 | 19 | 06.05.2024 | 10:45 | 06.05.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-62948 |  | > | Trieben | Rottenmann | 2024 | 2024 | 19 | 19 | 07.05.2024 | 07:30 | 08.05.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 6 |  | Lagersanierung Straßenbrücke km 154,672 - Aufbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-62775 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 19 | 19 | 08.05.2024 | 00:00 | 08.05.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | Y |  | 03.01.2023
| 0081 | 81-62776 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 19 | 19 | 09.05.2024 | 00:00 | 09.05.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | Y |  | 03.01.2023
| 0081 | 81-62944 |  | > | Üst Was 2 | Gaishorn | 2024 | 2024 | 19 | 19 | 09.05.2024 | 07:30 | 10.05.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Aufbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-62798 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 19 | 19 | 10.05.2024 | 00:00 | 10.05.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | Y |  | 03.01.2023
| 0081 | 81-63517 |  | < | Kalwang |  | 2024 | 2024 | 19 | 19 | 11.05.2024 | 07:00 | 12.05.2024 | 19:00 | 1 day + 12,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 12 |  | Inbetriebnahme ESTW Kalwang und Migration in die BFZ Villach |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-62947 |  | < | Gaishorn | Üst Was 2 | 2024 | 2024 | 19 | 19 | 11.05.2024 | 07:30 | 12.05.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Aufbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-64422 |  | > | Abzw Lof 1 | Dorfgastein | 2024 | 2024 | 20 | 20 | 13.05.2024 | 07:00 | 14.05.2024 | 17:30 | 2x 10,5 h | period. | SP |  | LT | [6 empty] | 3.5 |  | OL-Arbeiten, Sondieren |  | N |  | 02.04.2023
| 0081 | 81-63218 |  | > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 20 | 21 | 13.05.2024 | 22:00 | 25.05.2024 | 04:00 | 10x 6,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Herstellen der Fundamente für die Hilfsbrücken in km 165,808 |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-62778 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 20 | 20 | 13.05.2024 | 22:45 | 14.05.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62779 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 20 | 20 | 14.05.2024 | 22:45 | 15.05.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62780 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 20 | 20 | 15.05.2024 | 22:45 | 16.05.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62777 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 20 | 20 | 16.05.2024 | 22:45 | 17.05.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62539 |  | > | Villach Hbf | Abzw Gu 2 | 2024 | 2024 | 20 | 23 | 17.05.2024 | 07:00 | 03.06.2024 | 17:00 | 17 days + 10,0 h | cont. | SP |  | LT | S |  |  | C |  | B | 10 |  | Gleisneulage mit Untergrundverbesserung km 164,985 - km 166,487 |  | Y |  | 12.12.2022 |  |  |  | 10%
| 0081 | 81-60388 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 20 | 20 | 19.05.2024 | 00:15 | 19.05.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-60389 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 21 | 21 | 20.05.2024 | 00:15 | 20.05.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-60390 |  | < > | Gaishorn | Trieben | 2024 | 2024 | 21 | 21 | 21.05.2024 | 00:15 | 21.05.2024 | 04:45 | 4,5 h | cont. | GES |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T19 in km 156,900 - Sanierungsarbeiten am Tragwerk mit Turmwagen |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-62769 |  | > | Üst Bo 2 | St.Johann im Pongau | 2024 | 2024 | 21 | 23 | 21.05.2024 | 08:00 | 08.06.2024 | 17:00 | 18 days + 9,0 h | cont. | SP |  | LT | S |  |  | C |  | B | 4 |  | Gleisneulage mit PLV |  | Y |  | 01.10.2023
| 0081 | 81-62940 |  | < > | Sbl Leb 2 | St.Michael-Ost | 2024 | 2024 | 21 | 23 | 25.05.2024 | 23:00 | 03.06.2024 | 05:00 | 9x 6,0 h | period. | SP |  | LT | [6 empty] | 10 |  | WHZ St. Michael Ost - Herstellen der Querungen - Verkabelung |  | N |  | 12.12.2022
| 0081 | 81-63219 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 21 | 21 | 26.05.2024 | 00:30 | 26.05.2024 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Herstellen der Fundamente für die Hilfsbrücken in km 165,808 |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-64254 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2024 | 2024 | 21 | 21 | 26.05.2024 | 00:30 | 26.05.2024 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Vorarbeiten - Einbau von Arbeitstrenner in die Oberleitung |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-63220 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 22 | 22 | 27.05.2024 | 00:30 | 27.05.2024 | 04:00 | 3,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Herstellen der Fundamente für die Hilfsbrücken in km 165,808 |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-62949 |  | < | Rottenmann | Trieben | 2024 | 2024 | 22 | 22 | 28.05.2024 | 07:30 | 29.05.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 6 |  | Lagersanierung Straßenbrücke km 154,672 - Abbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-64252 |  | > | Pernegg | Mixnitz-Bärenschützklamm | 2024 | 2024 | 22 | 23 | 28.05.2024 | 20:30 | 04.06.2024 | 04:30 | 7x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Bf. Umbau Mixnitz-B.; Vorarbeiten - Fundierung und Maststellen Oberleitung Pn - Mx und Abtrag Oberleitung BGl 3, 5 und 7 |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-61637 |  | < | Marchtrenk |  | 2024 | 2024 | 22 | 23 | 29.05.2024 | 22:00 | 03.06.2024 | 05:00 | 4 days + 7,0 h | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Verschwenkung Gleis 1alt / 3neu / 1alt im Bahnhof Marchtrenk |  | Y |  | 12.12.2022
| 0081 | 81-60351 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 22 | 22 | 30.05.2024 | 00:15 | 30.05.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abbau der Schutzgerüste |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-64209 |  | > | Graz-Vbf Nord |  | 2024 | 2024 | 22 | 23 | 30.05.2024 | 07:00 | 03.06.2024 | 17:00 | 5x 10,0 h | period. | SP |  | ST | [8 empty] | Maschineneinsatz bei Gleis- und Weichenneulage BGl 181, 183 und W605 |  | N |  | 02.04.2023
| 0081 | 81-62945 |  | > | Üst Was 2 | Gaishorn | 2024 | 2024 | 22 | 22 | 30.05.2024 | 07:30 | 31.05.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Abbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-63972 |  | > | Rothenthurn |  | 2024 | 2024 | 22 | 47 | 31.05.2024 | 08:00 | 18.11.2024 | 04:00 | 171x 20,0 h | period. | BFUM |  | ST |  |  |  | C |  | B | 15 |  | Umbau Bf. Rothenthurn - Errichtung einer Personenunterführung - Errichtung Bgl 4, Neue WV 1/2 - Errichtung eines Randbahnsteigs neben Bgl 4, Verlängerung Bestandsbahnsteig auf 160m Umbau EB-Brücke km 192,529 Schwarzenbach OL-Erneuerung |  | Y |  | 05.02.2023
| 0081 | 81-62946 |  | < | Gaishorn | Üst Was 2 | 2024 | 2024 | 22 | 22 | 01.06.2024 | 07:30 | 02.06.2024 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Abbau Schutzgerüst |  | N |  | 03.09.2023
| 0081 | 81-60411 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 22 | 22 | 02.06.2024 | 00:15 | 02.06.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abbau Schutzgerüste zusätzlich: Lagersanierung der Straßenbrücken km 148,975 und km 154,672 - Aufbau der Schutzgerüste |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-60412 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 23 | 23 | 03.06.2024 | 00:15 | 03.06.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T15 in km 154,920 - Abbau Schutzgerüste zusätzlich: Lagersanierung der Straßenbrücken km 148,975 und km 154,672 - Aufbau der Schutzgerüste |  | Y |  | 29.08.2023 | Medium |  |  | 100%
| 0081 | 81-64550 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 23 | 23 | 03.06.2024 | 10:45 | 03.06.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 19.10.2023 | Medium |  |  | 100%
| 0081 | 81-63746 |  | < > | Marchtrenk | Wels Vbf-Terminal | 2024 | 2024 | 23 | 25 | 03.06.2024 | 13:00 | 17.06.2024 | 13:00 | 14 days | cont. | GES | T | LT |  |  |  | C |  |  |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 Herstellung Unterbau |  | Y |  | 12.12.2022
| 0081 | 81-62541 |  | > | Villach Hbf | Abzw Gu 2 | 2024 | 2024 | 23 | 24 | 04.06.2024 | 08:00 | 15.06.2024 | 16:00 | 12x 8,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Nacharbeiten zur Gleisneulage mit Untergrundverbesserung km 164,985 - km 166,487: - Kabelarbeiten - Begleitende Unterbauarbeiten |  | N |  | 12.12.2022
| 0081 | 81-63529 |  | < > | Marchtrenk | Wels Vbf-Terminal | 2024 | 2024 | 23 | 24 | 04.06.2024 | 20:00 | 10.06.2024 | 13:00 | 5 days + 17,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 01.05.2023
| 0081 | 81-66320A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 23 | 24 | 04.06.2024 | 20:00 | 10.06.2024 | 13:00 | 5 days + 17,0 h | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 01.05.2023
| 0081 | 81-66320A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 23 | 24 | 04.06.2024 | 20:00 | 10.06.2024 | 13:00 | 5 days + 17,0 h | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 01.05.2023
| 0081 | 81-64253 |  | > | Mixnitz-Bärenschützklamm |  | 2024 | 2024 | 23 | 23 | 05.06.2024 | 20:30 | 08.06.2024 | 04:30 | 3x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Bf. Umbau Mixnitz-B.; Vorarbeiten - Fundierung und Maststellen Oberleitung Pn - Mx und Abtrag Oberleitung BGl 3, 5 und 7 |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64483 |  | < | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 23 | 26 | 07.06.2024 | 07:00 | 24.06.2024 | 08:00 | 17 days + 1,0 h | cont. | SP |  | LT | [6 empty] | 4 |  | Gleisneulage und Schotterbettreinigung Bgl 203, LA-Beseitigung - WN W 52 |  | N |  | 03.09.2023
| 0081 | 81-63229 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 23 | 38 | 07.06.2024 | 20:00 | 16.09.2024 | 04:00 | 100 days + 8,0 h | cont. | SP |  | LT | S | [5 empty] | 1 |  | Schutz-LA80 bei den Hilfsbrücke in km 165,808 |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-63221 |  | > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 23 | 24 | 07.06.2024 | 20:30 | 10.06.2024 | 04:00 | 2 days + 7,5 h | cont. | SP |  | LT | S |  |  | C |  | B | 5 |  | Einbau der Hilfsbrücke in km 165,808 |  | Y |  | 12.07.2023 |  |  |  | 0%
| 0081 | 81-62182 |  | < | Üst Aj 5 | Hallein | 2024 | 2024 | 23 | 24 | 07.06.2024 | 22:00 | 10.06.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 4 |  | Vorarbeiten zur Erneuerung Bahnsteigdach Puch Urstein, Aufbau des Schutzgerüsts und Demontage des alten Bahnsteigdachs |  | Y |  | 01.10.2023 | Minor |  |  | 50%
| 0081 | 81-64246 |  | > | Marchtrenk | Abzw Mak 1 | 2024 | 2024 | 23 | 23 | 08.06.2024 | 22:00 | 09.06.2024 | 05:00 | 7,0 h | cont. | GES |  | LT |  |  |  | C |  | B | 3 |  | Vor- und Nacharbeiten Softwaretausch, Ein- bzw. Ausschwenken der Signale |  | Y |  | 02.04.2023
| 0081 | 81-63222 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 23 | 23 | 09.06.2024 | 00:30 | 09.06.2024 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Einbau der Hilfsbrücken |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-64215 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 23 | 24 | 09.06.2024 | 00:45 | 16.06.2024 | 05:00 | 2x 4,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kabelquerungen für Inbetriebnahme Schaltgerüst |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64245 |  | < > | Marchtrenk |  | 2024 | 2024 | 23 | 23 | 09.06.2024 | 01:20 | 09.06.2024 | 03:20 | 2,0 h | cont. | GES | T | ST |  |  |  | C |  | B |  |  | Softwaretausch Marchtrenk, IB der neuen Signale, IB der neuen Weichen Wev |  | Y |  | 02.04.2023
| 0081 | 81-62886 |  | > | Gaishorn | Trieben | 2024 | 2024 | 23 | 23 | 09.06.2024 | 07:00 | 09.06.2024 | 16:50 | 9,8 h | cont. | SP |  | LT | [6 empty] | 8 |  | Vorarbeiten für die OL-Erneuerung Gl. 2 |  | N |  | 05.11.2023
| 0081 | 81-64216 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 24 | 25 | 10.06.2024 | 00:45 | 17.06.2024 | 04:00 | 2x 3,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kabelquerungen für Inbetriebnahme Schaltgerüst |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64244 |  | < > | Marchtrenk | Wels Vbf-Terminal | 2024 | 2024 | 24 | 26 | 10.06.2024 | 13:00 | 24.06.2024 | 13:00 | 14 days | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 02.04.2023
| 0081 | 81-67397A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 24 | 26 | 10.06.2024 | 13:00 | 24.06.2024 | 13:00 | 14 days | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 02.04.2023
| 0081 | 81-67397A |  | < > | Linz Hbf | Wels Hbf | 2024 | 2024 | 24 | 26 | 10.06.2024 | 13:00 | 24.06.2024 | 13:00 | 14 days | cont. | RES | T | LT |  |  |  | C |  | B |  |  | Provisorische Anbindung St10112 (Überwerfung) an Gleis 106 und Talgleis 2 (Gleis 504) an Gleis 404 in Mak (= neue Anbindung WEV) Einbau W287 und 286,Ausbau HIB(W1,2) |  | Y |  | 02.04.2023
| 0081 | 81-62771 |  | > | Üst Bo 2 | St.Johann im Pongau | 2024 | 2024 | 24 | 27 | 10.06.2024 | 21:40 | 05.07.2024 | 05:20 | 25x 7,7 h | period. | SP |  | LT | [6 empty] | 3 |  | Nacharbeiten zur Gleisneulage |  | N |  | 01.10.2023
| 0081 | 81-61388 |  | < | Hallein | Üst Aj 5 | 2024 | 2024 | 24 | 37 | 10.06.2024 | 22:30 | 12.09.2024 | 05:00 | 81x 6,5 h | period. | SP |  | LT | [6 empty] | 4 |  | Hst. Puch-Urstein: Erneuerung des Bahnsteigdachs als Alugleitbügeldach |  | Y |  | 23.08.2023 | High |  |  | 50%
| 0081 | 81-62951 |  | > | Gaishorn | Trieben | 2024 | 2024 | 24 | 27 | 14.06.2024 | 08:10 | 05.07.2024 | 19:00 | 21 days + 10,8 h | cont. | SP |  | LT | [6 empty] | 5 |  | Erneuerung der Oberleitung - Umbauen der Lufttrennungen |  | Y |  | 05.11.2023
| 0081 | 81-63223 |  | < | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 24 | 25 | 14.06.2024 | 20:30 | 17.06.2024 | 04:00 | 2 days + 7,5 h | cont. | SP |  | LT | S |  |  | C |  | B | 5 |  | Einbau der Hilfsbrücke in km 165,808 |  | Y |  | 12.07.2023 |  |  |  | 0%
| 0081 | 81-64528 |  | < > | Leoben Hbf | Leoben Donawitz | 2024 | 2024 | 24 | 24 | 15.06.2024 | 08:00 | 15.06.2024 | 16:00 | 8,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsfenster |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-63518 |  | < > | Rottenmann | Stadt Rottenmann | 2024 | 2024 | 24 | 24 | 16.06.2024 | 00:00 | 16.06.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Inbetriebnahme ESTW Rottenmann und Migration in die BFZ Linz |  | Y |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-63224 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 24 | 24 | 16.06.2024 | 00:30 | 16.06.2024 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Einbau der Hilfsbrücken |  | N |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-62543 |  | < | Villach Hbf | Abzw Gu 2 | 2024 | 2024 | 25 | 25 | 17.06.2024 | 20:10 | 22.06.2024 | 05:10 | 5x 9,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Nacharbeiten zur Gleisneulage mit Untergrundverbesserung km 164,985 - km 166,487: - Abbau AWS - Ausbau Schotterbettsicherung |  | N |  | 12.12.2022
| 0081 | 81-64218 |  | > | Graz-Vbf | Graz-Fbf | 2024 | 2024 | 25 | 26 | 22.06.2024 | 08:00 | 30.06.2024 | 17:00 | 4x 9,0 h | period. | SP |  | LT | [8 empty] | Rückbau der Oberleitung |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64729 |  | < > | Wildon |  | 2024 | 2024 | 25 | 25 | 22.06.2024 | 19:30 | 23.06.2024 | 05:30 | 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Umbau VGS 80 für ETCS |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-63533 |  | < > | Marchtrenk |  | 2024 | 2024 | 26 | 31 | 24.06.2024 | 00:00 | 31.07.2024 | 24:00 | 38 days | cont. | SP |  | ST | [8 empty] | Errichtung Gleis 303 und 403 neu |  | N |  | 02.04.2023
| 0081 | 81-64484 |  | > | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 26 | 28 | 24.06.2024 | 08:00 | 08.07.2024 | 06:00 | 13 days + 22,0 h | cont. | SP |  | LT | [6 empty] | 3 |  | Gleisneulage und Schotterbettreinigung Bgl 204 - LA-Beseitigung |  | N |  | 01.05.2023
| 0081 | 81-64730 |  | < > | Wildon |  | 2024 | 2024 | 26 | 26 | 29.06.2024 | 19:30 | 30.06.2024 | 05:30 | 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Umbau VGS 80 für ETCS |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-65611 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 26 | 26 | 30.06.2024 | 00:15 | 30.06.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Lagersanierung der Straßenbrücken km 148,975 und km 154,672 - Abbau der Schutzgerüste |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-64217 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 26 | 26 | 30.06.2024 | 00:45 | 30.06.2024 | 05:00 | 4,2 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Inbetriebnahme Schaltgerüst |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64731 |  | < > | Wildon |  | 2024 | 2024 | 26 | 27 | 30.06.2024 | 19:30 | 01.07.2024 | 03:30 | 8,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Umbau VGS 80 für ETCS |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-65612 |  | < > | Trieben | Rottenmann | 2024 | 2024 | 27 | 27 | 01.07.2024 | 00:15 | 01.07.2024 | 04:45 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Lagersanierung der Straßenbrücken km 148,975 und km 154,672 - Abbau der Schutzgerüste |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-64114 |  | < > | Graz-Vbf Nord | Graz-Fbf | 2024 | 2024 | 27 | 31 | 01.07.2024 | 07:00 | 02.08.2024 | 17:00 | 25x 10,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Graz Vbf. (Graz Nord bis Peter Tunner Gasse) |  | N |  | 06.03.2023
| 0081 | 81-63041 |  | < > | Salzburg Aigen |  | 2024 | 2024 | 27 | 29 | 01.07.2024 | 08:00 | 21.07.2024 | 22:00 | 20 days + 14,0 h | cont. | SP |  | ST | [8 empty] | Sanierung Bahnsteig 2 |  | Y |  | 23.08.2023
| 0081 | 81-63131 |  | > | Rothenthurn |  | 2024 | 2024 | 27 | 27 | 01.07.2024 | 08:00 | 05.07.2024 | 16:00 | 5x 8,0 h | period. | BFUM |  | ST | [8 empty] | Bahnhofumbau Bf. Rothenthurn, Bauphase 2.1 - Rammen und Maststellen |  | Y |  | 05.02.2023
| 0081 | 81-62497 |  | < > | Judendorf-Straßengel |  | 2024 | 2024 | 27 | 36 | 06.07.2024 | 04:00 | 02.09.2024 | 04:00 | 58 days | cont. | BFUM |  | ST | S | [7 empty] | Sanierung Hst Judendorf-Straßengel: Sperre beider Randbahnsteige |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-60702 |  | > | Gratwein-Gratkorn | Graz-Vbf Nord | 2024 | 2024 | 27 | 31 | 06.07.2024 | 08:00 | 02.08.2024 | 24:00 | 27 days + 16,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 10 |  | Erneuerung der Oberleitung: Tausch der OL-Kette |  | Y |  | 12.04.2023
| 0081 | 81-63113 |  | > | Wald am Schoberpaß |  | 2024 | 2024 | 27 | 28 | 07.07.2024 | 08:00 | 14.07.2024 | 16:30 | 7 days + 8,5 h | cont. | SP |  | ST | [6 empty] | 15 |  | - GN mit Schotterbettreinigung Gl. 402 - Erneuerung Festlegevorrichtung im Bahnsteigbereich - Errichtung Hochwasserentlastung Jodlbachbrücke - Errichtung eines einseitigen Bedienraums neben Gl. 404 |  | Y |  | 24.07.2023
| 0081 | 81-63049 |  | < > | Werndorf | Wettmannstätten | 2024 | 2024 | 28 | 29 | 08.07.2024 | 07:00 | 21.07.2024 | 14:00 | 13 days + 7,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Einbau von Weichen auf BGl 3, 4, 6 sowie auf der Schleife |  | N |  | 11.09.2023 | High |  |  | 100%
| 0081 | 81-64551 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 28 | 28 | 08.07.2024 | 10:45 | 08.07.2024 | 16:00 | 5,2 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 01.06.2023 | Medium |  |  | 100%
| 0081 | 81-62498 |  | > | Judendorf-Straßengel |  | 2024 | 2024 | 28 | 31 | 09.07.2024 | 07:00 | 03.08.2024 | 17:00 | 25 days + 10,0 h | cont. | SP |  | ST | S | [7 empty] | Erneuerung Bahnsteig 1 - Setzen neuer Bahnsteigkanten - Neubau Bahnsteigdach |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-64670 |  | < > | Villach Hbf | Villach Hbf-Draubrücke | 2024 | 2024 | 28 | 30 | 12.07.2024 | 21:30 | 27.07.2024 | 04:30 | 15x 7,0 h | period. | SP |  | LT | [8 empty] | Aufziehen der Oberleitung BGl 201, 203, 205 und 207 |  | Y |  | 11.09.2023 |  |  |  | 0%
| 0081 | 81-65687 |  | < > | Graz Puntigam | Kalsdorf-Süd | 2024 | 2024 | 28 | 28 | 14.07.2024 | 00:30 | 14.07.2024 | 04:30 | 4,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Migration der Bahnhöfe Graz Puntigam und Kalsdorf in die BFZ Villach |  | N |  | 05.11.2023 | Medium |  |  | 100%
| 0081 | 81-63133 |  | > | Wald am Schoberpaß |  | 2024 | 2024 | 29 | 32 | 15.07.2024 | 20:10 | 09.08.2024 | 05:00 | 24 days + 8,8 h | cont. | SP |  | ST | [6 empty] | 8 |  | Rohrmasten setzen, 750m Kabeltrog, Querungen auf Gleis 404, OLM-Beleuchtung, Demontage alter Masten |  | Y |  | 30.08.2023
| 0081 | 81-62516 |  | < > | Graz-Fbf |  | 2024 | 2024 | 29 | 30 | 19.07.2024 | 07:00 | 22.07.2024 | 17:00 | 4x 10,0 h | period. | SP |  | ST | [8 empty] | WHZ-Station - Bodenplatte |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-64219 |  | < > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 29 | 29 | 21.07.2024 | 00:45 | 21.07.2024 | 05:00 | 4,2 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Graz (Inbetriebnahme BGl 183) |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-63043 |  | < | Pfarrwerfen |  | 2024 | 2024 | 30 | 34 | 22.07.2024 | 08:00 | 25.08.2024 | 22:00 | 34 days + 14,0 h | cont. | SP |  | ST | [8 empty] | Sanierung Bahnsteig 1 - Erneuerung Bahnsteigbeleuchtung und Bahnsteigentwässerung |  | N |  | 12.12.2022
| 0081 | 81-62517 |  | < > | Graz-Fbf |  | 2024 | 2024 | 30 | 31 | 26.07.2024 | 07:00 | 04.08.2024 | 17:00 | 10x 10,0 h | period. | SP |  | ST | [8 empty] | WHZ-Station - Aufstellen der Station |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-63279 |  | < | Pfarrwerfen |  | 2024 | 2024 | 30 | 31 | 26.07.2024 | 22:00 | 29.07.2024 | 05:00 | 3x 7,0 h | period. | SP |  | ST | [6 empty] | 4 |  | Sanierung Bahnsteig 1 |  | N |  | 12.12.2022
| 0081 | 81-63534 |  | < > | Marchtrenk |  | 2024 | 2025 | 31 | 29 | 01.08.2024 | 00:00 | 20.07.2025 | 24:00 | 354 days | cont. | SP |  | ST | [8 empty] | Errichtung Gleis 403 neu und Weiche 255 |  | N |  | 02.04.2023
| 0081 | 81-62917 |  | < > | Graz-Vbf |  | 2024 | 2024 | 31 | 32 | 03.08.2024 | 06:00 | 10.08.2024 | 18:00 | 7 days + 12,0 h | cont. | SP |  | ST | [8 empty] | Weichenneulage W120, 249, 253 |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-63601 |  | < > | Bad Gastein |  | 2024 | 2024 | 32 | 47 | 05.08.2024 | 08:00 | 18.11.2024 | 00:00 | 104 days + 17,0 h | cont. | SP |  | ST | [6 empty] | 3 |  | Umbau Bf. Bad Gastein - Bauphase 1 |  | N |  | 29.03.2023
| 0081 | 81-65411 |  | < > | Graz Don Bosco | Graz Liebenau-Murpark | 2024 | 2024 | 32 | 35 | 05.08.2024 | 12:00 | 01.09.2024 | 22:00 | 28x 10,0 h | period. | SP |  | LT | [8 empty] | Rammen der Fundamente und Stellen der OL-Maste |  | Y |  | 13.06.2023
| 0081 | 81-60703 |  | < | Gratwein-Gratkorn | Graz-Vbf Nord | 2024 | 2024 | 32 | 35 | 06.08.2024 | 07:00 | 01.09.2024 | 17:00 | 26 days + 10,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 10 |  | Erneuerung der Oberleitung: Tausch der OL-Kette |  | Y |  | 12.04.2023
| 0081 | 81-64116 |  | < > | Graz Don Bosco | Messendorf | 2024 | 2024 | 32 | 33 | 07.08.2024 | 07:00 | 16.08.2024 | 17:00 | 8x 10,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Graz-Don Bosco (a) - Messendorf (a) |  | N |  | 06.03.2023
| 0081 | 81-62916 |  | < > | Graz Don Bosco | Graz Ostbf-Messe | 2024 | 2024 | 32 | 33 | 09.08.2024 | 07:00 | 18.08.2024 | 24:00 | 9 days + 17,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Tausch Brückenhölzer Murbrücke |  | N |  | 11.09.2023 | High |  |  | 100%
| 0081 | 81-63042 |  | > | Pfarrwerfen |  | 2024 | 2024 | 33 | 37 | 12.08.2024 | 08:00 | 15.09.2024 | 22:00 | 34 days + 14,0 h | cont. | SP |  | ST | [8 empty] | Sanierung Bahnsteig 2 - Erneuerung Bahnsteigbeleuchtung und Bahnsteigentwässerung |  | N |  | 12.12.2022
| 0081 | 81-64552 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 33 | 33 | 12.08.2024 | 10:45 | 12.08.2024 | 16:00 | 5,2 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 19.10.2023 | Medium |  |  | 100%
| 0081 | 81-62950 |  | > | Gaishorn | Trieben | 2024 | 2024 | 33 | 37 | 12.08.2024 | 19:30 | 13.09.2024 | 06:00 | 32x 10,5 h | period. | SP |  | LT | [6 empty] | 5 |  | Vorarbeiten zur Gleisneulage Gl. 2 |  | N |  | 03.09.2023
| 0081 | 81-62782 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 33 | 33 | 12.08.2024 | 22:45 | 13.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62783 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 33 | 33 | 13.08.2024 | 22:45 | 14.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62784 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 33 | 33 | 14.08.2024 | 22:45 | 15.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62785 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 33 | 33 | 15.08.2024 | 22:45 | 16.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-63280 |  | > | Pfarrwerfen |  | 2024 | 2024 | 33 | 34 | 16.08.2024 | 22:00 | 19.08.2024 | 05:00 | 3x 7,0 h | period. | SP |  | ST | [6 empty] | 4 |  | Sanierung Bahnsteig 2 |  | N |  | 12.12.2022
| 0081 | 81-65425 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 33 | 34 | 16.08.2024 | 23:00 | 19.08.2024 | 04:00 | 2 days + 5,0 h | cont. | BFUM | T | LT |  |  |  | C |  | B |  |  | Umbau Bf. Jesenice |  | Y |  | 28.09.2023 | Medium |  |  | 100%
| 0081 | 81-63052 |  | < > | Penk |  | 2024 | 2024 | 34 | 34 | 19.08.2024 | 07:00 | 23.08.2024 | 17:00 | 4 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Vorarbeiten GN Gl. 201 und 203 in Tagessperren: Mo - Do: Bgl 203, Fr: Bgl 201 |  | N |  | 12.12.2022
| 0081 | 81-62786 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 34 | 34 | 19.08.2024 | 22:45 | 20.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62787 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 34 | 34 | 20.08.2024 | 22:45 | 21.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62788 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 34 | 34 | 21.08.2024 | 22:45 | 22.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-62789 |  | < > | Bischofshofen | Stainach-Irdning | 2024 | 2024 | 34 | 34 | 22.08.2024 | 22:45 | 23.08.2024 | 05:00 | 6,2 h | cont. | GES-N |  | LT | [8 empty] | Vorarbeiten Bahnhofumbau St. Martin a.G. Vorarbeiten Errichtung Haltestelle Hüttau |  | N |  | 03.01.2023
| 0081 | 81-64530 |  | < > | Leoben Hbf | Leoben Donawitz | 2024 | 2024 | 34 | 34 | 24.08.2024 | 08:00 | 24.08.2024 | 16:00 | 8,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsfenster |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-63075 |  | < | Penk |  | 2024 | 2024 | 34 | 34 | 24.08.2024 | 12:00 | 24.08.2024 | 20:00 | 8,0 h | cont. | SP |  | ST | [8 empty] | REI-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-63076 |  | < | Penk |  | 2024 | 2024 | 34 | 34 | 25.08.2024 | 07:00 | 25.08.2024 | 18:00 | 11,0 h | cont. | SP |  | ST | [8 empty] | REI-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-63068 |  | < | Penk |  | 2024 | 2024 | 35 | 35 | 26.08.2024 | 08:00 | 26.08.2024 | 16:00 | 8,0 h | cont. | SP |  | ST | [8 empty] | SUZ-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-62990 |  | < > | Kirchdorf a.d.Krems | Spital am Pyhrn | 2024 | 2024 | 35 | 36 | 26.08.2024 | 21:45 | 06.09.2024 | 04:20 | 8x 6,6 h | period. | WF |  | LT |  |  |  | C |  | B |  |  | Servicefenster Instandsetzung in Nächten Mo - Fr jeweils von 22:20 Uhr bis 04:20 Uhr - Schienentausch und GN km 68,00 - 69,000 und 73,900 - 74,900 |  | Y |  | 01.10.2023 | High |  |  | 100%
| 0081 | 81-65679 |  | < > | Nettingsdorf | Kirchdorf a.d.Krems | 2024 | 2024 | 35 | 35 | 26.08.2024 | 23:30 | 30.08.2024 | 04:20 | 4x 4,8 h | period. | WF |  | LT |  |  |  | C |  | B |  |  | Servicefenster Instandsetzung in Nächten Mo - Fr jeweils von 23:30 Uhr bis 04:20 Uhr |  | Y |  | 01.10.2023 | Medium |  |  | 100%
| 0081 | 81-63134 |  | < | Wald am Schoberpaß |  | 2024 | 2024 | 35 | 36 | 30.08.2024 | 20:10 | 06.09.2024 | 05:00 | 6 days + 8,8 h | cont. | SP |  | ST | [6 empty] | 8 |  | Rohrmasten setzen, Kabeltrog, OLM-Beleuchtung, Demontage alter Masten |  | Y |  | 30.08.2023
| 0081 | 81-63070 |  | < | Penk |  | 2024 | 2024 | 35 | 35 | 31.08.2024 | 10:00 | 31.08.2024 | 16:00 | 6,0 h | cont. | SP |  | ST | [8 empty] | REI-Maschineneinsatz |  | Y |  | 11.09.2023
| 0081 | 81-63071 |  | < | Penk |  | 2024 | 2024 | 36 | 36 | 02.09.2024 | 08:00 | 02.09.2024 | 16:00 | 8,0 h | cont. | SP |  | ST | [8 empty] | SUZ-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-62499 |  | > | Gratwein-Gratkorn | Graz-Vbf | 2024 | 2024 | 36 | 37 | 02.09.2024 | 22:45 | 14.09.2024 | 04:30 | 10x 5,8 h | period. | SP |  | LT | [8 empty] | Erneuerung Bahnsteig 1 in der Haltestelle Judendorf-St. - Restarbeiten Neubau Bahnsteigdach |  | N |  | 12.04.2023 |  |  |  | 0%
| 0081 | 81-63225 |  | > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 36 | 37 | 06.09.2024 | 20:30 | 09.09.2024 | 04:00 | 2 days + 7,5 h | cont. | SP |  | LT | S |  |  | C |  | B | 5 |  | Ausbau der Hilfsbrücke in km 165,808 |  | Y |  | 31.08.2023 |  |  |  | 10%
| 0081 | 81-65426 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 36 | 37 | 06.09.2024 | 23:00 | 09.09.2024 | 04:00 | 2 days + 5,0 h | cont. | BFUM | T | LT |  |  |  | C |  | B |  |  | Umbau Bf. Jesenice |  | Y |  | 28.09.2023 | Medium |  |  | 100%
| 0081 | 81-63226 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 36 | 36 | 07.09.2024 | 01:00 | 07.09.2024 | 02:30 | 1,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Ausbau der Hilfsbrücken |  | N |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-65494 |  | < | Graz-Vbf Nord | Graz-Fbf | 2024 | 2024 | 36 | 38 | 07.09.2024 | 18:00 | 22.09.2024 | 05:00 | 3x 11,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Kabelumlegungen für Neubau Brücke Peter Tunner Gasse (Bauphase 2025) |  | N |  | 01.07.2023
| 0081 | 81-62903 |  | < > | Hieflau | Selzthal-Nord | 2024 | 2024 | 36 | 38 | 08.09.2024 | 07:00 | 19.09.2024 | 17:00 | 11 days + 10,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Gesamtsperre - Arbeiten lt. Bündel 31a |  | Y |  | 01.10.2023
| 0081 | 81-60805 |  | < > | Bischofshofen | Selzthal | 2024 | 2024 | 37 | 39 | 09.09.2024 | 08:00 | 29.09.2024 | 22:00 | 20 days + 14,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | - Weichenneulagen und Tragseiltausch Bf. Hüttau - Errichtung Haltestelle Hüttau - Migration BFZ Bfe Stainach-Irdning, Schladming und Pichl - diverse Instandsetzungs- und Erneuerungsarbeiten |  | Y |  | 12.12.2022 | High |  |  | 100%
| 0081 | 81-63855 |  | < > | Bischofshofen | Pöham | 2024 | 2024 | 37 | 39 | 09.09.2024 | 08:00 | 29.09.2024 | 22:00 | 20 days + 14,0 h | cont. | SP |  | LT | [8 empty] | Erneuerung Stütz- und Futtermauer km 1,054 - 2,993 |  | N |  | 12.12.2022
| 0081 | 81-60805 |  | < > | Bischofshofen | Selzthal | 2024 | 2024 | 37 | 39 | 09.09.2024 | 08:00 | 29.09.2024 | 22:00 | 20 days + 14,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | - Weichenneulagen und Tragseiltausch Bf. Hüttau - Errichtung Haltestelle Hüttau - Migration BFZ Bfe Stainach-Irdning, Schladming und Pichl - diverse Instandsetzungs- und Erneuerungsarbeiten |  | Y |  | 12.12.2022 | High |  |  | 100%
| 0081 | 81-60805 |  | < > | Bischofshofen | Selzthal | 2024 | 2024 | 37 | 39 | 09.09.2024 | 08:00 | 29.09.2024 | 22:00 | 20 days + 14,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | - Weichenneulagen und Tragseiltausch Bf. Hüttau - Errichtung Haltestelle Hüttau - Migration BFZ Bfe Stainach-Irdning, Schladming und Pichl - diverse Instandsetzungs- und Erneuerungsarbeiten |  | Y |  | 12.12.2022 | High |  |  | 100%
| 0081 | 81-64553 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 37 | 37 | 09.09.2024 | 10:45 | 09.09.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 07.09.2023 | Medium |  |  | 100%
| 0081 | 81-64285 |  | < > | Bischofshofen | Schladming | 2024 | 2024 | 37 | 38 | 10.09.2024 | 02:30 | 22.09.2024 | 22:00 | 12 days + 19,5 h | cont. | SP |  | LT | [8 empty] | Seilzugarbeiten für die 380 kV Salzburgleitung |  | N |  | 02.04.2023
| 0081 | 81-65590 |  | < | Gaishorn | Trieben | 2024 | 2024 | 37 | 38 | 13.09.2024 | 19:30 | 16.09.2024 | 06:00 | 3x 10,5 h | period. | SP |  | LT | [6 empty] | 5 |  | Vorarbeiten zur Gleisneulage - Aufbau der ATWS |  | N |  | 03.09.2023
| 0081 | 81-63227 |  | < | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 37 | 38 | 13.09.2024 | 20:30 | 16.09.2024 | 04:00 | 2 days + 7,5 h | cont. | SP |  | LT | S |  |  | C |  | B | 5 |  | Ausbau der Hilfsbrücke in km 165,808 |  | Y |  | 12.07.2023 |  |  |  | 0%
| 0081 | 81-63228 |  | < > | Bruck a.d.Mur-Übelstein | Pernegg | 2024 | 2024 | 37 | 37 | 14.09.2024 | 01:00 | 14.09.2024 | 02:30 | 1,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Ausbau der Hilfsbrücken |  | N |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-65149 |  | < > | Peggau-Deutschfeistritz | Graz-Vbf Nord | 2024 | 2024 | 37 | 37 | 15.09.2024 | 01:00 | 15.09.2024 | 05:00 | 4,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Gw |  | N |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-65150 |  | < > | Wildon | Leibnitz | 2024 | 2024 | 37 | 37 | 15.09.2024 | 01:00 | 15.09.2024 | 05:00 | 4,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Wi 2 |  | N |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-63079 |  | > | Gaishorn | Trieben | 2024 | 2024 | 38 | 39 | 16.09.2024 | 08:00 | 29.09.2024 | 16:30 | 13 days + 8,5 h | cont. | SP |  | LT | [6 empty] | 6 |  | Gleisneulage und Schotterbettreinigung |  | Y |  | 04.08.2023
| 0081 | 81-64545 |  | > | Mixnitz-Bärenschützklamm | Frohnleiten | 2024 | 2024 | 38 | 38 | 16.09.2024 | 08:30 | 21.09.2024 | 15:00 | 6x 6,5 h | period. | SP |  | LT | [6 empty] | 1 |  | Schlägerungarbeiten |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-64115 |  | < > | Mixnitz-Bärenschützklamm | Graz-Vbf Nord | 2024 | 2024 | 38 | 50 | 16.09.2024 | 20:30 | 13.12.2024 | 04:30 | 52x 8,0 h | period. | SP |  | LT | [8 empty] | Montage der ETCS Balisen Mixnitz-B.- (a) - Graz Vbf. (a) |  | N |  | 06.03.2023
| 0081 | 81-65613 |  | < > | Seiz | St.Michael | 2024 | 2024 | 38 | 38 | 22.09.2024 | 00:15 | 22.09.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T2 in km 199,400 - Aufbau der Schutzgerüste |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-62515 |  | < > | Villach Westbf |  | 2024 | 2024 | 38 | 41 | 22.09.2024 | 07:00 | 07.10.2024 | 17:00 | 15 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Weichenneulage W435, 439, DKW450-451 |  | N |  | 12.12.2022
| 0081 | 81-64131 |  | < | Mallnitz-Hintertal | Mallnitz-Obervellach | 2024 | 2024 | 39 | 39 | 23.09.2024 | 08:00 | 28.09.2024 | 16:00 | 6x 8,0 h | period. | SP |  | LT | [6 empty] | 4 |  | Vorarbeiten zur Gleisneulage Gl. 1 |  | N |  | 01.05.2023
| 0081 | 81-63915 |  | < > | Liezen | Selzthal | 2024 | 2024 | 39 | 39 | 24.09.2024 | 07:00 | 29.09.2024 | 22:00 | 5 days + 15,0 h | cont. | SP |  | LT | [8 empty] | Schwellenneulage km 96,470-97,800; |  | N |  | 12.12.2022
| 0081 | 81-63915 |  | < > | Liezen | Selzthal | 2024 | 2024 | 39 | 39 | 24.09.2024 | 07:00 | 29.09.2024 | 22:00 | 5 days + 15,0 h | cont. | SP |  | LT | [8 empty] | Schwellenneulage km 96,470-97,800; |  | N |  | 12.12.2022
| 0081 | 81-61409 |  | > | Hallein | Üst Hl 3 | 2024 | 2024 | 39 | 40 | 27.09.2024 | 22:00 | 30.09.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 5 |  | Verlängerung Personentunnel Hallein Burgfried, Einbau HIB |  | Y |  | 30.08.2023
| 0081 | 81-62901 |  | < | Graz-Vbf | Graz Hbf | 2024 | 2025 | 39 | 14 | 28.09.2024 | 08:00 | 31.03.2025 | 17:00 | 184 days + 9,0 h | cont. | SP |  | LT | [6 empty] | 10 |  | Neubau der Brücke Peter-Tunner-Gasse (Phase 2) |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-65614 |  | < > | Seiz | St.Michael | 2024 | 2024 | 39 | 39 | 29.09.2024 | 00:15 | 29.09.2024 | 05:00 | 4,8 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | ASFINAG: Sanierung Tragwerk T2 in km 199,400 - Aufbau der Schutzgerüste |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-65492 |  | > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 39 | 44 | 29.09.2024 | 00:45 | 03.11.2024 | 05:00 | 6x 4,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umlegen der Kabel für Neubau Brücke Peter Tunner Gasse (Bauphase 2025) |  | N |  | 31.07.2023 | Medium |  |  | 100%
| 0081 | 81-65151 |  | < > | Leibnitz | Staatsgrenze nächst Spielfeld-Straß | 2024 | 2024 | 39 | 39 | 29.09.2024 | 01:30 | 29.09.2024 | 05:00 | 3,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Softwaretausch ESTW Rzn und Sd |  | N |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-65493 |  | > | Gratwein-Gratkorn | Graz-Fbf | 2024 | 2024 | 40 | 45 | 30.09.2024 | 00:45 | 04.11.2024 | 04:00 | 6x 3,2 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umlegen der Kabel für Neubau Brücke Peter Tunner Gasse (Bauphase 2025) |  | N |  | 01.07.2023 | Medium |  |  | 100%
| 0081 | 81-62762 |  | < | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 40 | 41 | 30.09.2024 | 07:00 | 09.10.2024 | 17:30 | 9 days + 10,5 h | cont. | SP |  | LT | S | [5 empty] | 5 |  | Erneuerung der Oberleitung Sgl 1 |  | N |  | 12.12.2022
| 0081 | 81-63493 |  | < > | Ehrenhausen | Spielfeld-Straß | 2024 | 2024 | 40 | 42 | 30.09.2024 | 07:00 | 20.10.2024 | 17:00 | 21x 10,0 h | period. | SP |  | LT | [8 empty] | Sanierung Stützmauer km 254,205-254,277 |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-64132 |  | < | Mallnitz-Hintertal | Mallnitz-Obervellach | 2024 | 2024 | 40 | 41 | 30.09.2024 | 08:00 | 12.10.2024 | 16:00 | 13x 8,0 h | period. | SP |  | LT | [6 empty] | 4 |  | Vorarbeiten zur Gleisneulage Gl. 1 |  | N |  | 01.05.2023
| 0081 | 81-63568 |  | < | Hallein | Üst Aj 5 | 2024 | 2024 | 40 | 41 | 04.10.2024 | 22:00 | 07.10.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 4 |  | Sanierung Brücke Ausbau Hib Sgl 1 |  | Y |  | 23.08.2023
| 0081 | 81-62722 |  | < > | Niklasdorf | Leoben Hbf | 2024 | 2024 | 40 | 40 | 06.10.2024 | 00:00 | 06.10.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Einbau Schotterbettsicherung Brücke in km 13,318 |  | Y |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-62723 |  | < > | Niklasdorf | Leoben Hbf | 2024 | 2024 | 41 | 41 | 07.10.2024 | 00:00 | 07.10.2024 | 04:00 | 4,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Einbau Schotterbettsicherung Brücke in km 13,318 |  | Y |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-62691 |  | < | Niklasdorf | Leoben Hbf | 2024 | 2024 | 41 | 46 | 07.10.2024 | 07:30 | 15.11.2024 | 17:00 | 39 days + 10,5 h | cont. | SP |  | LT | S |  |  | C |  | B | 10 |  | Sanierung Brücke in km 13,318 |  | Y |  | 03.05.2023 | Minor |  |  | 15%
| 0081 | 81-64605 |  | < > | Werndorf | Staatsgrenze nächst Spielfeld-Straß | 2024 | 2024 | 41 | 41 | 07.10.2024 | 22:00 | 11.10.2024 | 04:00 | 4x 6,0 h | period. | WF |  | LT |  |  |  | C |  | B |  |  | Wartungs- und Instandsetzungsarbeiten |  | N |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-62763 |  | > | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 41 | 42 | 10.10.2024 | 07:00 | 19.10.2024 | 17:30 | 9 days + 10,5 h | cont. | SP |  | LT | S | [5 empty] | 5 |  | Erneuerung der Oberleitung Sgl 2 |  | N |  | 12.12.2022
| 0081 | 81-63569 |  | > | Üst Aj 5 | Hallein | 2024 | 2024 | 41 | 42 | 11.10.2024 | 22:00 | 14.10.2024 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 4 |  | Sanierung Brücke Ausbau Hib Sgl 2 |  | Y |  | 23.08.2023
| 0081 | 81-65427 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 41 | 42 | 11.10.2024 | 23:00 | 14.10.2024 | 04:00 | 2 days + 5,0 h | cont. | BFUM | T | LT |  |  |  | C |  | B |  |  | Umbau Bf. Jesenice |  | Y |  | 28.09.2023 | Medium |  |  | 100%
| 0081 | 81-60804 |  | < > | Schwarzach-St.Veit | Böckstein | 2024 | 2024 | 41 | 42 | 12.10.2024 | 05:30 | 14.10.2024 | 17:00 | 2 days + 11,5 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten im Streckenverlauf |  | Y |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-63056 |  | > | Penk |  | 2024 | 2024 | 42 | 42 | 14.10.2024 | 07:00 | 18.10.2024 | 17:00 | 4 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Vorarbeiten GN Gl. 202 in Tagessperren |  | N |  | 12.12.2022
| 0081 | 81-64486 |  | < > | Villach Westbf | Villach Süd Gvbf-Auen | 2024 | 2024 | 42 | 42 | 14.10.2024 | 07:00 | 17.10.2024 | 17:00 | 4x 10,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Vorarbeiten zur Gleisneulage BGl 104 und Weichenneulage W101, 106 und 107 |  | N |  | 01.05.2023
| 0081 | 81-64486 |  | < > | Villach Westbf | Villach Süd Gvbf-Auen | 2024 | 2024 | 42 | 42 | 14.10.2024 | 07:00 | 17.10.2024 | 17:00 | 4x 10,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Vorarbeiten zur Gleisneulage BGl 104 und Weichenneulage W101, 106 und 107 |  | N |  | 01.05.2023
| 0081 | 81-64554 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 42 | 42 | 14.10.2024 | 10:45 | 14.10.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-60817 |  | > | Golling-Abtenau | Üst Gg 2 | 2024 | 2024 | 42 | 42 | 14.10.2024 | 22:00 | 16.10.2024 | 06:00 | 2x 8,0 h | period. | SP |  | LT | [8 empty] | Abschaltungen für Sanierung A10 Brücke ASFINAG (Richtungsfahrbahn Sb) |  | N |  | 12.12.2022 | Minor |  |  | 50%
| 0081 | 81-64566 |  | < > | Hieflau | Selzthal-Nord | 2024 | 2024 | 42 | 42 | 15.10.2024 | 08:00 | 15.10.2024 | 15:00 | 7,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Gesamtsperre - Instandsetzungsarbeiten im gesamten Streckenverlauf |  | Y |  | 01.05.2023
| 0081 | 81-60819 |  | < | Üst Gg 2 | Golling-Abtenau | 2024 | 2024 | 42 | 42 | 16.10.2024 | 22:00 | 18.10.2024 | 06:00 | 2x 8,0 h | period. | SP |  | LT | [8 empty] | Abschaltungen für Sanierung A10 Brücke ASFINAG (Richtungsfahrbahn Sb) |  | N |  | 12.12.2022 | Minor |  |  | 50%
| 0081 | 81-64567 |  | < > | Hieflau | Selzthal-Nord | 2024 | 2024 | 42 | 42 | 17.10.2024 | 08:00 | 17.10.2024 | 15:00 | 7,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Gesamtsperre - Instandsetzungsarbeiten im gesamten Streckenverlauf |  | Y |  | 01.05.2023
| 0081 | 81-62718 |  | < > | Villach Westbf | Villach Süd Gvbf-Auen | 2024 | 2024 | 42 | 45 | 18.10.2024 | 07:00 | 09.11.2024 | 06:00 | 22 days | cont. | SP |  | LT | S | [5 empty] | 10 |  | Gleisneulage BGl 104 und Weichenneulage W101, 106 und 107 |  | N |  | 11.04.2023 |  |  |  | 10%
| 0081 | 81-62718 |  | < > | Villach Westbf | Villach Süd Gvbf-Auen | 2024 | 2024 | 42 | 45 | 18.10.2024 | 07:00 | 09.11.2024 | 06:00 | 22 days | cont. | SP |  | LT | S | [5 empty] | 10 |  | Gleisneulage BGl 104 und Weichenneulage W101, 106 und 107 |  | N |  | 11.04.2023 |  |  |  | 10%
| 0081 | 81-63073 |  | > | Penk |  | 2024 | 2024 | 42 | 42 | 19.10.2024 | 10:00 | 19.10.2024 | 16:00 | 6,0 h | cont. | SP |  | ST | [8 empty] | REI-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-62764 |  | > | Dorfgastein | Bad Hofgastein | 2024 | 2024 | 42 | 44 | 20.10.2024 | 07:00 | 30.10.2024 | 17:00 | 11x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | OL-Restarbeiten Sgl 1 oder 2 |  | N |  | 12.12.2022
| 0081 | 81-63074 |  | > | Penk |  | 2024 | 2024 | 43 | 43 | 21.10.2024 | 08:00 | 21.10.2024 | 16:00 | 8,0 h | cont. | SP |  | ST | [8 empty] | SUZ-Maschineneinsatz |  | Y |  | 12.12.2022
| 0081 | 81-64499 |  | < > | Spielfeld-Straß | Bad Radkersburg | 2024 | 2024 | 43 | 44 | 21.10.2024 | 08:00 | 31.10.2024 | 14:00 | 9x 6,0 h | period. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungs- und Instansetzungsarbeiten im Streckenverlauf (Schwellenwechsel, Schlägerungsarbeiten |  | N |  | 01.05.2023 | High |  |  | 100%
| 0081 | 81-60820 |  | < | Üst Gg 2 | Golling-Abtenau | 2024 | 2024 | 43 | 43 | 21.10.2024 | 22:00 | 22.10.2024 | 06:00 | 8,0 h | cont. | SP |  | LT | [8 empty] | Abschaltungen für Sanierung A10 Brücke ASFINAG (Richtungsfahrbahn Sb) |  | N |  | 12.12.2022 | Minor |  |  | 50%
| 0081 | 81-60822 |  | > | Golling-Abtenau | Üst Gg 2 | 2024 | 2024 | 43 | 43 | 22.10.2024 | 22:00 | 23.10.2024 | 06:00 | 8,0 h | cont. | SP |  | LT | [8 empty] | Abschaltungen für Sanierung A10 Brücke ASFINAG (Richtungsfahrbahn Sb) |  | N |  | 12.12.2022 | Minor |  |  | 50%
| 0081 | 81-63099 |  | > | Wald am Schoberpaß | Üst Was 2 | 2024 | 2024 | 43 | 43 | 25.10.2024 | 08:10 | 26.10.2024 | 16:30 | 2x 8,3 h | period. | SP |  | LT | [6 empty] | 4 |  | Tragseiltausch Gl. 2 |  | N |  | 11.04.2023
| 0081 | 81-64911 |  | < > | Linz Wegscheid |  | 2024 | 2024 | 43 | 44 | 26.10.2024 | 08:00 | 29.10.2024 | 22:00 | 3 days + 15,0 h | cont. | SP |  | ST | [6 empty] | 4 |  | Weichenneulage W 56 und Entwässerungsarbeiten Bf. Linz Wegscheid |  | N |  | 01.10.2023
| 0081 | 81-63100 |  | > | Wald am Schoberpaß | Üst Was 2 | 2024 | 2024 | 43 | 44 | 27.10.2024 | 08:10 | 28.10.2024 | 02:00 | 17,8 h | cont. | SP |  | LT | [6 empty] | 8 |  | Tragseiltausch im Bereich der Lufttrennung Bf. Wald Gl. 2 |  | Y |  | 02.08.2023
| 0081 | 81-64133 |  | < | Mallnitz-Hintertal | Mallnitz-Obervellach | 2024 | 2024 | 44 | 44 | 28.10.2024 | 08:00 | 31.10.2024 | 16:00 | 4x 8,0 h | period. | SP |  | LT | [6 empty] | 4 |  | Nacharbeiten zur Gleisneulage Gl. 1 |  | N |  | 01.05.2023
| 0081 | 81-64234 |  | < > | Werfen |  | 2024 | 2024 | 44 | 45 | 28.10.2024 | 08:00 | 09.11.2024 | 23:30 | 12 days + 15,5 h | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Vorarbeiten zur Inbetriebnahme ESTW Werfen |  | Y |  | 02.04.2023 | High |  |  | 100%
| 0081 | 81-63957 |  | < > | Rohr-Bad Hall |  | 2024 | 2024 | 44 | 45 | 28.10.2024 | 08:00 | 04.11.2024 | 04:30 | 6 days + 20,5 h | cont. | GES | T | ST | [8 empty] | Weichenneulage W 353, 354, 356 und Gleisneulage der Anschlussbereiche |  | N |  | 01.10.2023
| 0081 | 81-63101 |  | > | Wald am Schoberpaß | Üst Was 2 | 2024 | 2024 | 44 | 44 | 29.10.2024 | 08:10 | 29.10.2024 | 16:30 | 8,3 h | cont. | SP |  | LT | [6 empty] | 4 |  | Tragseiltausch und Nacharbeiten Gl. 2 |  | N |  | 11.04.2023
| 0081 | 81-62365 |  | < > | Traun | Rohr-Bad Hall | 2024 | 2024 | 44 | 45 | 29.10.2024 | 22:00 | 04.11.2024 | 04:30 | 5 days + 6,5 h | cont. | GES | T | LT | S |  |  | C |  | B |  |  | Inbetriebnahme ESTW Traun und ESTW Nettingsdorf - Ausbau der Weichen 31 und 32 Bf. Nettingsdorf - Weichenneulage 353, 354 und 356 Bf. Rohr Bad Hall |  | Y |  | 07.09.2023 | Medium |  |  | 100%
| 0081 | 81-62365 |  | < > | Traun | Rohr-Bad Hall | 2024 | 2024 | 44 | 45 | 29.10.2024 | 22:00 | 04.11.2024 | 04:30 | 5 days + 6,5 h | cont. | GES | T | LT | S |  |  | C |  | B |  |  | Inbetriebnahme ESTW Traun und ESTW Nettingsdorf - Ausbau der Weichen 31 und 32 Bf. Nettingsdorf - Weichenneulage 353, 354 und 356 Bf. Rohr Bad Hall |  | Y |  | 07.09.2023 | Medium |  |  | 100%
| 0081 | 81-64287 |  | > | Linz Wegscheid | Traun | 2024 | 2024 | 44 | 44 | 29.10.2024 | 22:00 | 03.11.2024 | 07:00 | 4 days + 9,0 h | cont. | SP |  | LT | [8 empty] | Weichenneulage W 65 Bf. Linz Wegscheid |  | N |  | 01.10.2023
| 0081 | 81-63062 |  | < > | Paternion-Feistritz |  | 2024 | 2024 | 44 | 45 | 30.10.2024 | 07:00 | 05.11.2024 | 17:00 | 6 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Tragwerkserneuerung in km 183,469 |  | N |  | 07.08.2023
| 0081 | 81-64082 |  | < > | Graz-Vbf |  | 2024 | 2024 | 44 | 44 | 01.11.2024 | 07:00 | 03.11.2024 | 17:00 | 2 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Wartung Talbremsen |  | N |  | 05.02.2023
| 0081 | 81-63103 |  | < | Wald am Schoberpaß | Kalwang | 2024 | 2024 | 44 | 44 | 01.11.2024 | 07:30 | 02.11.2024 | 16:30 | 2x 9,0 h | period. | SP |  | LT | [6 empty] | 6 |  | Tragseiltausch |  | N |  | 02.08.2023
| 0081 | 81-63102 |  | < | Wald am Schoberpaß | Kalwang | 2024 | 2024 | 44 | 45 | 03.11.2024 | 08:10 | 04.11.2024 | 02:00 | 17,8 h | cont. | SP |  | LT | [6 empty] | 8 |  | Tragseiltausch im Bereich der Lufttrennung Bf. Wald Gl.1 |  | Y |  | 02.08.2023
| 0081 | 81-64134 |  | < | Mallnitz-Hintertal | Mallnitz-Obervellach | 2024 | 2024 | 45 | 45 | 04.11.2024 | 08:00 | 08.11.2024 | 16:00 | 5x 8,0 h | period. | SP |  | LT | [6 empty] | 4 |  | Nacharbeiten zur Gleisneulage Gl. 1 |  | N |  | 01.05.2023
| 0081 | 81-65495 |  | < | Gratwein-Gratkorn | Graz-Vbf Nord | 2024 | 2024 | 45 | 47 | 04.11.2024 | 23:00 | 19.11.2024 | 04:00 | 7x 5,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umlegen der Kabel für Neubau Brücke Peter Tunner Gasse (Bauphase 2025) |  | N |  | 01.07.2023 |  |  |  | 0%
| 0081 | 81-63063 |  | > | Paternion-Feistritz |  | 2024 | 2024 | 45 | 46 | 06.11.2024 | 07:00 | 12.11.2024 | 17:00 | 6 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Tragwerkserneuerung in km 183,469 |  | N |  | 07.08.2023
| 0081 | 81-62987 |  | < > | Villach Westbf | Villach Warmbad | 2024 | 2024 | 45 | 47 | 09.11.2024 | 20:30 | 18.11.2024 | 04:30 | 9x 8,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Erneuerung Lärmschutzwandelemente km 380,867 - 381,488 |  | N |  | 12.12.2022
| 0081 | 81-63516 |  | < > | Werfen |  | 2024 | 2024 | 45 | 45 | 09.11.2024 | 23:30 | 10.11.2024 | 05:30 | 6,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | Inbetriebnahme ESTW Werfen - BLOCKADE |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-63064 |  | < | Paternion-Feistritz |  | 2024 | 2024 | 46 | 47 | 13.11.2024 | 07:00 | 19.11.2024 | 17:00 | 6 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Tragwerkserneuerung in km 183,469 |  | Y |  | 07.08.2023
| 0081 | 81-63424 |  | < | Marchtrenk |  | 2024 | 2024 | 46 | 47 | 15.11.2024 | 23:00 | 18.11.2024 | 05:00 | 2 days + 6,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 10 |  | 4-gleisiger Ausbau: Einbau HiB LM22, Ausbau Weiche 5 Verschiebung aus 2022 (fehlender Berscheid) |  | Y |  | 06.03.2023
| 0081 | 81-63009 |  | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2024 | 2024 | 46 | 47 | 16.11.2024 | 07:00 | 18.11.2024 | 05:30 | 1 day + 22,5 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-62720 |  | < > | Niklasdorf | Leoben Hbf | 2024 | 2024 | 46 | 46 | 17.11.2024 | 00:00 | 17.11.2024 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Ausbau Schotterbettsicherung Brücke in km 13,318 |  | Y |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-62217 |  | < > | Bad Gastein | Mallnitz-Hintertal | 2024 | 2025 | 47 | 10 | 18.11.2024 | 00:00 | 03.03.2025 | 06:00 | 105 days + 6,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Tauernsperre - Modernisierung Tauerntunnel - Instandsetzungs- und Erneuerungsarbeiten |  | N |  | 28.06.2023 | Major |  |  | 100%
| 0081 | 81-64431 |  | < > | Bad Gastein |  | 2024 | 2025 | 47 | 10 | 18.11.2024 | 00:00 | 03.03.2025 | 05:00 | 105 days + 5,0 h | cont. | SP |  | ST | [6 empty] | 0 |  | Umbau Bf. Bad Gastein - Bauphase 2 |  | N |  | 02.04.2023
| 0081 | 81-64893A |  | < > | Linz Hbf | Selzthal | 2024 | 2025 | 47 | 29 | 18.11.2024 | 00:00 | 14.07.2025 | 04:00 | 238 days + 3,0 h | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Tauernsperre |  | N |  | 13.06.2023 | Minor |  |  | 20%
| 0081 | 81-62721 |  | < > | Niklasdorf | Leoben Hbf | 2024 | 2024 | 47 | 47 | 18.11.2024 | 00:00 | 18.11.2024 | 04:00 | 4,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Ausbau Schotterbettsicherung Brücke in km 13,318 |  | Y |  | 12.12.2022 | Medium |  |  | 100%
| 0081 | 81-64899A |  | < > | St.Michael | Selzthal | 2024 | 2025 | 47 | 29 | 18.11.2024 | 00:00 | 14.07.2025 | 04:00 | 238 days + 3,0 h | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Tauernsperre |  | N |  | 13.06.2023 | Minor |  |  | 20%
| 0081 | 81-64893A |  | < > | Linz Hbf | Selzthal | 2024 | 2025 | 47 | 29 | 18.11.2024 | 00:00 | 14.07.2025 | 04:00 | 238 days + 3,0 h | cont. | RES |  | LT |  |  |  | C |  | B |  |  | Tauernsperre |  | N |  | 13.06.2023 | Minor |  |  | 20%
| 0081 | 81-64493 |  | < > | Villach Hbf-Draubrücke | Villach Westbf | 2024 | 2024 | 47 | 48 | 18.11.2024 | 07:00 | 25.11.2024 | 04:00 | 6 days + 21,0 h | cont. | SP |  | LT |  |  |  | C |  |  |  |  | Sanierung W421 |  | Y |  | 01.05.2023
| 0081 | 81-64726 |  | > | Bad Hofgastein |  | 2024 | 2025 | 47 | 19 | 18.11.2024 | 08:00 | 09.05.2025 | 18:00 | 172 days + 9,0 h | cont. | SP |  | ST | [6 empty] | 0 |  | Herstellung Barrierefreiheit - Abtrag Mittelbahnsteig - Neubau Mittelbahnsteig, Einbau LIft |  | N |  | 01.05.2023
| 0081 | 81-64732 |  | > | Dorfgastein |  | 2024 | 2025 | 47 | 16 | 18.11.2024 | 08:00 | 15.04.2025 | 08:00 | 147 days + 23,0 h | cont. | BFUM |  | ST | [6 empty] | 0 |  | Umbau Bf. Dorfgastein - Fundierung und Errichtung Personentunnel NEU - Abtrag Bahnsteig 2 - ERrichtung Bahnsteig 2 NEU |  | N |  | 27.07.2023
| 0081 | 81-65690 |  | < | Dorfgastein | Abzw Lof 1 | 2024 | 2025 | 47 | 29 | 18.11.2024 | 08:00 | 14.07.2025 | 05:00 | 237 days + 20,0 h | cont. | SP |  | LT | [6 empty] | 0 |  | Erneuerung der Futtermauer km 11.173 - km 11.460 Sanierung der Ankerfuttermauer km 9.925 - km 10.115 |  | N |  | 05.11.2023
| 0081 | 81-64067 |  | < | Penk |  | 2024 | 2024 | 47 | 47 | 18.11.2024 | 08:10 | 24.11.2024 | 15:50 | 7x 7,7 h | period. | SP |  | ST | [8 empty] | OL-Arbeiten Bgl 201 - Aufziehen Rückleiter |  | Y |  | 13.06.2023
| 0081 | 81-62986 |  | < | Villach Westbf | Villach Warmbad | 2024 | 2024 | 47 | 49 | 18.11.2024 | 20:30 | 08.12.2024 | 04:30 | 20x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Villach Westbf - Villach Warmbad; Erneuerung Lärmschutzwandelemente km 380,291 - 380,938 |  | N |  | 12.12.2022 |  |  |  | 0%
| 0081 | 81-63825 |  | < > | Schwarzach-St.Veit | Bad Gastein | 2024 | 2025 | 47 | 10 | 18.11.2024 | 23:00 | 03.03.2025 | 06:00 | 105x 7,0 h | period. | GES-N |  | LT |  |  |  | C |  | B |  |  | Tauernsperre - Instandsetzungs- und Erneuerungsarbeiten in den Nächten |  | N |  | 12.12.2022 | Major |  |  | 100%
| 0081 | 81-64424 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2024 | 2024 | 47 | 51 | 18.11.2024 | 23:00 | 18.12.2024 | 06:00 | 22x 7,0 h | period. | GES-N |  | LT | [8 empty] | OL-Vorarbeiten für die Errichtung der Stromschienen |  | N |  | 02.04.2023
| 0081 | 81-63065 |  | < > | Paternion-Feistritz |  | 2024 | 2024 | 47 | 48 | 20.11.2024 | 07:00 | 26.11.2024 | 17:00 | 6 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Tragwerkserneuerung in km 183,469 |  | N |  | 12.12.2022
| 0081 | 81-63425 |  | > | Marchtrenk |  | 2024 | 2024 | 47 | 48 | 22.11.2024 | 23:00 | 25.11.2024 | 05:00 | 2 days + 6,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 10 |  | 4-gleisiger Ausbau: Einbau HiB LM22, Ausbau Weiche 5 Verschiebung aus 2022 (fehlender Berscheid) |  | Y |  | 06.03.2023
| 0081 | 81-64531 |  | < > | Leoben Hbf | Leoben Donawitz | 2024 | 2024 | 47 | 47 | 23.11.2024 | 08:00 | 23.11.2024 | 16:00 | 8,0 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsfenster |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64536 |  | > | Bruck a.d.Mur-Stadtwald | Leoben Hbf | 2024 | 2024 | 48 | 48 | 25.11.2024 | 08:30 | 28.11.2024 | 13:30 | 4x 5,0 h | period. | WF |  | LT |  |  |  | C |  | B | 10 |  | Diverse Instandhaltungsarbeiten im Streckenverlauf |  | N |  | 01.05.2023
| 0081 | 81-64555 |  | < > | Rosenbach | Jesenice | 2024 | 2024 | 50 | 50 | 09.12.2024 | 10:45 | 09.12.2024 | 16:20 | 5,6 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Wartungsarbeiten im Karawankentunnel |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64429 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2025 | 2025 | 3 | 3 | 13.01.2025 | 07:00 | 15.01.2025 | 17:00 | 3x 10,0 h | period. | SP |  | LT | [6 empty] | 0 |  | OL-Arbeiten, Rammen und Maststellen |  | N |  | 02.04.2023
| 0081 | 81-64428 |  | < | Dorfgastein | Abzw Lof 1 | 2025 | 2025 | 3 | 3 | 16.01.2025 | 07:00 | 19.01.2025 | 17:00 | 4x 10,0 h | period. | SP |  | LT | [6 empty] | 0 |  | OL-Arbeiten, Rammen und Maststellen |  | N |  | 02.04.2023
| 0081 | 81-65130 |  | > | Leoben Hbf | St.Michael-Ost | 2025 | 2025 | 5 | 9 | 27.01.2025 | 22:00 | 28.02.2025 | 04:30 | 20x 6,5 h | period. | SP |  | LT | [6 empty] | 10 |  | Erneuerung Handlauf und Tunnelfunk |  | N |  | 13.06.2023
| 0081 | 81-64255 |  | < | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 6 | 7 | 08.02.2025 | 20:30 | 15.02.2025 | 04:30 | 7x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Bf. Umbau Mixnitz-B.; Vorarbeiten - Fundierung und Maststellen Oberleitung Pn - Mx |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64256 |  | < | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 7 | 9 | 15.02.2025 | 20:30 | 24.02.2025 | 04:30 | 9x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Bf. Umbau Mixnitz-B.; Vorarbeiten - Fundierung und Maststellen Oberleitung Pn - Mx und Abtrag Oberleitung BGl 3, 5 und 7 |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-65137 |  | < > | Salzburg-Mitte |  | 2025 | 2025 | 8 | 12 | 22.02.2025 | 00:00 | 21.03.2025 | 24:00 | 28 days | cont. | SP |  | ST | [8 empty] | Salzburg Hbf; GN, WN 381-384 und Beleuchtung Gl.426-432; km 312,158 - 312,800; Bau |  | N |  | 13.06.2023
| 0081 | 81-64788 |  | < | Üst Pg 2 | Gratwein-Gratkorn | 2025 | 2025 | 9 | 9 | 24.02.2025 | 20:30 | 01.03.2025 | 04:30 | 5x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Fundierung für Hilfsbrücken (Pfähle) |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-65548 |  | > | Rothenthurn |  | 2025 | 2025 | 9 | 10 | 24.02.2025 | 22:30 | 06.03.2025 | 05:00 | 10x 6,5 h | period. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, OL-Arbeiten - Montage Spitzenleitung (U-Leitung, Rückleiter) Bgl 2 und 4 - Montage Kettenzug Bgl 2 und 4 |  | Y |  | 07.08.2023
| 0081 | 81-64438 |  | < > | Bad Gastein |  | 2025 | 2025 | 10 | 29 | 03.03.2025 | 05:00 | 14.07.2025 | 05:00 | 132 days + 23,0 h | cont. | SP |  | ST | [8 empty] | Umbau Bf. Bad Gastein - Bauphase 3 und 4 |  | N |  | 02.04.2023
| 0081 | 81-63343 |  | < > | Schwarzach-St.Veit | Mallnitz-Hintertal | 2025 | 2025 | 10 | 27 | 03.03.2025 | 06:00 | 04.07.2025 | 23:59 | 123 days + 17,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Tauernsperre - Modernisierung Tauerntunnel - Umbau Bf. Bad Gastein, - Viaduktsanierungen Swa - Bs - Einbau Stromschiene Klamm-Tunnels - Umbau und OL-Erneuerung Bf. Rothenthurn - diverse Instandsetzungs- und Erneuerungsarbeiten |  | Y |  | 01.07.2023 | Major |  |  | 100%
| 0081 | 81-65114 |  | < > | Abzw Hg 1 | Abzw Hg 2 | 2025 | 2025 | 10 | 27 | 03.03.2025 | 06:00 | 04.07.2025 | 06:00 | 122 days + 23,0 h | cont. | GES | T | LT | [8 empty] | Verstärkungsmaßnahmen am Steinbach- und Pyrkershöhenviadukt |  | N |  | 13.06.2023
| 0081 | 81-65115 |  | < > | Abzw Hg 4 | Bad Gastein | 2025 | 2025 | 10 | 27 | 03.03.2025 | 06:00 | 04.07.2025 | 06:00 | 122 days + 23,0 h | cont. | GES | T | LT | [8 empty] | Erneuerung Stütz- und Futtermauern u. Entwässerungsanlagen; km 27,767-29,419 |  | N |  | 13.06.2023
| 0081 | 81-65128 |  | < > | Spielfeld-Straß | Bad Radkersburg | 2025 | 2025 | 10 | 11 | 03.03.2025 | 08:00 | 14.03.2025 | 16:00 | 10x 8,0 h | period. | SP |  | LT | [8 empty] | Schlägerungsarbeiten |  | N |  | 13.06.2023
| 0081 | 81-64425 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2025 | 2025 | 10 | 10 | 04.03.2025 | 07:00 | 09.03.2025 | 17:00 | 5 days + 10,0 h | cont. | GES | T | LT | [8 empty] | OL-Kettenabtrag im Bereich der Klamm-Tunnels |  | N |  | 02.04.2023
| 0081 | 81-65242 |  | < > | Linz Hbf |  | 2025 | 2025 | 10 | 11 | 06.03.2025 | 07:00 | 13.03.2025 | 17:00 | 7 days + 10,0 h | cont. | SP |  | ST | [8 empty] | WN W741, W743, W744 u. W745 |  | N |  | 13.06.2023
| 0081 | 81-65549 |  | > | Rothenthurn |  | 2025 | 2025 | 10 | 11 | 06.03.2025 | 22:30 | 16.03.2025 | 05:00 | 10x 6,5 h | period. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, OL-Arbeiten - Montage Spitzenleitung (U-Leitung, Rückleiter) Bgl 2 und 4 - Montage Kettenzug Bgl 2 und 4 |  | Y |  | 07.08.2023
| 0081 | 81-64426 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2025 | 2025 | 11 | 12 | 10.03.2025 | 07:00 | 21.03.2025 | 17:00 | 10x 10,0 h | period. | GES |  | LT | [8 empty] | Stützpunktmontage für die Errichtung der Stromschienen in den Klamm-Tunnels |  | N |  | 02.04.2023
| 0081 | 81-65550 |  | < | Rothenthurn |  | 2025 | 2025 | 12 | 13 | 17.03.2025 | 22:30 | 27.03.2025 | 05:00 | 10x 6,5 h | period. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, OL-Arbeiten - Montage Spitzenleitung (U-Leitung, Rückleiter) Bgl 1 und 3 - Montage Kettenzug Bgl 1 und 3 |  | Y |  | 07.08.2023
| 0081 | 81-64467 |  | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2025 | 2025 | 12 | 13 | 22.03.2025 | 07:00 | 24.03.2025 | 05:30 | 1 day + 22,5 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-64427 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2025 | 2025 | 13 | 14 | 24.03.2025 | 07:00 | 06.04.2025 | 17:00 | 14x 10,0 h | period. | GES |  | LT | [8 empty] | Stromschienenmontage in den Klamm-Tunnels |  | N |  | 02.04.2023
| 0081 | 81-65551 |  | < | Rothenthurn |  | 2025 | 2025 | 13 | 14 | 28.03.2025 | 22:30 | 06.04.2025 | 05:00 | 5x 6,5 h | period. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, OL-Arbeiten - Montage Spitzenleitung (U-Leitung, Rückleiter) Bgl 1 und 3 - Montage Kettenzug Bgl 1 und 3 |  | Y |  | 07.08.2023
| 0081 | 81-64984 |  | < > | Graz-Vbf |  | 2025 | 2025 | 14 | 14 | 31.03.2025 | 07:00 | 06.04.2025 | 17:00 | 6 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Einbau Gleisprovisorium und Ausbau Gleisbremsen 070 |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64789 |  | < | Üst Pg 2 | Gratwein-Gratkorn | 2025 | 2025 | 14 | 15 | 04.04.2025 | 20:00 | 07.04.2025 | 04:00 | 2 days + 8,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Einbau der Hilfsbrücke |  | Y |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64793 |  | < > | Peggau-Deutschfeistritz | Gratwein-Gratkorn | 2025 | 2025 | 14 | 14 | 06.04.2025 | 00:45 | 06.04.2025 | 05:00 | 4,2 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Einbau der Hilfsbrücke |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64014 |  | < | Rothenthurn |  | 2025 | 2025 | 15 | 15 | 07.04.2025 | 07:00 | 13.04.2025 | 17:00 | 6 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, Bauphase 11 - Erneuerung W 51 - Erneuerung W 52 alt (W 53 neu) - EK-Bedielung Gl. 1 - Umbau Randbahnsteig neben Gl. 1 - Ausbau HIB Gl. 3 |  | Y |  | 13.06.2023
| 0081 | 81-64430 |  | < > | Loifarn-Süd | Abzw Lof 1 | 2025 | 2025 | 15 | 15 | 08.04.2025 | 07:00 | 12.04.2025 | 17:00 | 5x 10,0 h | period. | GES |  | LT | [8 empty] | OL-Montage im eingleisigen Bereich |  | N |  | 02.04.2023
| 0081 | 81-65124 |  | < > | Bruck a.d.Mur-Stadtwald | Bruck a.d.Mur-Übelstein | 2025 | 2025 | 15 | 16 | 10.04.2025 | 22:00 | 14.04.2025 | 05:00 | 4x 7,0 h | period. | SP |  | LT | S | [7 empty] | Vorarbeiten zum Tausch der Brückenhölzer |  | Y |  | 13.06.2023 |  |  |  | 10%
| 0081 | 81-64790 |  | > | Üst Pg 2 | Gratwein-Gratkorn | 2025 | 2025 | 15 | 16 | 11.04.2025 | 20:00 | 14.04.2025 | 04:00 | 2 days + 8,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Einbau der Hilfsbrücke |  | Y |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64794 |  | < > | Peggau-Deutschfeistritz | Gratwein-Gratkorn | 2025 | 2025 | 15 | 15 | 13.04.2025 | 00:45 | 13.04.2025 | 05:00 | 4,2 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Einbau der Hilfsbrücke |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64015 |  | > | Rothenthurn |  | 2025 | 2025 | 16 | 16 | 14.04.2025 | 07:00 | 18.04.2025 | 17:00 | 4 days + 10,0 h | cont. | BFUM |  | ST |  |  |  | C |  | B |  |  | Bahnhofumbau Bf. Rothenthurn, Bauphase 12 - Abtrag und Neuerrichtung Weiche 53 alt (54 neu) - EK-Bedielung Gl. 2 |  | Y |  | 13.06.2023
| 0081 | 81-65123 |  | < > | Bruck a.d.Mur-Stadtwald | Bruck a.d.Mur-Übelstein | 2025 | 2025 | 16 | 17 | 14.04.2025 | 07:00 | 22.04.2025 | 04:00 | 7 days + 21,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Tausch der Brückenhölzer |  | Y |  | 13.06.2023 | High |  |  | 100%
| 0081 | 81-65133 |  | < | Peggau-Deutschfeistritz | Üst Pg 2 | 2025 | 2025 | 16 | 17 | 14.04.2025 | 07:00 | 22.04.2025 | 04:00 | 7 days + 21,0 h | cont. | SP |  | LT | S |  |  | C |  | B | 10 |  | Gründliche Durcharbeitung W53, 54 und 57 |  | Y |  | 13.06.2023
| 0081 | 81-65102 |  | > | Böckstein |  | 2025 | 2025 | 16 | 18 | 14.04.2025 | 08:00 | 03.05.2025 | 16:00 | 19 days + 8,0 h | cont. | SP |  | ST | [8 empty] | Gleisneulage Bgl 302, 304, 306 und Weichenneulage W 3 |  | N |  | 25.08.2023
| 0081 | 81-65131 |  | > | Leoben Hbf | St.Michael-Ost | 2025 | 2025 | 16 | 35 | 14.04.2025 | 22:00 | 29.08.2025 | 04:30 | 80x 6,5 h | period. | SP |  | LT | [6 empty] | 10 |  | Erneuerung Handlauf und Tunnelfunk |  | N |  | 13.06.2023
| 0081 | 81-64733 |  | < | Dorfgastein |  | 2025 | 2025 | 16 | 27 | 15.04.2025 | 08:00 | 04.07.2025 | 16:00 | 80 days + 8,0 h | cont. | BFUM |  | ST | [8 empty] | Herstellung Barrierefreiheit Bf. Dorfgastein - Fundierung und Errichtung Personentunnel NEU - Abtrag Bahnsteig 1 - Errichtung Bahnsteig 1 NEU |  | N |  | 27.07.2023
| 0081 | 81-64806 |  | < > | Graz-Fbf | Graz-Vbf | 2025 | 2025 | 16 | 31 | 19.04.2025 | 07:00 | 31.07.2025 | 17:00 | 103 days + 10,0 h | cont. | SP |  | LT | [6 empty] | 10 |  | Neubau der Brücke Peter-Tunner-Gasse (Phase 3) |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64166 |  | < > | Graz-Vbf | Graz-Fbf | 2025 | 2025 | 16 | 17 | 19.04.2025 | 08:00 | 21.04.2025 | 18:00 | 2 days + 10,0 h | cont. | SP |  | LT | [8 empty] | Weichenneulage W251/252 und 247/248 (Bauphase 1) |  | N |  | 06.03.2023
| 0081 | 81-65134 |  | < > | Peggau-Deutschfeistritz |  | 2025 | 2025 | 17 | 17 | 21.04.2025 | 01:00 | 21.04.2025 | 04:00 | 3,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B | 10 |  | Maschineneinsatz bei der Gründliche Durcharbeitung W53, 54 und 57 |  | N |  | 13.06.2023
| 0081 | 81-65125 |  | < > | Bruck a.d.Mur-Stadtwald | Bruck a.d.Mur-Übelstein | 2025 | 2025 | 17 | 17 | 22.04.2025 | 22:00 | 26.04.2025 | 05:00 | 4x 7,0 h | period. | SP |  | LT | S | [7 empty] | Nacharbeiten zum Tausch der Brückenhölzer |  | Y |  | 13.06.2023 |  |  |  | 10%
| 0081 | 81-65617 |  | > | Hallein | Üst Hl 3 | 2025 | 2025 | 17 | 18 | 25.04.2025 | 22:00 | 28.04.2025 | 05:00 | 2 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 5 |  | Verlängerung Personentunnel Hallein Burgfried, Ausbau HIB |  | Y |  | 03.09.2023
| 0081 | 81-65324 |  | < > | Hallein |  | 2025 | 2025 | 17 | 18 | 26.04.2025 | 07:00 | 28.04.2025 | 04:00 | 1 day + 21,0 h | cont. | SP |  | ST | [6 empty] | 6 |  | Weichenneulage W 2Z Bf. Hallein |  | N |  | 13.06.2023
| 0081 | 81-65546 |  | > | Üst Mx 2 | Frohnleiten | 2025 | 2025 | 17 | 17 | 26.04.2025 | 08:30 | 27.04.2025 | 15:30 | 2x 7,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Aufbau von Schutzgerüsten: • DL km 182,002 • DL km 182,069 |  | N |  | 07.08.2023 |  |  |  | 0%
| 0081 | 81-64320 |  | < > | Linz Hbf |  | 2025 | 2025 | 19 | 20 | 05.05.2025 | 00:00 | 18.05.2025 | 24:00 | 14 days | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Anbindung Gleise 309-311 an Weiche 333 |  | Y |  | 02.04.2023
| 0081 | 81-64727 |  | > | Bad Hofgastein |  | 2025 | 2025 | 19 | 25 | 09.05.2025 | 18:00 | 16.06.2025 | 08:00 | 37 days + 14,0 h | cont. | SP |  | ST | [8 empty] | Herstellung Barrierefreiheit - Herstellen Bahnsteigdach und Wartekoje - Ausstattung Mittelbahnsteig |  | N |  | 01.05.2023
| 0081 | 81-64474 |  | < > | Selzthal |  | 2025 | 2025 | 20 | 21 | 12.05.2025 | 07:00 | 23.05.2025 | 17:00 | 11 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 3 |  | Gleisneulage und Schotterbettreinigung |  | N |  | 13.06.2023
| 0081 | 81-64474 |  | < > | Selzthal |  | 2025 | 2025 | 20 | 21 | 12.05.2025 | 07:00 | 23.05.2025 | 17:00 | 11 days + 10,0 h | cont. | SP |  | ST | [6 empty] | 3 |  | Gleisneulage und Schotterbettreinigung |  | N |  | 13.06.2023
| 0081 | 81-65322 |  | > | Salzburg Aigen |  | 2025 | 2025 | 20 | 21 | 15.05.2025 | 22:00 | 19.05.2025 | 05:00 | 3 days + 7,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 6 |  | Weichenneulage W 52 Bf. Aigen - Schotterbettreinigung und Überhöhungsabbau von 140 mm auf 90 mm |  | Y |  | 13.06.2023
| 0081 | 81-64321 |  | < > | Linz Hbf |  | 2025 | 2025 | 21 | 31 | 19.05.2025 | 00:00 | 01.08.2025 | 24:00 | 75 days | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Anbindung Gleise 307 an DKW317/318 |  | Y |  | 02.04.2023
| 0081 | 81-65323 |  | < | Salzburg Aigen |  | 2025 | 2025 | 21 | 22 | 22.05.2025 | 22:00 | 26.05.2025 | 05:00 | 3 days + 7,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 6 |  | Weichenneulage W 51 Bf. Aigen - Schotterbettreinigung und Überhöhungsabbau von 140 mm auf 90 mm |  | Y |  | 13.06.2023
| 0081 | 81-64167 |  | < > | Graz-Vbf | Graz-Fbf | 2025 | 2025 | 23 | 24 | 07.06.2025 | 08:00 | 09.06.2025 | 18:00 | 2 days + 10,0 h | cont. | SP |  | LT | [8 empty] | Weichenneulage W251/252 und 247/248 (Bauphase 2) |  | N |  | 06.03.2023
| 0081 | 81-64130 |  | < | Mallnitz-Hintertal | Mallnitz-Obervellach | 2025 | 2025 | 23 | 27 | 08.06.2025 | 08:00 | 30.06.2025 | 17:00 | 22 days + 9,0 h | cont. | SP |  | LT | [6 empty] | 4 |  | Gleisneulage und PLV Gl. 1; km 43,567 - km 45,260 |  | N | SAA708 | 15.05.2023
| 0081 | 81-65547 |  | > | Üst Mx 2 | Frohnleiten | 2025 | 2025 | 24 | 24 | 14.06.2025 | 08:30 | 15.06.2025 | 15:30 | 2x 7,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Abbau von Schutzgerüsten: • DL km 182,002 • DL km 182,069 |  | N |  | 07.08.2023 |  |  |  | 0%
| 0081 | 81-64728 |  | < | Bad Hofgastein |  | 2025 | 2025 | 25 | 27 | 16.06.2025 | 08:00 | 04.07.2025 | 04:00 | 17 days + 20,0 h | cont. | SP |  | ST | [6 empty] | 0 |  | Herstellung Barrierefreiheit - Aushub und Isolierung Personentunnel erneuern |  | N |  | 27.07.2023
| 0081 | 81-64791 |  | < | Üst Pg 2 | Gratwein-Gratkorn | 2025 | 2025 | 25 | 26 | 20.06.2025 | 20:00 | 23.06.2025 | 04:00 | 2 days + 8,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Ausbau der Hilfsbrücke |  | Y |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64795 |  | < > | Peggau-Deutschfeistritz | Gratwein-Gratkorn | 2025 | 2025 | 25 | 25 | 21.06.2025 | 01:30 | 21.06.2025 | 03:00 | 1,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Ausbau der Hilfsbrücke |  | Y |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-64792 |  | > | Üst Pg 2 | Gratwein-Gratkorn | 2025 | 2025 | 26 | 27 | 27.06.2025 | 20:00 | 30.06.2025 | 04:00 | 2 days + 8,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Ausbau der Hilfsbrücke |  | Y |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-63828 |  | > | Spittal-Millstättersee | Rothenthurn | 2025 | 2025 | 26 | 29 | 27.06.2025 | 23:45 | 14.07.2025 | 05:00 | 16 days + 5,2 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Tauernsperre - Erneuerung der Lieserbrücke - Tragseiltausch im Bereich der Lieserbrücke |  | Y | Saa713 | 13.06.2023 | High |  |  | 100%
| 0081 | 81-65105 |  | > | Spittal-Millstättersee | Rothenthurn | 2025 | 2025 | 26 | 29 | 27.06.2025 | 23:45 | 14.07.2025 | 05:00 | 16 days + 5,2 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Gleisneulage und Planumsverbesserung Gl. 1 und 2 km 199.152 - km 199.600 |  | N |  | 13.06.2023
| 0081 | 81-64796 |  | < > | Peggau-Deutschfeistritz | Gratwein-Gratkorn | 2025 | 2025 | 26 | 26 | 28.06.2025 | 01:30 | 28.06.2025 | 03:00 | 1,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Kraneinsatz beim Ausbau der Hilfsbrücke |  | Y |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-63382 |  | < > | Böckstein | Mallnitz-Obervellach | 2025 | 2025 | 27 | 29 | 05.07.2025 | 00:00 | 14.07.2025 | 05:00 | 9 days + 5,0 h | cont. | SP |  | LT |  |  |  | C |  | B |  |  | Fertigstellungsarbeiten Tauerntunnel - Handlaufmontage und Restarbeiten Kabelwege im Tauerntunnel - Fertigstellung Deckenstromschiene - diverse Instandsetzungsarbeiten |  | Y |  | 21.06.2023
| 0081 | 81-64138 |  | < > | Schwarzach-St.Veit | Böckstein | 2025 | 2025 | 27 | 29 | 05.07.2025 | 00:00 | 14.07.2025 | 05:00 | 9 days + 5,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten im Streckenverlauf |  | Y |  | 02.08.2023 | High |  |  | 100%
| 0081 | 81-63342 |  | < > | Böckstein | Mallnitz-Hintertal | 2025 | 2025 | 27 | 29 | 05.07.2025 | 20:00 | 14.07.2025 | 05:00 | 9x 9,0 h | period. | SP |  | LT |  |  |  | C |  | B |  |  | -Restarbeiten Modernisierung Tauerntunnel |  | Y |  | 01.07.2023
| 0081 | 81-68250A |  | < > | Bruck a.d.Mur | Leoben Hbf | 2025 | 2025 | 28 | 31 | 07.07.2025 | 07:00 | 28.07.2025 | 04:00 | 20 days + 21,0 h | cont. | RES |  | LT |  |  |  | C |  | B | 0 |  | Gleiseneulage BGl 601 |  | Y |  | 01.05.2023 | Minor |  |  | 20%
| 0081 | 81-65126 |  | > | Gratwein-Gratkorn | Graz-Vbf Nord | 2025 | 2025 | 29 | 29 | 14.07.2025 | 20:30 | 20.07.2025 | 04:30 | 6x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Sanierung Durchlass in km 206,497 und km 206,672 |  | N |  | 13.06.2023
| 0081 | 81-64462 |  | > | Mautern |  | 2025 | 2025 | 29 | 30 | 15.07.2025 | 19:00 | 26.07.2025 | 05:00 | 10x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Vorarbeiten zur Gleis- und Weichenneulage Bf. Mautern |  | Y |  | 13.06.2023
| 0081 | 81-64315 |  | < | Marchtrenk |  | 2025 | 2025 | 29 | 30 | 16.07.2025 | 00:00 | 21.07.2025 | 04:00 | 5 days + 4,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 0 |  | Einbau Weiche 64P, Ausbau Weichen 54 + 58 |  | Y |  | 01.05.2023
| 0081 | 81-64317 |  | < > | Wels Vbf-Terminal | Marchtrenk | 2025 | 2025 | 30 | 35 | 21.07.2025 | 01:00 | 31.08.2025 | 24:00 | 41 days + 23,0 h | cont. | SP |  | LT |  |  |  | C |  |  |  |  | Abtrag Überwerfungsbauwerk, Anbindung Talgleis 1prov an WEV und MAK Teilanbindung Talgleis 002 an WEV |  | Y |  | 02.04.2023
| 0081 | 81-64640 |  | < | Marchtrenk |  | 2025 | 2025 | 30 | 30 | 21.07.2025 | 01:20 | 21.07.2025 | 04:30 | 3,2 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | Softwaretausch Marchtrenk |  | Y |  | 01.05.2023
| 0081 | 81-64559 |  | < > | Selzthal-Nord | Hieflau | 2025 | 2025 | 30 | 31 | 21.07.2025 | 08:00 | 31.07.2025 | 16:00 | 10 days + 8,0 h | cont. | GES | T | LT |  |  |  | C |  | B |  |  | Instandsetzungsarbeiten, Mauersanierungen - Sanierung Ennsmauertunnel - Bf. Admont: GDA Gl. 1 km 124,769 - 125,456 |  | Y |  | 07.09.2023
| 0081 | 81-64257 |  | < > | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 30 | 31 | 21.07.2025 | 08:00 | 01.08.2025 | 17:00 | 11 days + 9,0 h | cont. | SP |  | ST | S | [5 empty] | 1 |  | Herstellen von Hauptkabelquerungen (km169,589 und km 171,067) mit Pressung LA80km/h von km 169,550 bis km 69,650 oder von km 171,000 bis km 171,100 |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64459 |  | > | Mautern |  | 2025 | 2025 | 31 | 34 | 28.07.2025 | 06:00 | 18.08.2025 | 06:00 | 21 days | cont. | SP |  | ST |  |  |  | C |  | B | 6 |  | Gleisneulage Bgl 2 und Weichenneulage W 52 und 56 Bf. Mautern |  | Y |  | 13.06.2023
| 0081 | 81-63956 |  | < > | Micheldorf |  | 2025 | 2025 | 31 | 37 | 01.08.2025 | 04:00 | 08.09.2025 | 04:00 | 38 days | cont. | BFUM | T | ST | [8 empty] | Umbau Bahnhof Micheldorf |  | N |  | 01.05.2023
| 0081 | 81-63958 |  | < > | Kirchdorf a.d.Krems | Micheldorf | 2025 | 2025 | 31 | 37 | 01.08.2025 | 04:00 | 08.09.2025 | 04:00 | 38 days | cont. | SP | T | LT | [8 empty] | Gleisneulage Kik - Mid km 51,520 - 52,695 |  | N |  | 17.04.2023
| 0081 | 81-64569 |  | < > | Micheldorf | Klaus | 2025 | 2025 | 31 | 37 | 01.08.2025 | 04:00 | 08.09.2025 | 04:00 | 38x 24,0 h | period. | SP | T | LT | [8 empty] | Brückenerneuerungen Mid - Kus km 57,945 - 58,114 |  | N |  | 01.05.2023
| 0081 | 81-64570 |  | < > | Klaus | Steyrling | 2025 | 2025 | 31 | 37 | 01.08.2025 | 04:00 | 08.09.2025 | 04:00 | 38 days | cont. | SP | T | LT | [8 empty] | Gleisneulage Kus - Sng km 61,487 - 62,835 |  | N |  | 01.05.2023
| 0081 | 81-64571 |  | < > | Klaus | Steyrling | 2025 | 2025 | 31 | 37 | 01.08.2025 | 04:00 | 08.09.2025 | 04:00 | 38 days | cont. | SP | T | LT | [8 empty] | Erneuerung der Abdichtung und Randbalkenerneuerung Viadukt, km 62,962 |  | N |  | 01.05.2023
| 0081 | 81-63959 |  | > | Schlierbach |  | 2025 | 2025 | 32 | 37 | 04.08.2025 | 04:00 | 08.09.2025 | 04:00 | 35 days | cont. | SP | T | ST | [8 empty] | Bahnsteigerneuerung Hst. Schlierbach |  | N |  | 03.01.2023
| 0081 | 81-64853 |  | < > | Linzerhaus | Ardning | 2025 | 2025 | 31 | 33 | 01.08.2025 | 07:30 | 17.08.2025 | 17:00 | 17x 9,5 h | period. | GES | T | LT |  |  |  | C |  | B |  |  | Erneuerung der Entwässerungsanlagen |  | Y |  | 13.06.2023
| 0081 | 81-64322 |  | < > | Linz Hbf |  | 2025 | 2025 | 31 | 33 | 02.08.2025 | 00:00 | 17.08.2025 | 24:00 | 16 days | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Zwischenzustand: Keine Anbindung Bahnsteig 8 West |  | Y |  | 02.04.2023
| 0081 | 81-64260 |  | > | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 31 | 35 | 02.08.2025 | 20:30 | 25.08.2025 | 04:30 | 23x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Vorarbeiten - Kabelquerungen, Umrüsten der Weichen, Signalfundamente und Ortsverkabelung |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64258 |  | < | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 31 | 33 | 03.08.2025 | 00:30 | 17.08.2025 | 05:00 | 3x 4,5 h | period. | GES-N |  | ST |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Vorarbeiten - Herstellen der Gleisquerungen am südlichen Weichenkopf |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64259 |  | < | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 32 | 34 | 04.08.2025 | 00:30 | 18.08.2025 | 04:00 | 3x 3,5 h | period. | GES-N |  | ST |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Vorarbeiten - Herstellen der Gleisquerungen am südlichen Weichenkopf |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64807 |  | > | Graz-Vbf Nord |  | 2025 | 2025 | 32 | 35 | 04.08.2025 | 07:00 | 31.08.2025 | 17:00 | 27 days + 10,0 h | cont. | SP |  | ST | S | [5 empty] | 5 |  | Einbau Erschütterungsschutz |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-65098 |  | > | Linz Wegscheid |  | 2025 | 2025 | 32 | 32 | 06.08.2025 | 07:00 | 10.08.2025 | 18:00 | 4 days + 11,0 h | cont. | SP |  | ST | [8 empty] | Weichenneulage W 57 und 58 Bf. Linz Wegscheid |  | N |  | 13.06.2023
| 0081 | 81-65129 |  | < > | Üst Bm 2L | Niklasdorf | 2025 | 2025 | 32 | 36 | 08.08.2025 | 20:30 | 01.09.2025 | 04:30 | 12x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Errichtung Widerlager für Straßenbrücke in km 9,182 (EK-Auflassung) |  | N |  | 13.06.2023
| 0081 | 81-65407 |  | < > | Kalsdorf |  | 2025 | 2025 | 33 | 34 | 11.08.2025 | 07:00 | 22.08.2025 | 17:00 | 11 days + 10,0 h | cont. | SP |  | ST | [8 empty] | Sanierung Randbalken Brücke in km 224,040 |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64678 |  | < | Linz Wegscheid |  | 2025 | 2025 | 33 | 34 | 14.08.2025 | 07:00 | 23.08.2025 | 17:00 | 9 days + 10,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 0 |  | Weichenneulage W 59, 60, 61, 62 und 64 inkl. PLV |  | Y |  | 05.11.2023
| 0081 | 81-64323 |  | < > | Linz Hbf |  | 2025 | 2025 | 34 | 43 | 18.08.2025 | 00:00 | 26.10.2025 | 24:00 | 70 days + 1,0 h | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Anbindung Gleis 309 an Weiche 331, Anbindung Weiche 319 an Weiche 333 |  | Y |  | 02.04.2023
| 0081 | 81-65404 |  | > | Schwarzach-St.Veit | Lend | 2025 | 2025 | 34 | 42 | 18.08.2025 | 07:00 | 19.10.2025 | 18:00 | 62 days + 11,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 40 |  | Erneuerung Brücke L 270 km 71,454 |  | Y |  | 13.06.2023 |  |  |  | 10%
| 0081 | 81-65592 |  | > | Üst Was 2 | Gaishorn | 2025 | 2025 | 34 | 34 | 19.08.2025 | 07:30 | 20.08.2025 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Aufbau Schutzgerüst |  | N |  | 24.08.2023
| 0081 | 81-65593 |  | < | Gaishorn | Üst Was 2 | 2025 | 2025 | 34 | 34 | 21.08.2025 | 07:30 | 22.08.2025 | 17:30 | 2x 10,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Instandsetzung Brückenlager km 163,718 - Aufbau Schutzgerüst |  | N |  | 24.08.2023
| 0081 | 81-64463 |  | < | Mautern |  | 2025 | 2025 | 34 | 36 | 21.08.2025 | 19:00 | 04.09.2025 | 05:00 | 12x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Vorarbeiten zur Gleis- und Weichenneulage Bf. Mautern - Teilabtrag Bahnsteig 2 |  | Y |  | 13.06.2023
| 0081 | 81-65405 |  | > | Schwarzach-St.Veit | Lend | 2025 | 2025 | 34 | 34 | 22.08.2025 | 00:00 | 22.08.2025 | 05:00 | 5,0 h | cont. | GES-N |  | LT |  |  |  | C |  | B | 40 |  | Erneuerung Brücke L 270 km 71,454 - Ausbau Hilfsbrücken (Kraneinsatz) |  | Y |  | 13.06.2023 | Medium |  |  | 100%
| 0081 | 81-64629 |  | < | Hörsching | Marchtrenk | 2025 | 2025 | 34 | 36 | 24.08.2025 | 23:00 | 05.09.2025 | 21:00 | 11 days + 22,0 h | cont. | SP |  | LT | S |  |  | C |  | B | 4 |  | Schotterbettreinigung |  | Y |  | 25.05.2023
| 0081 | 81-64263 |  | < | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 35 | 36 | 25.08.2025 | 20:30 | 01.09.2025 | 04:30 | 7x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1a: - Vormontage Oberleitung |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-65325 |  | < | Werfen | Üst Gg 4 | 2025 | 2025 | 35 | 37 | 29.08.2025 | 22:00 | 08.09.2025 | 05:00 | 9 days + 7,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 12 |  | Gleisneulage Gleis 1 km 41,634 - 42,038 |  | Y |  | 13.06.2023
| 0081 | 81-64168 |  | < > | Graz-Vbf |  | 2025 | 2025 | 36 | 36 | 01.09.2025 | 07:00 | 05.09.2025 | 17:00 | 5x 10,0 h | period. | SP |  | ST | [8 empty] | Errichtung Sockerschlitz zwischen BGl 110 und 112 |  | N |  | 06.03.2023 |  |  |  | 0%
| 0081 | 81-63291 |  | > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 36 | 37 | 01.09.2025 | 20:30 | 08.09.2025 | 04:30 | 7x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1a: - Vormontage Oberleitung |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64460 |  | < | Mautern |  | 2025 | 2025 | 36 | 40 | 05.09.2025 | 19:00 | 29.09.2025 | 05:00 | 23 days + 10,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 7 |  | Gleisneulage Bgl 1 und Weichenneulage W 57, 53 und 1D Bf. Mautern - Abtrag und Neuerrichtung Bahnsteig 2 (160m) |  | Y |  | 20.06.2023
| 0081 | 81-64169 |  | < > | Graz-Vbf |  | 2025 | 2025 | 36 | 37 | 06.09.2025 | 14:00 | 14.09.2025 | 18:00 | 8 days + 4,0 h | cont. | SP |  | ST | [8 empty] | Gleisneulage BGl 110 |  | N |  | 06.03.2023
| 0081 | 81-64811 |  | < > | St.Michael |  | 2025 | 2025 | 36 | 36 | 06.09.2025 | 23:00 | 07.09.2025 | 05:00 | 6,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | Einbau von Bautrenner |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64810 |  | < > | St.Michael |  | 2025 | 2025 | 37 | 50 | 13.09.2025 | 07:00 | 13.12.2025 | 24:00 | 91 days + 18,0 h | cont. | SP |  | ST | [6 empty] | 10 |  | Gleisneulage BGl 503/533; Neubau Bahnsteig 3 |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-64261 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 37 | 37 | 14.09.2025 | 00:30 | 14.09.2025 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Bauphase 1a: Querungen LS in km 169,992: Einbau Schotterbettsicherung |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64262 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 38 | 38 | 15.09.2025 | 00:30 | 15.09.2025 | 04:00 | 3,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Bauphase 1a: Querungen LS in km 169,992: Einbau Schotterbettsicherung |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-62895 |  | > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 38 | 41 | 19.09.2025 | 08:00 | 10.10.2025 | 17:00 | 21 days + 9,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1b: - Neubau der Oberleitung Pn - Mx - Einbau der neuen Weichen 4 und 6 - Begleitende Unterbau- und Kabelarbeiten |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64251 |  | > | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 38 | 39 | 19.09.2025 | 22:00 | 23.09.2025 | 04:00 | 3 days + 6,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1b: - Maschineneinsatz (REI; Kran,...) |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64250 |  | > | Pernegg |  | 2025 | 2025 | 39 | 40 | 27.09.2025 | 20:30 | 29.09.2025 | 04:30 | 2x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1b: - OL Umbau Lufttrennung Pn |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64464 |  | < | Mautern |  | 2025 | 2025 | 40 | 40 | 29.09.2025 | 19:00 | 01.10.2025 | 05:00 | 2x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Nacharbeiten zur Gleis- und Weichenneulage Bf. Mautern - SSM-Schienenschleifen |  | Y |  | 13.06.2023
| 0081 | 81-64475 |  | < | Trieben |  | 2025 | 2025 | 40 | 40 | 29.09.2025 | 19:00 | 03.10.2025 | 05:00 | 4x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Vorarbeiten zur Gleis- und Weichenneulage Bf. Trieben |  | Y |  | 13.06.2023
| 0081 | 81-64813 |  | < > | St.Michael |  | 2025 | 2025 | 40 | 50 | 03.10.2025 | 08:00 | 12.12.2025 | 16:00 | 51x 8,0 h | period. | SP |  | ST | [8 empty] | BGl 505 ist das Logistikgleis für Gleisneulage und Neubau Bahnsteig |  | N |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-64985 |  | < > | Graz-Vbf |  | 2025 | 2025 | 40 | 42 | 03.10.2025 | 20:00 | 17.10.2025 | 17:00 | 13 days + 21,0 h | cont. | SP |  | ST | [8 empty] | Einbau Gleisprovisorium und Einbau Gleisbremsen BGl 070 |  | N |  | 13.06.2023 |  |  |  | 0%
| 0081 | 81-64476 |  | < | Trieben |  | 2025 | 2025 | 40 | 43 | 05.10.2025 | 07:00 | 20.10.2025 | 05:00 | 14 days + 22,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 6 |  | Gleis- und Weichenneulage Bf. Trieben - WN W 53, 56 und 59 |  | Y |  | 13.06.2023
| 0081 | 81-64318 |  | > | Marchtrenk | Abzw Mak 1 | 2025 | 2025 | 42 | 43 | 13.10.2025 | 00:00 | 20.10.2025 | 04:00 | 7 days + 4,0 h | cont. | SP |  | LT |  |  |  | C |  | B | 2 |  | Anbindung Talgleis 002 an Weiche 70P in Mak |  | Y |  | 01.05.2023
| 0081 | 81-63294 |  | > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 42 | 44 | 13.10.2025 | 08:00 | 30.10.2025 | 16:00 | 18x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1c: - Unterbauarbeiten und Kabelarbeiten |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-63295 |  | < | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 42 | 44 | 13.10.2025 | 20:30 | 31.10.2025 | 04:30 | 18x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 1c: - Kabelwege, Unterbau, Vorarbeiten AHM,... |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64585 |  | < > | Abzw Mak 1 | Marchtrenk | 2025 | 2025 | 42 | 43 | 15.10.2025 | 00:00 | 20.10.2025 | 04:00 | 6x 4,0 h | period. | GES-N |  | LT | [8 empty] | Anbindung Weiche 70P an Gleis 002 Sperre Weststrecke |  | Y |  | 01.05.2023
| 0081 | 81-64641 |  | > | Marchtrenk | Sbl Mak 2 | 2025 | 2027 | 43 | 7 | 20.10.2025 | 04:00 | 21.02.2027 | 24:00 | 490 days | cont. | SP |  | LT | S | [5 empty] | 0 |  | Sperre der Weststreckengleise 533/534 Errichtung Autobahnbrücke A25 / Neubau Gleise, Oberleitung und Errichtung Überwerfungsbauwerk Str10102 |  | N |  | 01.05.2023
| 0081 | 81-64477 |  | < | Trieben |  | 2025 | 2025 | 43 | 43 | 21.10.2025 | 19:00 | 24.10.2025 | 05:00 | 3x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Nacharbeiten zur Gleis- und Weichenneulage Bf. Trieben |  | Y |  | 13.06.2023
| 0081 | 81-64324 |  | < > | Linz Hbf |  | 2025 | 2025 | 44 | 48 | 27.10.2025 | 00:00 | 30.11.2025 | 24:00 | 35 days | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Einbau Weiche 332 und DKW315/316, Anbindung der Gleise 303 und 305 |  | Y |  | 02.04.2023
| 0081 | 81-64478 |  | > | Trieben |  | 2025 | 2025 | 44 | 44 | 27.10.2025 | 19:00 | 31.10.2025 | 05:00 | 4x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Vorarbeiten zur Gleis- und Weichenneulage Bf. Trieben - Bauphase 2 |  | Y |  | 13.06.2023
| 0081 | 81-62896 |  | < | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 44 | 49 | 31.10.2025 | 08:00 | 02.12.2025 | 17:00 | 32 days + 9,0 h | cont. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 2: - Neubau der Oberleitung Pn - Mx - Einbau der neuen Weichen 2,3 und 5 - Begleitende Unterbau- und Kabelarbeiten |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64248 |  | < | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 44 | 45 | 31.10.2025 | 22:00 | 03.11.2025 | 04:00 | 2 days + 6,0 h | cont. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Maschineneinsatz (PM) ) |  | N |  | 02.04.2023
| 0081 | 81-63297 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 44 | 44 | 01.11.2025 | 00:30 | 01.11.2025 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Maschineneinsatz / OL-Querungen für SG |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64479 |  | > | Trieben |  | 2025 | 2025 | 44 | 46 | 01.11.2025 | 07:00 | 16.11.2025 | 05:00 | 14 days + 22,0 h | cont. | SP |  | ST |  |  |  | C |  | B | 8 |  | Gleis- und Weichenneulage Bf. Trieben - WN W 55, 57 und 58 |  | Y |  | 13.06.2023
| 0081 | 81-64808 |  | < > | Kalsdorf | Kalsdorf-Süd | 2025 | 2025 | 44 | 50 | 01.11.2025 | 22:00 | 09.12.2025 | 04:00 | 38x 6,0 h | period. | SP |  | LT | [6 empty] | 10 |  | Umbau der Oberleitung (Mitteltrennung,...) |  | Y |  | 01.05.2023 |  |  |  | 0%
| 0081 | 81-63298 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 44 | 44 | 02.11.2025 | 00:30 | 02.11.2025 | 05:00 | 4,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Maschineneinsatz und OL-Querungen Schaltgerüst |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-63299 |  | < > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 45 | 45 | 03.11.2025 | 00:30 | 03.11.2025 | 04:00 | 3,5 h | cont. | GES-N |  | LT |  |  |  | C |  | B |  |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Maschineneinsatz und OL-Querungen Schaltgerüst |  | Y |  | 02.04.2023 | Medium |  |  | 100%
| 0081 | 81-64235 |  | < > | Schwarzach-St.Veit |  | 2025 | 2025 | 45 | 47 | 03.11.2025 | 08:00 | 22.11.2025 | 23:00 | 19 days + 15,0 h | cont. | SP |  | ST |  |  |  | C |  | B |  |  | Vorarbeiten zur Inbetriebnahme ESTW Schwarzach-St. Veit |  | Y |  | 07.04.2023 | High |  |  | 100%
| 0081 | 81-64286 |  | < | Mixnitz-Bärenschützklamm |  | 2025 | 2025 | 45 | 45 | 03.11.2025 | 20:30 | 05.11.2025 | 04:30 | 2x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Maschineneinsatz (Kran) |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64249 |  | < | Pernegg |  | 2025 | 2025 | 46 | 47 | 15.11.2025 | 20:30 | 17.11.2025 | 04:30 | 2x 8,0 h | period. | SP |  | ST | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 2A: - Umbau OL Lufttrennung Pn |  | N |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64480 |  | > | Trieben |  | 2025 | 2025 | 47 | 47 | 17.11.2025 | 19:00 | 21.11.2025 | 05:00 | 4x 10,0 h | period. | SP |  | ST | [6 empty] | 6 |  | Nacharbeiten zur Gleis- und Weichenneulage Bf. Trieben |  | Y |  | 13.06.2023
| 0081 | 81-64468 |  | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2025 | 2025 | 47 | 48 | 22.11.2025 | 07:00 | 24.11.2025 | 05:30 | 1 day + 22,5 h | cont. | WF | T | LT |  |  |  | C |  | B |  |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | Y |  | 03.09.2023 | Medium |  |  | 100%
| 0081 | 81-63519 |  | < > | Schwarzach-St.Veit |  | 2025 | 2025 | 47 | 47 | 22.11.2025 | 23:00 | 23.11.2025 | 05:00 | 6,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | Inbetriebnahme ESTW Schwarzach-St. Veit |  | Y |  | 07.04.2023 | Medium |  |  | 100%
| 0081 | 81-63300 |  | > | Pernegg | Mixnitz-Bärenschützklamm | 2025 | 2025 | 49 | 50 | 06.12.2025 | 20:30 | 12.12.2025 | 04:30 | 6x 8,0 h | period. | SP |  | LT | [6 empty] | 5 |  | Umbau Bf. Mixnitz-B.: Bauphase 2b: - Abtrag der alten OL-Maste Pn - Mx SGl 1 oder 2 |  | Y |  | 02.04.2023 |  |  |  | 0%
| 0081 | 81-64812 |  | < > | St.Michael |  | 2025 | 2025 | 49 | 49 | 06.12.2025 | 23:00 | 07.12.2025 | 05:00 | 6,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | SUZ EInsatz |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0081 | 81-64814 |  | < > | St.Michael |  | 2025 | 2025 | 50 | 50 | 13.12.2025 | 23:00 | 14.12.2025 | 05:00 | 6,0 h | cont. | GES-N |  | ST |  |  |  | C |  | B |  |  | Restarbeiten (Bügeln,...) |  | Y |  | 01.05.2023 | Medium |  |  | 100%
| 0079 |  |  | < | State border | Dobova | 2023 | 2023 | 31 | 31 | 2023-07-28 19:00 | 19:00 | 2023-07-30 | 19:00 | 2 days | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | > | State border | Dobova | 2023 | 2023 | 32 | 32 | 2023-08-04 | 19:00 | 2023-08-06 | 19:00 | 2 days | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Zagorje | Zagorje | 2023 | 2023 | 6 | 40 | 2023-02-01 | 0:00 | 2023-09-30 | 23:59 | 242 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Litija | Litija | 2023 | 2023 | 35 | 52 | 2023-08-22 | 0:00 | 2023-12-31 | 23:59 | 132 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Laze | Laze | 2023 | 2023 | 23 | 29 | 2023-05-29 | 0:00 | 2023-07-11 | 23:59 | 44 days | continuous | tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < | Sava | Litija | 2023 | 2023 | 44 | 45 | 2023-10-27 | 19:00 | 2023-10-30 | 15:00 | 68 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track + track 1 in station Litija to km 534+300 |  | N |  | 2021-12-02 | unclassified | 5,6,7,1 | 1 | 0 |  |  |  | planned
| 0079 |  |  | > | Sava | Litija | 2023 | 2023 | 45 | 45 | 2023-10-30 | 15:00 | 2023-11-05 | 19:00 | 148 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track + tracks 2 and 3 in station Litija to km 534+300 |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < | Litija | Kresnice | 2023 | 2023 | 28 | 36 | 2023-07-08 | 7:00 | 2023-08-30 | 19:00 | 52 days + 36 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | > | Litija | Kresnice | 2023 | 2023 | 18 | 23 | 2023-04-29 | 7:00 | 2023-05-30 | 19:00 | 30 days + 36 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | > | Laze | Ljubljana Zalog | 2023 | 2023 | 24 | 25 | 2023-06-09 | 19:00 | 2023-06-12 | 5:00 | 58 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track |  | N |  | 2021-12-02 | unclassified | 5,6,7,1 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < | Laze | Ljubljana Zalog | 2023 | 2023 | 25 | 26 | 2023-06-16 | 19:00 | 2023-06-20 | 5:00 | 82 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track |  | N |  | 2021-12-02 | unclassified | 5,6,7,1,2 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Ljubljana | Ljubljana | 2023 | 2023 | 23 | 52 | 2023-06-01 | 0:00 | 2023-12-31 | 23:59 | 214 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Jesenice | State border | 2023 | 2023 | 46 | 47 | 2023-11-11 | 6:00 | 2023-11-13 | 6:00 | 48 hours | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 6,7,1 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Jesenice | Jesenice | 2023 | 2023 | 24 | 52 | 2023-06-07 | 0:00 | 2023-12-31 | 23:59 | 208 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | > | Hoče | Maribor Tezno | 2023 | 2023 | 45 | 47 | 2023-11-05 | 7:00 | 2023-11-18 | 19:00 | 13 days + 12 hours | continuous | track & rail |  | RT | [8 empty] | Renewal of the right track + tracks 1, 101, 201, 301 and 401 in station Maribor Tezno |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < | Hoče | Maribor Tezno | 2023 | 2023 | 47 | 52 | 2023-11-19 | 7:00 | 2023-12-31 | 19:00 | 42 days + 12 hours | continuous | track & rail |  | LT | [8 empty] | Renewal of the left track + tracks 2, 102 and 39 in station Maribor Tezno |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Maribor | Pesnica | 2023 | 2023 | 31 | 33 | 2023-07-29 | 7:35 | 2023-08-13 | 18:00 | 15 days + 10,5 hours | continuous | track & rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 |  |  | < > | Maribor | Pesnica | 2023 | 2023 | 34 | 36 | 2023-08-16 | 11:45 | 2023-08-31 | 18:10 | 16 days | periodically (5 -7 hours daily, not every day) | rail | [10 empty] | Renewal of the railway line |  | N |  | 2021-12-02 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791001 |  | < > | Krško | Krško | 2024 | 2024 |  |  | 2024-07-01 | 0:00 | 2025-03-30 | 23:59 |  | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-22 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791002 |  | < > | Litija | Litija | 2024 | 2024 |  |  | 2024-04-15 | 0:00 | 2024-12-15 | 23:59 |  | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-23 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791003 |  | < > | Ljubljana | Ljubljana | 2024 | 2025 |  |  | 2024-01-01 | 0:00 | 2025-11-30 | 23:59 | 1year 10months 29days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-24 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 792001 |  | < > | Ljubljana Šiška | Škofja Loka | 2024 | 2024 |  |  | 2024-08-19 | 7:00 | 2024-09-01 | 19:00 | 13days | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2023-11-25 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 792002 |  | < > | Jesenice | Jesenice | 2024 | 2024 |  |  | 2024-02-05 | 0:00 | 2025-10-05 | 23:59 | 1year 8 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-26 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 793001 |  | < > | Dolga Gora | Poljčane | 2024 | 2024 |  |  | 2024-04-26 | 7:00 | 2024-11-03 | 19:00 | 6months 7days | continuous | rail | [10 empty] | Maintenance |  | N |  | 2023-11-27 | unclassified | 1,2,3,4,5,6,8 | 1 | 0 |  |  |  | planned
| 0079 | 793002 |  | < > | Maribor Tezno | Maribor Tezno | 2024 | 2024 |  |  | 2024-11-02 | 7:00 | 2025-12-29 | 19:00 | 1year 1month 27days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-28 | unclassified | 1,2,3,4,5,6,9 | 1 | 0 |  |  |  | planned
| 0079 | 791002 |  | < > | Sevnica | Sevnica | 2025 | 2025 |  |  | 2025-04-07 | 0:00 | 2025-12-07 | 23:59 | 8 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-23 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 792001 |  | < > | Medvode | Škofja Loka | 2025 | 2025 |  |  | 2025-08-04 | 7:00 | 2025-08-17 | 19:00 | 13 days | continuous | rail | [10 empty] | Renewal of the railway line |  | N |  | 2023-11-25 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791002 |  | < > | Podnart | Podnart | 2025 | 2025 |  |  | 2025-10-06 | 0:00 | 2025-12-31 | 23:59 | 2months 25 days | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-23 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791004 |  | < > | State border | Dobova | 2025 | 2025 |  |  | 2025-08-08 | 0:00 | 2025-12-08 | 23:59 | 4months | continuous | rail | [10 empty] | Maintenance |  | N |  | 2023-11-29 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791004 |  | < > | Laze | Ljubljana Zalog | 2025 | 2025 |  |  | 2025-07-05 | 0:00 | 2025-08-17 | 23:59 | 1month 12days | continuous | rail | [10 empty] | left track closed |  | N |  | 2023-11-29 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0079 | 791004 |  | < > | Trbovlje | Trbovlje | 2024 | 2024 |  |  | 2024-04-15 | 0:00 | 2024-09-15 | 23:59 | 5 months | continuous | station tracks | [10 empty] | Renewal of the individual tracks |  | N |  | 2023-11-29 | unclassified | 1,2,3,4,5,6,7 | 1 | 0 |  |  |  | planned
| 0078 |  |  | < > | Zagreb Zk (Kustošija) | Zagreb Gk | 2022 | 2024 | 50 | 52 |  |  |  |  | 2 years | periodical | trask & rail renewal |  | LT+ST | X | [7 empty] | Renewal of the line section: Zagreb Zk (Kustošija) - Zagreb Gk left track and right track. Permanent closure of one track for the laying of subbase, permanent closure of one track for replacing of the track, closures by day (Monday - Sunday) 6-8 hours (as needed). Possible closures of the line section Zagreb ZK-Trešnjevka fork, closures by day (Monday - Sunday) 6-8 hours (as needed), possible closuresfor 72 hours according to the needs of contractors | 0079 | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  |  | Zagreb Zapadni kolodvor | Zagreb Zapadni kolodvor | 2022 | 2024 | 48 | 52 |  |  |  |  | 23 months | periodical | station tracks renewal |  |  | X | [7 empty] | Renewal of Zagreb Zapadni kolodvor station. Closures by day (Monday - Sunday) for 6 to 8 hours, alternately left track and right track (as needed), possible closures for 72 hours according to the needs of contractors. Possible closures of the line section Zagreb ZK-Trešnjevka fork, closures by day (Monday - Sunday) 6-8 hours (as needed), possible closuresfor 72 hours according to the needs of contractors |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Savski Marof | Zaprešić | 2024 | 2024 | 5 | 39 |  |  |  |  | 8 months | periodical | bridge reconstruction |  |  | X | [7 empty] | Bridge reconstruction km 443+568 (Brdovec) |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Zagreb GK | Sesvete | 2024 | 2025 | 39 | 38 |  |  |  |  | 12 months | periodical | bridge renewal |  |  | X | [7 empty] | Bridge reconstruction "Držićeva-Harambašićeva from km 425+966 to km 427+555 |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Zagreb GK | Sesvete | 2024 | 2025 | 23 | 22 |  |  |  |  | 12 months | periodical | bridge reconstruction km 422+224 (Lužnica) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Sesvete | Dugo Selo | 2024 | 2025 | 2 | 18 |  |  |  |  | 16 months | periodical | construction of the railway stop |  | X | X | [7 empty] | Construction of the new railway stop Sesvetska Sela km 436+775. Several track closures in duration of 48 to 72 hours. |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Sibinj | Slavonski Brod | 2024 | 2025 | 15 | 52 |  |  |  |  | 21 months | periodical | bridge reconstruction km 226+412 (Lateralni kanal) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | <> | Okučani | Nova Gradiška | 2024 | 2025 | 15 | 52 |  |  |  |  | 21 months | periodical | bridge reconstruction km 281+282 |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | < > | Dugo Selo | Novska | 2024 | 2029 | 44 | 52 |  |  |  |  | 4 years and 1 month | periodical | Upgrade, renewal, construction of the second track and construction of a new double-track line |  |  | X | [7 empty] | 8 hours day closure every working day from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the parts of the section (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). If needed, possible closures longer than 72 hours. |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | > | Andrijevci | Garčin | 2025 | 2025 | 2 | 52 |  |  |  |  | 1 year | periodical | Renewal of the left track km 198+480 - 206+260 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0078 |  |  | > | Strizivojna-Vrpolje | Andrijevci | 2025 | 2025 | 2 | 52 |  |  |  |  | 1 year | periodical | Renewal of the right track 188+500 - 197+400 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0072 |  |  | <> | Sićevo | Dimitrovgrad | 2023 | 2026 | 35 | 14 |  |  |  |  | 2 years and 6 months | periodical | Civil engineering reconstruction of the Niš – Dimitrovgrad railway line | X1) | X2) | X | [7 empty] | 1) Total railway closure for 91 days in 2025. from the 1st of April to the 1st of July 2)Traffic functioning and works execution (from Tuesday 07.00 until Wednesday 19.00 and from Saturday 07.00 until Sunday 19.00) according to the dynamics 36/36/36/60 |  | N |  | 2023-12-09 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0072 |  |  | <> | Niš station | Niš station | 2023 | 2024 | 40 | 42 |  |  |  |  | 2 years | periodical | Railway bypass Niš |  |  | X | [7 empty] | Civil works on construction of railway bypass Niš |  | N |  | 2022-12-08 | minor | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0072 |  |  | <> | Sićevo | Dimitrovgrad | 2024 | 2026 | 9 | 14 |  |  |  |  | 2 years | periodical | Electrification of the Niš – Dimitrovgrad railway line and railway bypass Niš |  |  | X | [7 empty] | Traffic functioning and works execution will be performed alternately during time intervals that are going to be agreed with the Contractor |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
| 0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2026 | 19 | 11 |  |  |  |  | 5 years and 10 months | periodical | railway line km 22+554 to km 42+200 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Elin-Pelin | Kostenets | 2019 | 2024 | 41 | 39 |  |  |  |  | 5 years | periodical | railway line km 42+200 to km 62+400 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2025 | 33 | 52 |  |  |  |  | 5 years and 4 months | periodical | railway line km 62+400 to km 73 +598 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Kostenets | Septemvri | 2019 | 2024 | 15 | 33 |  |  |  |  | 5 years and 4 months | periodical | railway line | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2022-12-08 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Voluyak | Sofia | 2023 | 2025 | 50 | 50 | 2023-12-10 |  | 2025-12-13 |  | 24 months | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption of one of the running lines. Bypass line - Voluyak - Iliyantsi - Sofia |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Dragoman | Voluyak | 2023 | 2026 | 50 | 50 | 2023-12-10 |  | 2026-12-12 |  | 36 months | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be carried out under the conditions of full interruption of one of the running lines. The train traffic will be conducted along a newly built running line (the railway line is doubled) |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Sofia station | Sofia station | 2023 | 2025 | 50 | 50 | 2023-12-10 |  | 2025-12-13 |  | 24 months | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Interruption of traffic along the eastern part of the station tracks from track 8 to track 14. Partial isolation of the signalling equipment at the station. Bypass line - Voluyak - Iliyantsi - Yana - Kazichene |  | N |  | 2023-12-04 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Septemvri | Dobrinishte | 2024 | 2024 | 27 | 31 | 2024-07-01 |  | 2024-07-30 |  | 30 days | continuous | Repair of equipment | X | [5 empty] | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption. No bypass line is available |  | N |  | 2022-12-08 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | overpass km 97+217 | overpass km 97+217 | 2023 | 2023 | 20 | 20 | 2023-05-10 | 9:00 | 2023-05-10 | 17:00 | 8 hours | continuous | Overpass construction | X | [5 empty] | X |  |  |  | During the interruption from Plovdiv to Dimitrovgrad, a bypass route Kazichene – Karlovo – Plovdiv/transboarding is offered. |  | N |  | 2022-12-08 | major | 3 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 23 | 23 | 2023-06-01 | 8:00 | 2023-06-02 | 8:00 | 24 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | During the interruption from Plovdiv to Dimitrovgrad, a bypass route Plovdiv-MihailovoDimitrovgrad / transboarding is offered. |  | N |  | 2022-12-08 | major | 4.5 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 23 | 23 | 2023-06-02 | 8:00 | 2023-06-03 | 8:00 | 24 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | No capacity is offered for freight traffic/transboarding |  | N |  | 2022-12-08 | major | 5.6 | 1 |  |  |  |  | publication
| 0052 |  |  | < > | Krumovo station | Krumovo station | 2023 | 2023 | 32 | 32 | 2023-08-01 | 8:00 | 2023-08-03 | 8:00 | 48 hours | continuous | Change of switches | X | [5 empty] | X |  |  |  | No capacity is offered for freight traffic/transboarding |  | N |  | 2022-12-08 | major | 2,3,4 | 1 |  |  |  |  | publication
New
Changed
Deleted
Map
Show all

## TCR 2023 Map SŽ-I
Zagorje – the closure of individual tracks 01.02. to 30.09.2023
Litija – the closure of individual tracks 22.08. to 31.12.2023
Laze – the closure of individual tracks 29.05. to 11.07.2023
Litija - Kresnice (LT) 08.07 to 30.08.2023 continuously
Litija - Kresnice (RT) 29.04 to 30.05.2023 continuously
Laze – Ljubljana Zalog (RT) 09.06 to 12.06.2023 continuously
Laze – Ljubljana Zalog (LT) 16.06 to 20.06.2023 continuously
Ljubljana - the closure of individual tracks 01.06.do 31.12.2023
Jesenice – the closure of individual tracks 07.06. to 31.12. 2023
Ljubljana Šiška – the closure of individual tracks 01.01. to 31.05.2023

## TCR 2024 Map SŽ-I
Krško – the closure of individual tracks 1.7.-31.12.2024
Litija- the closure of individual tracks 15.4.-15.12.2024
Trbovlje-the closure of individual tracks 15.4.-15.9.2024
Ljubljana – the closure of individual tracks 01.01. to 31.12.2024
Jesenice – the closure of individual tracks 5.2-31.12.2024
Lj. Šiška-Škofja Loka- total closure 19.8.-1.9.2024
Dolga Gora-Poljčane- right/left track closed 26.4.-3.11.2024
Maribor Tezno- the closure of individual tracks 2.11.-29.12.2024

## TCR 2025 Map SŽ-I
Ljubljana - closure of tracks 01.01.do 30.11.2025
Krško- closure of tracks 1.1.-30.3.2025
Sevnica-closure of tracks 7.4.-7.12.2025
Medvode-Škofja Loka-4.8.-17.8. total closure
Jesenice- closure of tracks 1.1.-5.10.2025
Podnart-closure of tracks 6.10.-31.12.2025
Maribor Tezno- closure of tracks 2.11.-29.12.2025
State border-Dobova right/left track 8.8.-5.10., 6.10.-8.12.2025
Laze-Ljubljana Zalog-left track closed 5.7.-17.8.2025

## TCR Map HŽI
Zagreb ZK (Kustošija) - Zagreb GK | Dugo Selo - Novska | Andrijevci - Garčin
2022 - 2024 | 2024 - 2029 | Strizivojna Vrpolje - Andrijevci
Periodical | Periodical | 2025
Track and rail renewal | Upgrade, renewal, construction of | Renewal of the tracks
the second track and construction of
a new double-track line

## TCR Map IŽS
Niš station
2023 – 2024
Periodical
Railway bypass Niš
Sićevo – Dimitrovgrad
2024 – 2026
Periodical
Reconstruction & Electrification of the Niš – Dimitrovgrad railway line

## TCR Map NRIC
Dragoman – Voluyak
10.12.2023.-14.12.2024., 15.12.2024-13.12.2025.
Modernization of the railway infrastructure
Voluyak – Sofia
10.12.2023.-14.12.2024., 15.12.2024.-13.12.2025.
Modernization of the railway infrastructure
Sofia station
10.12.2023.-14.12.2024., 15.12.2024.-13.12.2025.
Modernization of the railway infrastructure
Sofia – Septemvri
15.12.2024.-13.12.2025.
Modernization of the railway infrastructure
Krumovo – Katunitsa
1.4.-7.4.2024., 1.5.-7.5.2024., 4.6.-10.6.2025.
Works along switches