## Schedule
10000
IM | ID | Section | Direction | Line |  | Year |  | Week |  | Period from |  | Period to |  | Duration | Time of day | Reason for restriction | Traffic impact |  |  |  |  | Traffic measures |  |  |  |  | Description | International coordination | In yearly timetable | IM Project ID (Optional) | Last update | Classification | Weekdays | Interval | Affected estimated travel volume | Affected border | Deviation location | Deviation border | Status | Additional information | Automatic process | Bitmap Days | Variant
|  |  |  | From | To | From | To | From | To | Date from | Time from | Date to | Time to |  |  |  | Total Closure | Reduced Track Availability | Speed Restrictions | Weight, Length, Profile | No catenary | Cancellation | Re-routing | Train replacement | Delays | Other
ÖBB Infra | 81-B-90480 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Frohnleiten | Peggau-Deutschfeistritz | 2027 | 2027 | 28 | 28 | 12.07.2027 | 22:30 | 17.07.2027 | 04:00 | 4 days + 5,5 h | periodically | Others | T | LT | [6 empty] | 0 |  | Erneuerung Durchlass km 187,904 Vorarbeiten |  | N | SAC608 (20-187758) | 11.11.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-83847 | Salzburg Hbf (in Sb)=Wörgl Hbf (in W) | < > | Werfen | Bischofshofen | 2027 | 2027 | 14 | 19 | 05.04.2027 | 00:00 | 15.05.2027 | 24:00 | 41 days | periodically | Others | T | LT | [6 empty] | 0 |  | Pfarrwerfen; Erneuerung Bahnsteigbeleuchtung und Bahnsteigentwässerung; Bahnsteigverlängerung auf 220m |  | N | IMT021 | 26.09.2024 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-98009 | St.Michael (in M)=Selzthal (in Sl) | < > | Stadt Rottenmann | Selzthal-Süd | 2027 | 2027 | 44 | 46 | 02.11.2027 | 00:00 | 20.11.2027 | 24:00 | 19 days | periodically | Others | T | LT | [6 empty] | 0 |  | Sanierung der Futtermauer km 140,683 - 144,749 |  | N | BAE0.IHA9ISSY | 26.08.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-90533 | Marchtrenk (in Mak)=Wels Hbf | < > | Wels Vbf | Wels Vbf-Terminal | 2027 | 2027 | 18 | 18 | 05.05.2027 | 21:00 | 09.05.2027 | 18:00 | 3 days + 21,0 h | continuous | Others | T | LT |  |  |  | C |  |  | 0 |  | Weichenneulage 112, 113 |  | N |  | 26.05.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-99300 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice) | < > | Rosenbach | Jesenice | 2027 | 2027 | 5 | 47 | 01.02.2027 | 07:00 | 22.11.2027 | 13:00 | 294 days + 6,0 h | continuous | Maintenance | T | LT |  |  |  | C | R | T | 0 |  | Wartungsarbeiten im Karawankentunnel | Affected Border: 79 Affected Ims: Jesenice Deviation Border(s): Spielfeld | N |  | 30.10.2025 | Major |  |  | 51-100%
ÖBB Infra | 81-B-91936 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Mixnitz-Bärenschützklamm | - | 2027 | 2027 | 21 | 24 | 29.05.2027 | 14:00 | 15.06.2027 | 17:00 | 17 days + 3,0 h | continuous | Miscellaneous | T | LT |  |  |  | C | R | T | 0 |  | Bahnhofsumbau Bf. Mixnitz-Bärenschützklamm Bauphasen 2027 Tragwerk Mixnitzbach - Fertigstellungsarbeiten Gleis 2 |  | N | BAP010 | 01.06.2025 | High |  |  | 31-50%
ÖBB Infra | 81-B-82001 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Rothenthurn | - | 2026 | 2027 | 51 | 27 | 20.12.2026 | 00:00 | 09.07.2027 | 16:00 | 201 days + 15,0 h | continuous periodically | Miscellaneous | T | LT | S |  |  | C |  | T | 0 |  | Bahnhofumbau Rothenthurn - Bauphasen 19 - 31 |  | N | NAA141 | 02.04.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-89302 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Penk | - | 2027 | 2027 | 19 | 21 | 13.05.2027 | 00:00 | 24.05.2027 | 24:00 | 12 days | continuous periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Gründliche Durcharbeitung Weichen 1-5 Bf. Penk |  | N | 25-208126 | 03.06.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-91380 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice), Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), Villach Seebach=Villach Süd Gvbf-West (in Vsv) | < > | Villach Süd Gvbf-Auen | - | 2027 | 2027 | 32 | 35 | 15.08.2027 | 00:00 | 30.08.2027 | 24:00 | 16 days | continuous | Others | T | LT |  |  |  | C | R | T | 10 |  | Villach Süd Gvbf - Auen Weichenneulagen W101,106, 107 sowie Gleisneulage Gl 104, 106 von km 381,875 bis km 383,410 |  | N |  | 02.06.2025 | High |  |  | 31-50%
ÖBB Infra | 81-B-90090 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Linzerhaus | Selzthal | 2027 | 2027 | 35 | 37 | 03.09.2027 | 22:00 | 13.09.2027 | 05:00 | 9 days + 7,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Gesamtsperre Pyhrn Süd | Affected Border: 80 Affected Ims: Passau Deviation Border(s): Kufstein, Freilassing | N | SAB417 | 15.05.2025 | High |  |  | 51-100%
ÖBB Infra | 81-B-92587 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl), St.Michael (in M)=Selzthal (in Sl) | < > | Selzthal | - | 2027 | 2027 | 31 | 32 | 02.08.2027 | 08:00 | 11.08.2027 | 18:00 | 9 days + 10,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | WN/WA DKW 66/67, W 76,77 und 78 Bf. Selzthal |  | N | 21-191813 | 16.06.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-92589 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl), St.Michael (in M)=Selzthal (in Sl) | < > | Selzthal | - | 2027 | 2027 | 32 | 33 | 12.08.2027 | 08:00 | 21.08.2027 | 18:00 | 9 days + 10,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | WN/WA DKW 68/69, W 72, 73 und 74 Bf. Selzthal |  | N | 21-191813 | 16.06.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-92722 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Bruck a.d.Mur-Fbf | Peggau-Deutschfeistritz | 2027 | 2027 | 2 | 6 | 17.01.2027 | 01:00 | 08.02.2027 | 04:00 | 22 days + 3,0 h | continuous | Miscellaneous | T | LT |  |  |  | C |  |  | 0 |  | Oberleitungserneuerung Bf. Bruck a. d. Mur Fbf Montage Quertragwerke zw. Bk und Bm |  | N | AMV699.06 | 20.06.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-83928 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Schwarzach-St.Veit | Mallnitz-Obervellach | 2027 | 2027 | 6 | 27 | 08.02.2027 | 00:00 | 09.07.2027 | 21:00 | 151 days + 20,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Tauernsperre - Modernisierung Tauerntunnel, Modul 2 - Viaduktsanierungen - Tunnelaufweitung und Stromschienenmontage Klamm-Tunnels - Instandsetzungsarbeiten im gesamten Streckenverlauf | Affected Border: 80, 83, 79 Affected Ims: Kufstein, Jesenice, Brenner Deviation Border(s): Tarvis | Y | AMA49901 | 03.12.2025 | Major |  |  | 51-100%
ÖBB Infra | 81-B-92605 | Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Klaus | - | 2027 | 2027 | 34 | 35 | 23.08.2027 | 23:10 | 03.09.2027 | 05:30 | 10 days + 6,3 h | periodically | Others | T | LT |  |  |  | C | R |  | 0 |  | Klaus; Erneuerung der Oberleitungsanlage, km 60,459 |  | N | 24-204919 | 16.06.2025 | Minor |  |  | 51-100%
ÖBB Infra | 81-B-84782 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Linz Hbf | Hörsching | 2027 | 2027 | 48 | 48 | 05.12.2027 | 01:30 | 05.12.2027 | 02:30 | 1,0 h | continuous | Miscellaneous | T | LT |  |  |  | C |  |  | 0 |  | Softwaretausch und Inbetriebnahme der Ersatzhaltestelle Leonding |  | N |  | 17.07.2025 | Minor |  |  | 51-100%
ÖBB Infra | 81-B-91443 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Linz Hbf | - | 2027 | 2027 | 30 | 36 | 26.07.2027 | 00:00 | 11.09.2027 | 24:00 | 48 days | continuous periodically | Miscellaneous | T | LT | [6 empty] | 0 |  | Viergleisigen Anbindung Linz Hbf Bauphase 32 |  | N |  | 18.06.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90656 | Marchtrenk (in Mak)=Wels Hbf | < > | Wels Vbf - gesamt | - | 2027 | 2027 | 46 | 47 | 20.11.2027 | 18:00 | 22.11.2027 | 17:00 | 1 day + 23,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Weichenneulage 354 |  | N |  | 26.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-92523 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Selzthal | Hieflau | 2027 | 2027 | 46 | 46 | 15.11.2027 | 00:00 | 19.11.2027 | 24:00 | 5 days | continuous | Others | T | LT |  |  |  | C | R |  | 0 |  | OL-Erneuerung Bf. Admont und Gstatterboden |  | N |  | 12.06.2025 | Medium |  |  | 51-100%
ÖBB Infra | 81-B-87768 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice) | < > | Jesenice - gesamt | Rosenbach | 2026 | 2027 | 50 | 39 | 13.12.2026 | 00:00 | 27.09.2027 | 24:00 | 288 days + 23,0 h | continuous | Others | T | LT |  |  |  |  | R |  | 0 |  | Bahnhofumbau Jesenice - Bauphasen 7-10 | Affected Border: 79 Affected Ims: Jesenice Deviation Border(s): Spielfeld | N |  | 05.09.2025 | Major |  |  | 51-100%
ÖBB Infra | 81-B-91440 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Linz Hbf (in Lz)=Gaumberg | < > | Linz Hbf | - | 2027 | 2027 | 10 | 11 | 08.03.2027 | 07:00 | 21.03.2027 | 17:00 | 13 days + 10,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Gleineulage 422, 424 |  | N |  | 27.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-84777 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Linz Hbf | Marchtrenk | 2027 | 2027 | 48 | 49 | 05.12.2027 | 01:30 | 11.12.2027 | 24:00 | 6 days + 22,5 h | continuous | Miscellaneous | T | LT | S |  |  | C | R | T | 0 |  | Viergleisiger Ausbau: Einbau LM16 im Bereich Oftering 2. Anschwenkung an Gleis 3 neu im Bereich Leonding |  | N |  | 17.07.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-84747 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Marchtrenk (in Mak)=Traun (in T) | < > | Hörsching | Marchtrenk | 2027 | 2027 | 3 | 5 | 24.01.2027 | 00:00 | 05.02.2027 | 24:00 | 13 days | continuous | Miscellaneous | T | LT | S |  |  | C | R | T | 0 |  | Viergleisiger Ausbau 1. Anschwenkung an Gleis 4 in Marchtrenk |  | N |  | 28.04.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90529 | Marchtrenk (in Mak)=Wels Hbf | < > | Wels Vbf | Wels Vbf-Terminal | 2027 | 2027 | 43 | 44 | 30.10.2027 | 18:00 | 01.11.2027 | 18:00 | 2 days + 1,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Weichenneulage 114 |  | N |  | 25.06.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90482 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Frohnleiten | Peggau-Deutschfeistritz | 2027 | 2027 | 28 | 29 | 17.07.2027 | 18:00 | 19.07.2027 | 21:00 | 2 days + 3,0 h | continuous | Others | T | LT | S |  |  | C |  | T | 0 |  | Erneuerung Durchlass km 187,904 Hauptarbeiten |  | N | SAC608 (20-187758) | 17.11.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-84755 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Marchtrenk (in Mak)=Wels Hbf, Marchtrenk (in Mak)=Wels Hbf, Marchtrenk (in Mak)=Traun (in T) | < > | Marchtrenk | Sbl Hoe 2 | 2027 | 2027 | 29 | 30 | 23.07.2027 | 00:00 | 01.08.2027 | 24:00 | 10 days | continuous | Miscellaneous | T | LT | S |  |  | C | R | T | 0 |  | Viergleisiger Ausbau 2. Anschwenkung an Gleis 3 in Marchtrenk |  | N |  | 28.04.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90941 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Mallnitz-Obervellach | Penk | 2027 | 2027 | 5 | 26 | 05.02.2027 | 00:00 | 02.07.2027 | 24:00 | 147 days + 23,0 h | periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Erneuerung der elektrotechnischen Anlagen im Kaponigtunnel |  | N |  | 24.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-91934 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Mixnitz-Bärenschützklamm | - | 2027 | 2027 | 6 | 8 | 12.02.2027 | 00:00 | 22.02.2027 | 24:00 | 11 days | continuous | Miscellaneous | T | LT |  |  |  | C |  |  | 0 |  | Bahnhofsumbau Bf. Mixnitz-Bärenschützklamm Bauphasen 2027 - Einbau Hilfsbrücken Gl 1,2 - Mixnitzbachbrücke |  | N | BAP010 | 19.07.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-99288 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice), Villach Süd Gvbf-Ausfgr (in Vsv)=Abzww Villach Süd Gvbf-Ost (in Vsv) | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2027 | 2027 | 11 | 12 | 20.03.2027 | 07:00 | 22.03.2027 | 05:30 | 1 day + 22,5 h | continuous | Maintenance | T | LT |  |  |  | C | R | T | 0 |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | N |  | 30.10.2025 | Medium |  |  | 51-100%
ÖBB Infra | 81-B-79759 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Mallnitz-Obervellach | - | 2027 | 2027 | 15 | 23 | 12.04.2027 | 08:00 | 12.06.2027 | 18:00 | 61 days + 10,0 h | continuous periodically | Others | T | LT | [6 empty] | 0 |  | Böckstein - Mallnitz-Obervellach; Gleisneulage und Planumsverbesserung Gl. 2,km 43,557 - 45,069 |  | N |  | 14.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-92596 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl), St.Michael (in M)=Selzthal (in Sl) | < > | Selzthal | - | 2027 | 2027 | 35 | 36 | 30.08.2027 | 00:00 | 08.09.2027 | 24:00 | 10 days | continuous | Others | T | LT | [6 empty] | 0 |  | Bf. Selzthal; WA inkl. Schotterbetterneuerung W225, W226, DKW231/232 |  | N | 21-191168, 21-192762 | 16.06.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-84776 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Linz Hbf | Marchtrenk | 2027 | 2027 | 47 | 48 | 26.11.2027 | 22:30 | 05.12.2027 | 01:30 | 8 days + 3,0 h | continuous | Miscellaneous | T | LT | S |  |  | C | R | T | 0 |  | Viergleisiger Ausbau: Einbau LM16 im Bereich Oftering 1. Anschwenkung an Gleis 4 neu im Bereich Leonding |  | N |  | 17.07.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90929 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Gummern | Paternion-Feistritz | 2027 | 2027 | 7 | 12 | 20.02.2027 | 06:00 | 27.03.2027 | 05:00 | 34 days + 23,0 h | continuous periodically | Others | T | LT |  |  |  | C |  | T | 0 |  | Gummern - Paternion-Feistritz, GN Sgl 1km 181,600 - 182,290 |  | N | SAA99921 | 18.06.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-89473 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Admont | Ardning | 2027 | 2027 | 35 | 48 | 04.09.2027 | 00:00 | 29.11.2027 | 05:00 | 86 days + 6,0 h | periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Neubau Schwimmbadbrücke km 137,785 Bf. Selzthal |  | N |  | 03.06.2025 | Minor |  |  | 51-100%
ÖBB Infra | 81-B-90055 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Spittal-Millstättersee | - | 2027 | 2027 | 10 | 14 | 08.03.2027 | 00:00 | 11.04.2027 | 24:00 | 34 days + 23,0 h | continuous periodically | Others | T | LT | [6 empty] | 0 |  | Spittal a.M., WN W 1,2,3,4, 7 und GAL Gl.105 km 80,006 - 80,315 |  | N | 23-199148 | 14.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-89468 | Abzw Ams 11=Bischofshofen (in Bo), Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Admont | Ardning | 2027 | 2027 | 21 | 26 | 27.05.2027 | 00:00 | 28.06.2027 | 05:00 | 32 days + 5,0 h | periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Neubau Schwimmbadbrücke km 137,785 Bf. Selzthal |  | N |  | 03.06.2025 | Minor |  |  | 51-100%
ÖBB Infra | 81-B-93398 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Marchtrenk (in Mak)=Wels Hbf, Marchtrenk (in Mak)=Wels Hbf, Marchtrenk (in Mak)=Traun (in T) | < > | Marchtrenk | Wels Hbf | 2027 | 2027 | 3 | 3 | 24.01.2027 | 01:30 | 24.01.2027 | 02:30 | 1,0 h | continuous | Miscellaneous | T | LT |  |  |  | C |  |  | 0 |  | Softwaretausch für Anschwenkung an Neubau und Vollinbetriebnahme Kreuzungsbauwerk Marchtrenk |  | N |  | 17.07.2025 | Minor |  |  | 51-100%
ÖBB Infra | 81-B-82903 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Peggau-Deutschfeistritz | Üst Pg 2 | 2027 | 2027 | 5 | 48 | 05.02.2027 | 20:00 | 05.12.2027 | 04:30 | 302 days + 8,5 h | continuous periodically | Others | T | LT |  |  |  | C |  |  | 7 |  | Erneuerung Brücke Feldgasse km 192,144 |  | N | 20-186868 | 11.11.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-90659 | Marchtrenk (in Mak)=Wels Hbf | < > | Wels Vbf - gesamt | - | 2027 | 2027 | 47 | 48 | 27.11.2027 | 18:00 | 29.11.2027 | 17:00 | 1 day + 23,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Weichenneulage 354 |  | N |  | 26.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-89294 | St.Michael (in M)=Selzthal (in Sl) | < > | Wald am Schoberpaß | Kalwang | 2027 | 2027 | 22 | 30 | 31.05.2027 | 00:00 | 28.07.2027 | 04:30 | 58 days + 4,5 h | continuous periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Erneuerung der Tunnelfunkanlage im Unterwaldertunnel |  | N | 24-204933 | 25.04.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-91682 | St.Michael (in M)=Selzthal (in Sl) | < > | Selzthal | Rottenmann | 2027 | 2027 | 39 | 40 | 01.10.2027 | 22:00 | 04.10.2027 | 05:00 | 2 days + 7,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Teilerneuerung W 284 und W 285 Bf. Selzthal | Affected Border: 80, 83, 79 Affected Ims: Freilassing, Passau, Spielfeld Deviation Border(s): Kufstein, Jesenice, Brenner | N | 21-191166 | 30.05.2025 | Medium |  |  | 51-100%
ÖBB Infra | 81-B-79762 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Mallnitz-Obervellach | - | 2027 | 2027 | 15 | 18 | 12.04.2027 | 08:00 | 08.05.2027 | 16:00 | 26 days + 8,0 h | periodically | Others | T | LT | [6 empty] | 0 |  | Böckstein - Mallnitz-Obervellach; Vorarbeiten zur Gleisneulage und Planumsverbesserung Gl. 2,km 43,557 - 45,069 |  | N |  | 28.04.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-79765 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Mallnitz-Obervellach | - | 2027 | 2027 | 22 | 23 | 31.05.2027 | 08:00 | 12.06.2027 | 16:00 | 12 days + 8,0 h | periodically | Others | T | LT | [6 empty] | 0 |  | Böckstein - Mallnitz-Obervellach; Gleisneulage und Planumsverbesserung Gl. 2,km 43,557 - 45,069 |  | N |  | 28.04.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-89929 | St.Michael (in M)=Selzthal (in Sl) | < > | Seiz | - | 2027 | 2027 | 30 | 41 | 26.07.2027 | 00:00 | 16.10.2027 | 24:00 | 83 days | continuous periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Bf. Seiz; Weichenneulagen und Planumsverbesserung W1, W2, W5, W6, W7 Km 194,696-194,965 |  | N | SAV644, SAU602 | 15.05.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90845 | Salzburg Hbf (in Sb)=Wörgl Hbf (in W) | < > | Hallein | - | 2027 | 2027 | 5 | 8 | 01.02.2027 | 07:00 | 28.02.2027 | 22:00 | 27 days + 15,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Gleisneulage Gl. 106, 108, 110, 112 Bf. Hallein |  | N | SAB582 | 22.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-91910 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj), Bruck a.d.Mur (in Bm)=Staatsgrenze nächst Thörl-Maglern -(Tarvisio B.), Bruck a.d.Mur-Übelstein (in Bm)=Bruck a.d.Mur-Stadtwald (in Bm) | < > | Bruck a.d.Mur - gesamt | - | 2027 | 2027 | 42 | 44 | 24.10.2027 | 06:00 | 07.11.2027 | 05:00 | 14 days | continuous | Others | T | LT |  |  |  | C | R | T | 20 |  | Gleisneulage Gl.4 und Weichenneulage W214 inkl. Planumsverbesserung km 157,552-158,216, |  | N | 20-184573 | 01.06.2025 | High |  |  | 31-50%
ÖBB Infra | 81-B-91935 | Wien Hbf-Südosttangente (in Wbf)=Staatsgrenze nächst Spielfeld-Straß - (Sentilj) | < > | Mixnitz-Bärenschützklamm | - | 2027 | 2027 | 18 | 21 | 07.05.2027 | 22:30 | 26.05.2027 | 17:00 | 18 days + 18,5 h | continuous | Miscellaneous | T | LT |  |  |  | C | R |  | 0 |  | Bahnhofsumbau Bf. Mixnitz-Bärenschützklamm Bauphasen 2027 Tragwerk Mixnitzbach - Fertigstellungsarbeiten Gleis 1 |  | N | BAP010 | 01.06.2025 | High |  |  | 31-50%
ÖBB Infra | 81-B-92907 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Paternion-Feistritz | - | 2027 | 2027 | 30 | 32 | 26.07.2027 | 00:00 | 13.08.2027 | 24:00 | 19 days | periodically | Others | T | LT |  |  |  | C |  |  | 0 |  | Paternion-Feistritz; GN Gl. 201, 202 und 204 km 182,821 - 183,473 |  | N | SAW730 | 07.08.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-90086 | Linz Hbf (in Lz)=Selzthal (in Sl) | < > | Rohr-Bad Hall | Kirchdorf a.d.Krems | 2027 | 2027 | 34 | 35 | 23.08.2027 | 06:00 | 03.09.2027 | 22:00 | 11 days + 16,0 h | continuous | Others | T | LT |  |  |  | C | R | T | 0 |  | Gesamtsperre Pyhrn Nord | Affected Border: 80 Affected Ims: Passau Deviation Border(s): Kufstein, Freilassing | N | SAB417 | 15.05.2025 | High |  |  | 51-100%
ÖBB Infra | 81-B-83851 | Salzburg Hbf (in Sb)=Wörgl Hbf (in W) | < > | Werfen | Bischofshofen | 2027 | 2027 | 20 | 25 | 18.05.2027 | 22:00 | 26.06.2027 | 05:00 | 38 days + 7,0 h | periodically | Others | T | LT | [6 empty] | 0 |  | Pfarrwerfen; Erneuerung Bahnsteigbeleuchtung und Bahnsteigentwässerung; Bahnsteigverlängerung auf 220m |  | N | IMT021 | 26.09.2024 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-90649 | Marchtrenk (in Mak)=Wels Hbf | < > | Wels Vbf | Wels Vbf-Terminal | 2027 | 2027 | 44 | 45 | 06.11.2027 | 18:00 | 08.11.2027 | 23:00 | 2 days + 5,0 h | continuous | Others | T | LT | [6 empty] | 0 |  | Weichenneulage 114 |  | N |  | 25.06.2025 | Minor |  |  | 1-10%
ÖBB Infra | 81-B-92913 | Schwarzach-St.Veit=Villach Hbf (in Vb) | < > | Paternion-Feistritz | - | 2027 | 2027 | 32 | 37 | 14.08.2027 | 22:00 | 13.09.2027 | 04:30 | 29 days + 6,5 h | continuous | Others | T | LT |  |  |  | C |  |  | 0 |  | Paternion-Feistritz; GN Gl. 201, 202 und 204 km 182,821 - 183,473 |  | N | SAW730 | 07.08.2025 | Medium |  |  | 11-30%
ÖBB Infra | 81-B-90839 | Knoten Wagram (in Wat)=Salzburg Hbf (in Sb), Salzburg Hbf (in Sb)=Wörgl Hbf (in W), Salzburg Itzling=Salzburg Gnigl-Einfgr (in Sb) | < > | Salzburg Hbf - gesamt | - | 2027 | 2027 | 14 | 15 | 08.04.2027 | 00:00 | 12.04.2027 | 24:00 | 5 days | continuous | Others | T | LT | [6 empty] | 0 |  | Gleis und Weichenneulage |  | N |  | 22.05.2025 | Unclassified |  |  | 0%
ÖBB Infra | 81-B-86371 | Marchtrenk (in Mak)=Traun (in T) | < > | Marchtrenk | Sbl Mak 1P | 2027 | 2027 | 31 | 37 | 02.08.2027 | 00:00 | 13.09.2027 | 00:00 | 42 days | continuous | Miscellaneous | T | LT |  |  |  | C |  |  | 0 |  | Neubau Gleis 1 / Anbindung an Schleife Traun |  | N |  | 28.04.2025 | Major |  |  | 51-100%
ÖBB Infra | 81-B-99294 | Villach Süd Gvbf-Auen (in Vsv)=Staatsgrenze nächst Rosenbach - (Jesenice), Villach Süd Gvbf-Ausfgr (in Vsv)=Abzww Villach Süd Gvbf-Ost (in Vsv) | < > | Abzww Villach Süd Gvbf-Ost | Staatsgrenze nächst Rosenbach | 2027 | 2027 | 38 | 39 | 25.09.2027 | 07:00 | 27.09.2027 | 05:30 | 1 day + 22,5 h | continuous | Maintenance | T | LT |  |  |  | C | R | T | 0 |  | Diverse Instandhaltungs- und Erneuerungsarbeiten |  | N |  | 30.10.2025 | Medium |  |  | 51-100%
0079 | 7907 | Zidani Most - Dobova | < > | Sevnica | Sevnica | 2026 | 2026 | 25 | 53 | 2026-06-19 | 10:00 | 2026-12-31 | 19:00 | 195days 7h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7910 | Koper - Ljubljana | < > | Borovnica | Verd | 2026 | 2026 | 27 | 39 | 2026-07-01 | 7:00 | 2026-09-15 | 19:00 | 76days 12h | continuous | Track & Rail |  | ST |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7911 | Koper - Ljubljana | < > | Borovnica | Verd | 2026 | 2026 | 38 | 50 | 2026-09-16 | 7:00 | 2026-12-10 | 19:00 | 85days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7913 | Koper - Ljubljana | < > | Brezovica | Brezovica | 2026 | 2026 | 2 | 27 | 2026-01-10 | 7:00 | 2026-06-29 | 19:00 | 170days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7914 | Koper - Ljubljana | < > | Preserje | Preserje | 2026 | 2026 | 2 | 26 | 2026-01-11 | 7:00 | 2026-06-25 | 19:00 | 165days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7916 | Koper-Ljubljana | < > | Ljubljana | Ljubljana | 2023 | 2026 | 46 | 42 | 2024-11-10 | 7:00 | 2026-10-02 | 19:00 | 691days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7923 | Ljubljana - Jesenice | < > | Jesenice | Jesenice | 2026 | 2026 | 6 | 39 | 2026-02-06 | 7:00 | 2027-09-27 | 19:00 | 598days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7918 | Ljubljana - Jesenice | < > | Ljubljana Šiška | Kranj | 2026 | 2026 | 39 | 41 | 2026-09-25 | 7:00 | 2026-10-11 | 19:00 | 16days 12h | continuous | Track & Rail | T | LT+ST |  |  |  | C | R | B |  |  | maintenance |  | N |  | 2025-12-05
0079 | 7924 | Zidani Most - Dobova | < > | Krško | Krško | 2027 | 2027 | 4 | 38 | 2027-01-25 | 7:00 | 2027-09-20 | 19:00 | 238days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-05
0079 | 7925 | Zidani Most - Dobova | < > | Sevnica | Sevnica | 2027 | 2027 | 42 | 5 | 2027-10-18 | 8:00 | 2028-01-30 | 20:00 | 104days 12h | continuous | Track & Rail | [10 empty] | Station renewal |  | N |  | 2025-12-06
0079 | 7910 | Koper - Ljubljana | < > | Borovnica | Verd | 2027 | 2027 | 26 | 39 | 2027-07-01 | 7:00 | 2027-09-30 | 19:00 | 91days 12h | continuous | Track & Rail |  | ST |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7911 | Koper - Ljubljana | < > | Borovnica | Verd | 2027 | 2027 | 39 | 49 | 2027-10-01 | 7:00 | 2027-12-11 | 19:00 | 71days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0079 | 7912 | Koper - Ljubljana | < > | Preserje | Borovnica | 2027 | 2027 | 51 | 5 | 2026-12-16 | 7:00 | 2027-01-24 | 19:00 | 39days 12h | continuous | Track & Rail |  | LT |  |  |  | C |  | B | 20 |  | maintenance |  | N |  | 2025-12-05
0078 |  | Savski Marof - Zagreb | <> | Savski Marof | Zaprešić | 2026 | 2026 | 22 | 52 | 2026-06-01 | 0:00 | 2026-12-31 | 23:59 | 7 months | periodical | bridge reconstruction km 442+225 (Lužnica) |  | X | X | [7 empty] | Track closure during the removing and instaling a new bridge construction - 48 hours |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb Glavni kolodvor | <> | Zagreb GK | Zagreb GK | 2026 | 2027 | 5 | 52 | 2026-02-01 | 0:00 | 2027-12-31 | 23:59 | 23 months | periodical | Tracks renewal |  | X | X | [7 empty] | Station tracks renewal and switch points replacement |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb Ranžirni kolodvor | <> | Zagreb RK | Zagreb RK | 2025 | 2027 | 48 | 52 | 2025-12-31 | 0:00 | 2027-12-31 | 23:59 | 25 months | periodical | Switch points replacement |  | X | X | [7 empty] | Switch points replacement in station Zagreb Ranžirni kolodvor |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb GK - Dugo Selo | <> | Zagreb GK | Sesvete | 2026 | 2027 | 1 | 52 | 2026-01-01 | 0:00 | 2027-12-31 | 23:59 | 24 months | periodical | bridge renewal km 425+966 - 427+555 (vijadukt Držićeva - Harambašićeva) |  | X | X | [7 empty] | Daily closures 6-8 hours and ocasionaly 72 hours closure |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb GK - Dugo Selo | <> | Sesvete | Dugo Selo | 2026 | 2027 | 1 | 52 | 2026-01-01 | 0:00 | 2027-12-31 | 23:59 | 24 months | periodical | construction of the railway stop |  | X | X | [7 empty] | Construction of the new railway stop Sesvetska Sela km 436+775. Several track closures in duration of 48 to 72 hours. |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Sesvete | <> | Sesvete | Sesvete | 2026 | 2026 | 1 | 26 | 2026-01-01 | 0:00 | 2026-06-30 | 23:59 | 6 months | periodical | Switch points replacement in station Sesvete |  | X | X | [7 empty] | Switch points replacement in station Sesvete |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Dugo Selo - Novska | < > | Dugo Selo | Novska | 2026 | 2031 | 44 | 52 |  |  |  |  | 4 years and 1 month | periodical | Upgrade, renewal, construction of the second track and construction of a new double-track line |  |  | X | [7 empty] | 8 hours day closure every working day from 7:00 am to 4:00 pm, occasional closures at weekends for up to 72 hours according to the needs of contractors, possible closures on the parts of the section (8 hours closure from 7:00 am to 4:00 pm and occasional closures of the line for up to 72 hours). If needed, possible closures longer than 72 hours. |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Novska - Slavonski Brod | <> | Sibinj | Okučani | 2026 | 2029 | 38 | 52 | 2026-10-01 | 0:00 | 2029-12-31 | 23:59 | 39 months | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Novska - Slavonski Brod | < > | Sibinj | Slavonski Brod | 2026 | 2027 | 34 | 52 | 2026-09-01 | 0:00 | 2027-12-31 | 23:59 | 16 months | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Novska - Vinkovci | < > | Andrijevci | Garčin | 2026 | 2027 | 34 | 52 | 2026-09-01 | 0:00 | 2027-12-31 | 23:59 | 16 months | periodical | Renewal of the left track km 198+480 - 206+260 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Novska - Vinkovci | < > | Strizivojna-Vrpolje | Andrijevci | 2026 | 2027 | 34 | 52 | 2026-09-01 | 0:00 | 2027-12-31 | 23:59 | 16 months | periodical | Renewal of the right track 188+500 - 197+400 |  |  | X | [7 empty] | Closures by day (Monday - Sunday) for 6 to 8 hours (as needed) |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Slavonski Brod - Vinkovci | < > | Strizivojna-Vrpolje | Ivankovo | 2026 | 2027 | 34 | 52 | 2026-09-01 | 0:00 | 2027-12-31 | 23:59 | 16 months | periodical | Renewal of the line section |  | X | X | [7 empty] | 6-8 hours daily closure every working day, occasional 72 hours closures depending on the needs of contractors. |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Tovarnik | < > | Tovarnik | Tovarnik | 2025 | 2026 | 5 | 39 |  |  |  |  | 20 months | periodical | Construction works in border station Tovarnik - alignment with Schengen border requirements |  |  | X | [7 empty] | Ocasionally daily 8 hours closures of tracks in border station Tovarnik |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Hrvatski Leskovac | Karlovac | 2026 | 2028 | 1 | 47 | 2026-01-01 | 0:00 | 2028-11-30 | 23:59 | 35 months | periodical | Construction of the second track and reconstruction of the existing track |  |  | X | [9 empty] | N |  | 2025-12-22 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | km 588+327 | km 588+600 | 2026 | 2027 | 38 | 34 | 2026-10-01 | 0:00 | 2027-08-31 | 23:59 | 11 months | periodical | Bridge reconstruction |  |  | X | [9 empty] | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Zalesina | Delnice | 2027 | 2027 | 13 | 43 | 2027-04-01 | 0:00 | 2027-10-31 | 23:59 | 7 months | periodical | Maintenance of the Sušica tunel |  |  | X | [9 empty] | N |  | 2025-12-22 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Lokve | Drivenik | 2027 | 2027 | 13 | 43 | 2027-04-01 | 0:00 | 2027-10-31 | 23:59 | 7 months | periodical | Maintenance of the track |  |  | X | [9 empty] | N |  | 2025-12-22 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Škrljevo | Rijeka | 2027 | 2027 | 13 | 52 | 2027-04-01 | 0:00 | 2027-12-31 | 23:59 | 9 months | periodical | Maintenance of the track |  |  | X | [9 empty] | N |  | 2025-12-22 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Drivenik | Škrljevo | 2027 | 2028 | 34 | 52 | 2027-09-01 | 0:00 | 2028-12-31 | 23:59 | 16 months | periodical | Renewal of the track |  |  | X | [9 empty] | N |  | 2025-12-22 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0078 |  | Zagreb - Rijeka | < > | Karlovac | Zvečaj | 2027 | 2027 | 1 | 52 | 2027-01-01 | 0:00 | 2027-12-31 | 23:59 | 12 months | periodical | Maintenance of the track |  |  | X | [9 empty] | N |  | 2025-12-22 | Medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  | Niš - Dimitrovgrad | < > | Sićevo | Dimitrovgrad | 2024 | 2026 | 35 | 51 |  |  |  |  | 2 years and 6 months | periodical | Civil engineering reconstruction of the Niš – Dimitrovgrad railway line | X1) | X2) | X | [7 empty] | 1) Total railway closure for 91 days in the second quarter of 2026. 2)Traffic functioning and works execution (from Tuesday 07.00 until Wednesday 19.00 and from Saturday 07.00 until Sunday 19.00) according to the dynamics 36/36/36/60 |  | N |  | 2025-12-22 | major | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0072 |  | Niš station | < > | 1. Crveni Krst 2. Trupale 3. Trupale | 1. Matejevac 2. Crveni Krst 3. Niš ranžirna | 2024 | 2026 | 1 | 40 |  |  |  |  | 33 months | periodical | Railway bypass Niš | X |  | X | [7 empty] | 1. Total railway closure for 122 days from April 2026. 2. During total closure of Crveni Krst - Matejevac 3. According to the dynamics 36/36/36/60 |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0072 |  | Niš - Dimitrovgrad | < > | Sićevo | Dimitrovgrad | 2024 | 2026 | 1 | 51 |  |  |  |  | 36 months | periodical | Electrification of the Niš – Dimitrovgrad railway line and railway bypass Niš |  |  | X | [7 empty] | Traffic functioning and works execution will be performed alternately during time intervals that are going to be agreed with the Contractor |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | planned
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2030 | 52 | 52 |  |  |  |  | 10 years | periodical | railway line km 22+554 to km 42+200 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2027 | 52 | 52 |  |  |  |  | 7 years | periodical | railway line km 42+200 to km 62+400 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Elin-Pelin | Kostenets | 2020 | 2029 | 52 | 52 |  |  |  |  | 9 years | periodical | railway line km 62+400 to km 73 +598 | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Kostenets | Septemvri | 2019 | 2028 | 52 | 52 |  |  |  |  | 9 years | periodical | railway line | X |  | X | [7 empty] | Modernization of railway infrastructure in accordance with the requirements to the railway infrastructure of the core TEN-T network as specified in Regulation 1315/2013 |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Voluyak | Sofia | 2023 | 2027 | 50 | 50 | 2023-12-10 |  | 2027-12-13 |  | 4 years | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be conducted under the conditions of full interruption of one of the running lines. Bypass line - Voluyak - Iliyantsi - Sofia |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Dragoman | Voluyak | 2023 | 2027 | 50 | 50 | 2023-12-10 |  | 2027-12-13 |  | 4 years | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Construction and repair works will be carried out under the conditions of full interruption of one of the running lines. The train traffic will be conducted along a newly built running line (the railway line is doubled) |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0052 |  |  | < > | Sofia station | Sofia station | 2023 | 2026 | 50 | 50 | 2023-12-10 |  | 2026-12-13 |  | 36 months | periodical | Modernization of the railway infrastructure |  | X | X |  |  |  | X |  |  |  | Interruption of traffic along the eastern part of the station tracks from track 8 to track 14. Partial isolation of the signalling equipment at the station. Bypass line - Voluyak - Iliyantsi - Yana - Kazichene |  | N |  | 2025-12-22 | medium | 1,2,3,4,5,6,7 | 1 |  |  |  |  | publication
0083 | RFI-2026-102 | Venezia - Trieste | < > | Aurisina | Villa Opicina | 2026 | 2026 | 1 | 31 | 2026-01-01 |  | 2026-08-01 |  | 40x270' | periodical | Others | T | [9 empty] | Villa Opicina - Bivio D'Aurisina Line upgrading Attività di piazzale - posa canalizzazioni, posa cavi, enti di campo - 2 | 80, 81 | N |  | 2025-06-04 | Minor |  |  | <10%
0083 | RFI-2026-08 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2026 | 2026 | 1 | 50 | 2026-01-01 | 0:00 | 2026-12-12 | 4:00 | 240' | periodical | Others | T | [7 empty] | 120 |  | IPO: total closure of 240' Fri/Sat to Tue/Wed; station renewal | 80, 81 | Y |  | 2023-11-23 | Minor
0083 | RFI-2026-76 | Venezia - Trieste | < > | Bivio D'Aurisina | Trieste Centrale | 2026 | 2026 | 1 | 14 | 2026-01-01 |  | 2026-03-31 |  | 15x 240' | periodical | Bridge | T | [9 empty] | Extraordinary maintenance on a bridge km 10+473,60 | 80, 81 | Y |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2026-75 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2026 | 2026 | 1 | 31 | 2026-01-01 |  | 2026-08-01 |  | 50x 240' | periodical | Bridge | T | [9 empty] | 50 line interruptions for the new overpass after the removal of the level crossing in Prosecco + line Upgrading | 81 | N |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2026-101 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 1 | 53 | 2026-01-01 |  | 2026-12-31 |  | 60x12h | periodical | Others |  | ST | [8 empty] | Trieste Campo Marzio Fascio Aquilinia (interruzioni relative al fascio) for Consolidation of "San Pantaleone" tunnel | 80, 81 | N |  | 2025-06-04 | High |  |  | 10% - 30%
0083 | RFI-2026-45 | Venezia - Trieste | > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 1 | 50 | 2026-01-01 |  | 2026-12-12 |  | 137x 300'-390' | periodical | Others |  | ST | [8 empty] | improvement of the railway systems serving the port of trieste |  |  |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2026-12 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 1 | 42 | 2026-01-01 | 23:00 | 2026-10-17 | 4:00 | 240' | periodical | Others | T | [7 empty] | 60 |  | From Mo/Tu to Sun/Mo - late trains for the direction North-South at Tarvisio station for activities of others Ims must arrive to Trieste Campo Marzio before the 11:00 p.m. in order to respect this important works (94_2026_ed.dec.23) | 80, 81 | Y |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2026-105 | Venezia - Trieste | < > | Trieste Centrale | Trieste Centrale | 2026 | 2026 | 3 | 49 | 2026-01-13 |  | 2026-12-05 |  | 200x270' | periodical | Track & Rail |  | ST | [8 empty] | Trieste Central Station renewal on electrical line (Phase 2/2) | 80, 81 | N |  | 2025-06-04 | Minor |  |  | 10% - 30%
0083 | RFI-2026-139 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2026 | 2026 | 10 | 11 | 2026-03-06 |  | 2026-03-09 |  | 52h | continuous | Others | T |  |  |  |  | C |  |  | Y |  | PRG + ACC Villa Opicina | 81 | N |  | 2024-11-18 | Medium |  |  | >50%
0083 | RFI-2026-73 | Venezia - Trieste | < > | Bivio D'Aurisina | Trieste Centrale | 2026 | 2026 | 14 | 24 | 2026-04-01 |  | 2026-06-12 |  | 45x 240' | periodical | Switch | T | [9 empty] | 45 line interruptions of 4h for works on the overpass km 8+700 | 80, 81 | Y |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2026-138 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2026 | 2026 | 14 | 15 | 2026-04-03 |  | 2026-04-05 |  | 52h | continuous | Others | T |  |  |  |  | C |  |  | Y |  | PRG + ACC Villa Opicina | 81 | N |  | 2024-11-18 | Medium |  |  | >50%
0083 | RFI-2026-109 | Ljubljana - Udine | < > | Aurisina | Villa Opicina | 2026 | 2026 | 18 | 27 | 2026-05-01 |  | 2026-06-30 |  | 29 x 270' | periodical | Others | T | [9 empty] | Villa Opicina - Bivio D'Aurisina Line upgrading Appalto 4 - Prove di integrazione | 80, 81 | N |  | 2025-06-04 | Minor |  |  | <10%
0083 | RFI-TS-25-19 | Udine - Trieste | < > | Bivio D'Aurisina | Villa Opicina | 2026 | 2026 | 28 | 29 | 2026-07-11 |  | 2026-07-12 |  | 12h | continous | Others | T | [9 empty] | new overpass after the removal of the level crossing in Prosecco (TS-26-27) |  |  |  |  | Minor |  |  | >50%
0083 | RFI-2026-15 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 33 | 34 | 2026-08-14 |  | 2026-08-16 |  | 72h | continuous | Others | T | [7 empty] | Y |  | PRG Trieste Campo Marzio - activation phase 5 (TS-26-04) | 81 | N |  | 2023-11-23 | Minor |  |  | 10% - 30%
0083 | RFI-2026-121 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 33 | 34 | 2026-08-14 |  | 2026-08-19 |  | 96h | continuous | Others | T | [9 empty] | Trieste Campo Marzio - Works for Phase 5 | 80, 81 | N |  | 2025-06-04 | Medium |  |  | >50%
0083 | RFI-2026-130 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2026 | 2026 | 45 | 49 | 2026-11-02 |  | 2026-11-30 |  | 20x300' | periodical | Track & Rail |  | ST | [8 empty] | IPO nocturnal closure of 300' for track (I,II) for track and switches renewal | 80, 81 | N |  | 2025-06-04 | Minor |  |  | 10% - 30%
0083 | RFI-2026-131 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2026 | 2026 | 45 | 47 | 2026-11-02 |  | 2026-11-20 |  | 1x6h | periodical | Track & Rail | T | ST | [8 empty] | IPO nocturnal closure of 300' for track (III, IV, V, VI, VIII) and switches renewal + a total closure of 6h | 80, 81 | N |  | 2025-06-04 | Minor |  |  | 10% - 30%
0083 | RFI-2027-04 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2026 | 2027 | 51 | 50 | 2026-12-13 | 0:00 | 2027-12-11 | 4:00 | 240' | periodical | Others | T | [7 empty] | 120 |  | IPO: total closure of 240' Fri/Sat to Tue/Wed; station renewal | 80, 81 |  |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2027-05 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2027 | 51 | 50 | 2026-12-13 | 23:00 | 2027-12-11 | 4:00 | 300' | periodical | Others | T | [7 empty] | 60 |  | From Mo/Tu to Sun/Mo - late trains for the direction North-South at Tarvisio station for activities of others Ims must arrive to Trieste Campo Marzio before the 11:00 p.m. in order to respect this important works | 80, 81 |  |  | 2024-11-18 | Minor |  |  | <10%
0083 | RFI-2027-33 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 52 | 53 | 2026-12-26 |  | 2026-12-31 |  | 72h | continuous | Others | T | [9 empty] | PRG E ACC TRIESTE C.M station interruption (1 for Fasci Servola and Aquilina) | 80, 81 |  |  | 2026-03-02 | Medium |  |  | >50%
0083 | RFI-2025-61 | Ljubljana - Udine | < > | Villa Opicina | Villa Opicina | 2027 | 2027 | 22 | 26 | 2027-06-25 |  | 2027-06-27 |  | 40h | continuous | Others | T |  |  |  |  | C | R |  | Y |  | PRG + ACC Villa Opicina (TS-25-20), cancellation of the trains (rerouting via Jesenice possible) Full closure of the station | 81 | N |  | 2026-03-02 | Medium |  |  | >50%
0083 | RFI-2027-33 | Venezia - Trieste | < > | Trieste Campo Marzio | Trieste Campo Marzio | 2026 | 2026 | 33 | 34 | 2027-08-14 |  | 2027-08-19 |  | 72h | continuous | Others | T | [9 empty] | PRG and ACC Trieste 2 station interruption (1 for Fasci Servola and Aquilina) | 80, 81 |  |  | 2025-11-17 | Medium |  |  | >50%
0083 | RFI-TS-26-05 | Ljubljana - Udine | < > | Bivio D'Aurisina | Villa Opicina | 2027 | 2027 | 53 | 53 | 2027-12-28 |  | 2027-12-30 |  | 36h | continuous | Others | T | [7 empty] | 120 |  | Line upgrading (TS-26-05) | 80, 81 |  |  | 2024-11-18 | Medium |  |  | >50%
0083 | RFI-TS-27-08 | Ljubljana - Udine | < > | Bivio D'Aurisina | Villa Opicina | 2028 | 2028 | 23 | 27 | 2028-06-01 |  | 2028-06-30 |  | 40h | continuous | Others | T | [7 empty] | Y |  | PRGe ACC Villa Opicina - attivazione fase 3 (TS-27-08) | 80, 81 |  |  | 2024-11-18 | Medium |  |  | >50%
0073 |  | Palaiofarsalos-Kalambaka | < > | Palaiopharsalos | Kalambaka | 2023 | 2026 | 37 | 53 | 2023-09-06 |  | 2026-12-30 |  | 1213d | continuous | Restoration of the single-track railway | X | [9 empty] | Restoration of the single-track railway line from Palaiofarsalos to Kalambaka, in identified sections of the line, following the natural disasters ‘Daniel’ and ‘Elias |  |  |  | 2025-12-19 | major | 1,2,3,4,5,6,7
0073 |  | Thessaloniki - Athina | < > | Larisa | Leianokladi | 2024 | 2026 | 1 | 27 | 2024-01-01 |  | 2026-06-30 |  | 746d | Continuous | Maintenance |  | LT | S | [7 empty] | one track closed and the other one with speed restriction |  |  |  | 2025-12-19 |  | 1,2,3,4,5,6,7
Formulas:
Week = WEEKNUM([Period from])
To = WEEKNUM([Period to])
New
Changed
Deleted
Map
Show all

## TCR Map ÖBB-I
Rosenbach - Jesenice 1.2.2027 - 22.11.2027
Schwarzach-St.Veit - Mallnitz-Obervellach 8.2.2027 - 9.7.2027
Jesenice - gesamt - Rosenbach 13.12.2026 - 27.9.2027
Bruck a.d.Mur - gesamt 24.10.2027 - 7.11.2027
Mixnitz-Bärenschützklamm 7.5.2027 - 26.5.2027
Rohr-Bad Hall - Kirchdorf a.d.Krems 23.8.2027 - 3.9.2027
Marchtrenk - Sbl Mak 1P 2.8.2027 - 13.9.2027
Mixnitz-Bärenschützklamm 29.5.2027 - 15.6.2027
Due to high number of TCRs on WBEM RFC line sections in Austria, only TCRs with major and high impact on traffic are shawn on the map.

## TCR Map SŽ-I
Ljubljana - closure of tracks 1.1.2026 - 2.10.2026, upgrading of station, building new tracks - Phase B and C
Ljubljana - closure of tracks 1.1.2027-1.10.2027 - Phase D
Ljubljana Šiška - Kranj 25.9.-11.10.2026 total closure (maintenance)
Jesenice - closure of tracks 6.2.2026 - 27.9.2027, upgrading of station, building new tracks
Sava - Litija 4.5.-31.5.2026, left/right track closure maintenance
Krško - station upgrading 25.1.-20.9.2027
Brezovica - Preserje 1.4.-10.5.2026, one track closure (upgrading of section)
Borovnica - Verd 1.7.-10.12.2026, left/right track closure, bridge upgrading
Preserje, Brezovica - closure of tracks (stations upgrading, modernization) 10.1.-25.6.2026
Borovnica - Verd 1.7.-11.12.2027 left/right track closure, bridge upgrading

## TCR Map HŽI
Savski Marof - Zaprešić 2024 - 2026, periodical, bridges reconstruction and switch point replacement Zagreb GK - Sesvete - Dugo Selo 2024 - 2027, switch point replacement, construction of the new stop, bridge construction Dugo Selo - Novska 2026 - 2031, periodical, upgrade, renewal, construction of the second track and construction of a new double-track line Andrijevci - Garčin, Strizivojna-Vrpolje - Andrijevci, Strizivojna-Vrpolje - Ivankovo, Sibinj - Slavonski Brod 1.9.2026 - 31.12.2027, renewal of the tracks Tovarnik station 2025 - 2026, completion of works, Schengen adjustment Zagreb GK 1.9.2026 - 31.12.2027, renewal of the tracks and switch point replacement Sibinj - Okučani 1.10.2026 - 31.12.2029, renewal of the tracks Zagreb RK 1.12.2025 - 31.12.2027, switch point replacement Hrvatski Leskovac - Karlovac 1.1.2026 - 30.11.2028, construction of the second track and reconstruction of the existing track km 588+327 - km 588+600 1.10.2026 - 31.8.2027, bridge reconstruction Zalesina - Delnice 1.4.2027 - 31.10.2027, maintenance of the Sušica tunel Lokve - Drivenik 1.4.2027 - 31.10.2027, maintenance of the track Škrljevo - Rijeka 1.4.2027 - 31.12.2027, maintenance of the track Drivenik - Škrljevo 1.9.2027 - 31.12.2028, renewal of the track Karlovac - Mrzlo Polje - Zvečaj 1.1.2027 - 31.12.2027, maintenance of the track

## TCR Map IŽS
Niš station 2024 - 2026, periodical, Railway bypass Niš
Sićevo – Dimitrovgrad 2024 – 2026, periodical, Reconstruction & Electrification of the Niš – Dimitrovgrad railway line

## TCR Map NRIC
Elin-Pelin - Kostenets
December 2020 - December 2030
Modernization of the railway infrastructure
Dragoman – Voluyak
December 2023 - December 2027
Modernization of the railway infrastructure
Voluyak – Sofia
December 2023 - December 2027
Modernization of the railway infrastructure
Sofia station
December 2023 - December 2026
Modernization of the railway infrastructure
Kostenets - Septemvri
December 2019 - December 2028
Modernization of the railway infrastructure

## TCR Map RFI
Trieste Campo Marzio, 1.1.2026. - 31.12.2026., 14.8.2026. - 19.8.2026., 26.12.2026. - 31.12.2026., Consolidation of "San Pantaleone" tunnel, works for Phase 5, PRG E ACC TRIESTE C.M. station interruption (1 for Fasci Servola and Aquilina)
Aurisina - Villa Opicina, 6.3.2026. - 9.3.2026., 3.4.2026. - 5.4.2026., PRG + ACC Villa Opicina
Villa Opicina, 25.6.2026. - 27.6.2026., PRG + ACC Villa Opicina (TS-25-20), cancellation of the trains (rerouting via Jesenice possible) Full closure of the station
Bivio D'Aurisina - Villa Opicina, 28.12.2026. - 30.12.2026., Line upgrading (TS-26-05)
Only TCRs with high and medium impact on traffic are shawn on the map.

## TCR Map OSE SMSA
Palaiofarsalos - Kalambaka 6.9.2023 - 30.12.2026, Restoration of the single-track railway line from Palaiofarsalos to Kalambaka, in identified sections of the line, following the natural disasters ‘Daniel’ and ‘Elias
Larisa - Leianokladi 1.1.2024 - 30.6.2026, One track closed and the other one with speed restriction

## TCR Map MAV
There are no planned TCRs in TT period 2026 on Hungarian WBEM RFC line section. The TCRs in TT period 2027 will be added afterwards (in updated TCRs list).